## Sprint Retro
Sprint Retrospective – Partially Filled Example
Sprint Details |  |  | Sprint Summary
Sprint Name / No. | Sprint 12 |  | Total Stories | 4
Sprint Start Date | 01-Sep-2026 |  | Completed Stories | 2
Sprint End Date | 14-Sep-2026 |  | Incomplete Stories | 2
|  |  | New Backlog Stories Created | 2
|  |  | Completion % | 50%
Story Status / Task Tracking
Story No. | Task | Task Status | Task Owner | Reason for Not Completing Task | New Backlog Story No. | Story Result
ST-101 | Create login UI | Completed | Ayesha |  |  | Completed
ST-101 | Implement authentication API | Completed | Rahim
ST-101 | Add login validation tests | Completed | Nabila
ST-102 | Create profile page | Completed | Ayesha |  |  | Incomplete
ST-102 | Implement profile update API | Blocked | Rahim | Dependency on identity-service API was not available. | BL-201
ST-102 | Add profile tests | Completed | Nabila
ST-103 | Build export report screen | Completed | Ayesha |  |  | Incomplete
ST-103 | Generate PDF report | Deferred | Farhan | Scope was larger than estimated and remaining work was moved to backlog. | BL-202
ST-104 | Add audit-log table | Completed | Rahim |  |  | Completed
ST-104 | Add audit-log search | Completed | Farhan

## New Backlog
New Backlog Stories for Incomplete Tasks
At retrospective time, New Backlog Status is limited to To Do or Ready. In Progress begins only after a story is selected during Sprint Planning.
New Backlog Story No. | Source Sprint Story No. | Incomplete Task | Owner | Reason / Context | Priority | Backlog Status | Notes / Acceptance Criteria
BL-201 | ST-102 | Complete profile update API | Rahim | Identity-service dependency was unavailable during Sprint 12. | High | Ready | Complete API integration and verify profile update end-to-end.
BL-202 | ST-103 | Complete PDF report generation | Farhan | Remaining PDF-generation work exceeded the sprint estimate. | Medium | To Do | Refine estimate and split PDF rendering from formatting if needed.

## Retrospective
Sprint Retrospective Discussion & Actions
A. What Went Well
No. | Observation / Feedback | Impact | Action / Follow-up | Owner | Target / Notes
1 | Authentication work was completed as planned. | High | Keep early API/UI coordination in the next sprint. | Team | Continue the same practice.
2 | Audit-log story was completed without carry-over. | Medium | Reuse the same task breakdown approach. | Farhan | Apply to similar backend stories.
3
4
5
6
7
8
B. What Didn't Go Well
No. | Observation / Feedback | Impact | Action / Follow-up | Owner | Target / Notes
1 | Profile API was blocked by an external dependency. | High | Identify external dependencies before sprint commitment. | Rahim | Before next Sprint Planning.
2 | PDF-report work was underestimated. | Medium | Break reporting work into smaller estimable tasks. | Farhan | During backlog refinement.
3
4
5
6
7
8
C. What Can Be Improved
No. | Observation / Feedback | Impact | Action / Follow-up | Owner | Target / Notes
1 | Dependency readiness should be checked earlier. | High | Add a dependency-readiness check to refinement. | Team | Starting next refinement session.
2 | Large technical tasks need smaller acceptance units. | Medium | Split large tasks before they enter Sprint Planning. | Scrum Team | Next sprint backlog.
3
4
5
6
7
8

## Lists
Task Status | New Backlog Status | Priority | Impact
Not Started | To Do | High | High
In Progress | Ready | Medium | Medium
Blocked |  | Low | Low
Completed
Deferred