## Team
Ordinis — Project Team
SL | Student ID | Student Name | Role
1 | 23201023 | Md. Nazmuz Saif | Software Developer (Programmer)
2 | 23201008 | Fawjiya Fahima Eifa | System Designer / Software Architect
3 | 23201055 | Montasim Kabir Mahin | Project Manager
4 | 23201029 | Sadia Jahan Disha | System Analyst / Business Analyst
5 | 23201050 | Md. Tahsin Rahman Khan | Tester / Quality Assurance (QA) Engineer

## Product Backlog
Ordinis — Product Backlog
Organization Operating System (OrgOS) — Multi-Tenant SaaS Platform
Backlog ID | Epic / Module | User Story | Priority | Story Points | Status | Sprint Assigned | Owner
PB-01 | Authentication & Onboarding | As a Company Owner, I want to self-register my company and create my CEO account in one step, so that I can start using Ordinis without manual setup by an admin. | High | 5 | Done | Sprint 1 | Md. Nazmuz Saif
PB-02 | Authentication & Onboarding | As a User, I want to log in with my email and password, so that I can securely access my company's Ordinis dashboard. | High | 3 | Done | Sprint 1 | Md. Nazmuz Saif
PB-03 | Authentication & Onboarding | As a User, I want my login blocked if my company's subscription is suspended, so that access matches billing status. | Medium | 2 | Done | Sprint 1 | Md. Nazmuz Saif
PB-04 | Organization Management | As a CEO, I want to create and manage Departments for my company, so that I can structure my organization the way I need. | High | 3 | Done | Sprint 1 | Md. Nazmuz Saif
PB-05 | Organization Management | As a CEO, I want to create and manage Designations (job titles), so that employees can be labeled correctly without affecting their access rights. | High | 3 | Done | Sprint 1 | Md. Nazmuz Saif
PB-06 | Organization Management | As a CEO, I want to add Employees and assign each one a manager (reports-to), so that my real reporting hierarchy is reflected in the system. | High | 5 | Done | Sprint 1 | Md. Nazmuz Saif
PB-07 | Organization Management | As a Department Head, I want the system to resolve my full list of subordinates automatically, so that I can see my whole team regardless of hierarchy depth. | Medium | 5 | Done | Sprint 2 | Md. Nazmuz Saif
PB-08 | RBAC (Roles & Permissions) | As a CEO, I want to create custom Roles as bundles of Permissions, so that access rights are independent of job titles. | High | 5 | Done | Sprint 2 | Montasim Kabir Mahin
PB-09 | RBAC (Roles & Permissions) | As a CEO, I want to assign one or more Roles to any Employee, so that I can grant exactly the access that person needs. | High | 3 | Done | Sprint 2 | Sadia Jahan Disha
PB-10 | RBAC (Roles & Permissions) | As the System, I want every protected action to check a specific Permission codename, so that access control never depends on a hardcoded job-title check. | High | 5 | Done | Sprint 2 | Fawjiya Fahima Eifa
PB-11 | RBAC (Roles & Permissions) | As the System, I want the unfinished Sprint 2 RBAC work and the gaps left in PB-01, PB-07, and PB-10 closed, so that every protected action is really permission-checked and no company can reach another company's data. | High | 8 | Done | Sprint 3 | Md. Nazmuz Saif
PB-12 | Approval Workflow | As a CEO, I want to define a multi-step Approval Chain for leave requests, so that my company's actual approval process is enforced by the system. | Medium | 5 | Done | Sprint 3 | Md. Nazmuz Saif
PB-13 | Approval Workflow | As an Approver, I want to approve or reject a pending request with a comment, so that decisions and reasons are recorded. | Medium | 3 | Done | Sprint 3 | Md. Nazmuz Saif
PB-14 | Task Management | As a Department Head, I want to create Tasks and assign them to Employees with a priority and deadline, so that work is tracked centrally. | High | 5 | Done | Sprint 3 | Montasim Kabir Mahin
PB-15 | Task Management | As an Employee, I want to submit a Task only through valid status changes, so that progress reporting stays accurate and consistent. | High | 3 | Done | Sprint 3 | Montasim Kabir Mahin
PB-16 | UI & Experience | As a User, I want every screen to use the same status badges, metric cards, empty states, and chart cards, so that the product looks consistent and is easy to learn. | High | 3 | Done | Sprint 3 | Md. Nazmuz Saif
PB-17 | Approval Workflow | As a Department Head, I want to delegate my approval authority to someone else for a date range, so that requests are not stuck when I'm on leave. | Medium | 3 | Done | Sprint 3 | Md. Tahsin Rahman Khan
PB-18 | RBAC (Roles & Permissions) | As an Accountant, I want to define a Salary Structure per employee and keep salary and financial data restricted to users with finance permission, so that confidential pay data stays private regardless of hierarchy. | High | 3 | Incomplete | Sprint 3 | Fawjiya Fahima Eifa
PB-19 | Attendance & Leave | As an Employee, I want to check in and check out once per day, so that my attendance is recorded accurately. | High | 3 | Done | Sprint 3 | Sadia Jahan Disha
PB-20 | UI & Experience | As a User, I want a polished app shell (grouped sidebar, navbar, notification dropdown, company switcher, plan badge), so that the product feels professional and is easy to navigate. | High | 5 | Done | Sprint 3 | Md. Nazmuz Saif
PB-21 | Quality & Setup | As a Developer, I want all list endpoints paginated and the project set up with requirements, environment example, and README, so that the system scales and can be installed by anyone. | Medium | 3 | Done | Sprint 4 | Md. Nazmuz Saif
PB-22 | UI & Experience | As a User, I want a dashboard made for my Role (CEO, Manager, HR, Accountant, Employee), so that I see only what matters to my work. | High | 8 | Done | Sprint 4 | Md. Nazmuz Saif
PB-23 | Billing & Platform Admin | As the Platform Owner, I want a Break-Glass access process for support, so that I can help a client without having default access to their data. | Medium | 5 | Done | Sprint 4 | Md. Nazmuz Saif
PB-24 | Billing & Platform Admin | As the Platform Owner, I want an admin panel for companies, support tickets, and Break-Glass requests, so that I can operate the platform without seeing client data by default. | Medium | 5 | Done | Sprint 4 | Md. Nazmuz Saif
PB-25 | Task Management | As a Department Head, I want to see Tasks on a Kanban board (To Do, In Progress, Review, Done), so that I can see team progress at a glance. | High | 5 | Done | Sprint 4 | Montasim Kabir Mahin
PB-26 | Task Management | As an Employee, I want to log daily progress on a multi-day task, so that my manager can see progress without me uploading code or files. | Medium | 3 | Done | Sprint 4 | Montasim Kabir Mahin
PB-27 | Notifications | As a User, I want a personalized Action Inbox combining my pending tasks, approvals, and notifications, so that I know what needs my attention in one place. | Medium | 5 | Done | Sprint 4 | Md. Tahsin Rahman Khan
PB-28 | Payroll | As an Accountant, I want to generate a Payslip for a given month without creating duplicates, so that payroll runs stay accurate. | High | 5 | Done | Sprint 4 | Sadia Jahan Disha
PB-29 | Attendance & Leave | As an Employee, I want to apply for leave and have my balance validated automatically, so that I can't accidentally over-request leave. | High | 5 | Done | Sprint 4 | Fawjiya Fahima Eifa
PB-30 | Attendance & Leave | As an Employee, I want my leave request to follow my company's Approval Chain, and approvers to approve or reject it, so that leave is decided by the right people in the right order. | High | 5 | Done | Sprint 5 | Md. Nazmuz Saif
PB-31 | Quality & Setup | As a Presenter, I want a command that fills the system with realistic demo data, so that every screen looks real during the demo. | High | 3 | Done | Sprint 5 | Md. Nazmuz Saif
PB-32 | Quality & Setup | As a Developer, I want a Selenium regression suite and backend tests, so that changes cannot silently break working features. | High | 5 | Done | Sprint 5 | Md. Nazmuz Saif
PB-33 | Quality & Setup | As a Reviewer, I want the SRS, SDS, and structure documents to match the delivered system, so that the documents are trustworthy. | Medium | 3 | Done | Sprint 5 | Md. Nazmuz Saif
PB-34 | Quality & Setup | As a Team, I want a full demo rehearsal with a bug-fix buffer, so that the final presentation runs smoothly. | High | 5 | Done | Sprint 5 | Md. Nazmuz Saif
PB-35 | Audit & Analytics | As a CEO, I want an Analytics page with attendance and task-completion charts, so that I can see my company's health. | Medium | 5 | Done | Sprint 5 | Montasim Kabir Mahin
PB-36 | Audit & Analytics | As a CEO, I want every sensitive action logged in an append-only Audit Log, so that I have a tamper-proof history of what happened. | High | 5 | Done | Sprint 5 | Md. Tahsin Rahman Khan
PB-37 | Audit & Analytics | As a CEO, I want an Audit Log page with module filter and export, so that I can review who did what and when. | High | 3 | Done | Sprint 5 | Md. Tahsin Rahman Khan
PB-38 | Billing & Platform Admin | As a CEO, I want a Billing page showing my plan, employee limit, and invoices, so that I can manage my subscription. | Medium | 3 | Done | Sprint 5 | Sadia Jahan Disha
PB-39 | Attendance & Leave | As an Employee, I want a monthly attendance calendar with summary cards, so that I can see my attendance history at a glance. | Medium | 3 | Done | Sprint 5 | Fawjiya Fahima Eifa
PB-40 | RBAC (Roles & Permissions) | As an Accountant, I want the unfinished Sprint 3 Salary Structure work (database, API, self-test and the Edit/Delete screen) completed, so that confidential pay data can be defined, edited and deleted per employee and stays restricted to users with the finance Permission. | High | 3 | Done | Sprint 4 | Md. Nazmuz Saif
PB-41 | RBAC (Roles & Permissions) | As a CEO, I want every Permission to have a clear name, a plain-language description and a module, kept in one place in the code, and the Roles page to offer only real Permissions, so that a Role I create keeps every Permission I tick and I know what each one allows. | High | 5 | To Do | Sprint 6 | Md. Nazmuz Saif
PB-42 | RBAC (Roles & Permissions) | As a CEO, I want a Roles page with Permissions in sections, a detail page for each Role that explains what every Permission lets people do, and the ability to edit a Role, so that I can design access without guessing. | High | 5 | To Do | Sprint 6 | Md. Nazmuz Saif
PB-43 | Profile & Identity | As an employee, I want my full name and profile details stored and editable by me, so that the system shows real names everywhere and I keep my own details current. | High | 5 | To Do | Sprint 6 | Md. Nazmuz Saif
PB-44 | Profile & Identity | As any user (employee, CEO or Platform Admin), I want a My Profile page where I see and edit my own details, so that I keep my information current myself. | High | 5 | To Do | Sprint 6 | Md. Nazmuz Saif
PB-45 | Profile & Identity | As a CEO and as an employee, I want a safe way to change my password and a temporary password for new employees, so that nobody has to share a password. | High | 5 | To Do | Sprint 6 | Md. Nazmuz Saif
PB-46 | Organization Management | As a CEO or HR user, I want an Employee detail page with the full profile and the Permissions that person really has, so that I can see exactly who someone is and what they can do. | High | 5 | To Do | Sprint 6 | Md. Nazmuz Saif
PB-47 | Attendance & Leave | As a CEO or a manager with the Permission, I want to pick an employee from a dropdown and see their attendance for a month, so that I know how many days they came and at what times. | High | 5 | To Do | Sprint 6 | Md. Nazmuz Saif
PB-48 | Billing & Platform Admin | As the Platform Owner, I want every company's subscription to have a start and end date, a days-left count, automatic reminders before it ends and a restricted mode after it ends, so that unpaid companies stop using the product without being locked out of paying. | High | 8 | To Do | Sprint 6 | Md. Nazmuz Saif
PB-49 | Billing & Platform Admin | As a company owner, I want to choose a plan for any number of months, pay by bKash, Nagad or bank transfer outside the system and submit the payment details, so that the platform team can check and approve it and my plan starts. | High | 8 | To Do | Sprint 6 | Md. Nazmuz Saif
PB-50 | Billing & Platform Admin | As a new client, I want to register, choose a plan and duration, pay and submit my payment details, and wait for approval, so that my company starts only after my payment is checked. | High | 5 | To Do | Sprint 6 | Md. Nazmuz Saif
PB-51 | Billing & Platform Admin | As the Platform Owner, I want a Payments page to review the payments companies submit and a Subscriptions page that shows every company's days left, so that I approve what I verified and see who expires soon. | High | 5 | To Do | Sprint 6 | Montasim Kabir Mahin
PB-52 | Billing & Platform Admin | As a CEO, I want a Billing timeline showing how many days my plan has left, a Renew button with an invoice to pay, and a detail page for every invoice, so that I always know when and how much to pay. | High | 8 | To Do | Sprint 6 | Montasim Kabir Mahin
PB-53 | Organization Management | As a CEO or Department Head, I want a detail page for each Department and each Designation, so that I can see who is in it, what they do and what work is running. | High | 8 | To Do | Sprint 6 | Md. Tahsin Rahman Khan
PB-54 | Billing & Platform Admin | As a CEO, I want to request a plan change, see the extra amount to pay, pay it and have the admin approve it, so that my plan changes only after payment. | Medium | 5 | To Do | Sprint 6 | Md. Tahsin Rahman Khan
PB-55 | Billing & Platform Admin | As the Platform Owner, I want a detail page for each company with its plan, subscription timeline, owner contact, size and support history, so that I can help a company without opening its data. | Medium | 5 | To Do | Sprint 6 | Sadia Jahan Disha
PB-56 | Billing & Platform Admin | As the Platform Owner, I want a dashboard showing companies by state, revenue, dues and what needs my attention, so that I can see the health of the platform at a glance. | Medium | 5 | To Do | Sprint 6 | Sadia Jahan Disha
PB-57 | Billing & Platform Admin | As the Platform Owner and as a company user, I want a note on every suspend or activate, a way to request access to a company, a way to send a support request from inside my company, and a sidebar without unfinished items, so that every action is explained and every menu item works. | High | 5 | To Do | Sprint 6 | Fawjiya Fahima Eifa
PB-58 | Quality & Setup | As a Team, I want the tests, documents and demo script to match the Sprint 6 system and one more full rehearsal, so that the final build is ready to present. | High | 5 | To Do | Sprint 6 | Fawjiya Fahima Eifa

## Sprint 1
Ordinis — Sprint 1 Planning
Sprint Duration: Sep 1 – Sep 9
Sprint Goal: Stand up Company onboarding, authentication, and the core Organization structure (Department, Designation, Employee with hierarchy) so a company can self-register and build its org chart.
Selected Stories for this Sprint
Story ID | User Story | Owner | Story Points | Acceptance Criteria
ST-101 | As a Company Owner, I want to self-register my company and create my CEO account in one step, so that I can start using Ordinis without manual setup by an admin. | Md. Nazmuz Saif | 5 | - Registration form creates Company, CompanySettings, CEO Designation, User, and Employee in one atomic transaction - A valid JWT is returned immediately - Registration fails cleanly (no partial records) if any step fails
ST-102 | As a User, I want to log in with my email and password, so that I can securely access my company's Ordinis dashboard. | Md. Nazmuz Saif | 3 | - Valid credentials return an access token and a refresh token - Invalid credentials return a generic error (no enumeration) - Access token works on a protected endpoint; refresh token issues a new access token
ST-103 | As a User, I want my login blocked if my company's subscription is suspended, so that access matches billing status. | Md. Nazmuz Saif | 2 | - Login from a suspended company returns a specific error and no token - An already-issued token from a since-suspended company is rejected on the next call
ST-104 | As a CEO, I want to create and manage Departments for my company, so that I can structure my organization the way I need. | Md. Nazmuz Saif | 3 | - CRUD works for Departments, scoped strictly to the CEO's own company - Accessing another company's Department by ID returns 404
ST-105 | As a CEO, I want to create and manage Designations (job titles), so that employees can be labeled correctly without affecting their access rights. | Md. Nazmuz Saif | 3 | - CRUD works for Designations, scoped to the CEO's own company - Creating/removing a Designation has no effect on any Employee's permissions
ST-106 | As a CEO, I want to add Employees and assign each one a manager (reports-to), so that my real reporting hierarchy is reflected in the system. | Md. Nazmuz Saif | 5 | - Employee can be created with Department, Designation, and reports_to - Hierarchy supports any depth without code changes - An Employee cannot be set as their own manager
Task Breakdown — one owner does the full story (Design → Database → Backend → Frontend → Self-Test)
Story ID | Category | Task | Owner | Estimate (hrs) | Status
ST-101 | Design | Design Company + CompanySettings + CEO Designation data model and registration sequence | Md. Nazmuz Saif | 3 | Done
ST-101 | Database | Create and verify migrations for Company, CompanySettings, Designation, User, Employee | Md. Nazmuz Saif | 2 | Done
ST-101 | Backend | Build atomic CompanyRegisterSerializer (transaction-wrapped) + CompanyRegisterView | Md. Nazmuz Saif | 4 | Done
ST-101 | Frontend | Build Company Registration page (form, validation, API call) | Md. Nazmuz Saif | 3 | Done
ST-101 | Self-Test | Self-test registration with valid data and with a missing required field | Md. Nazmuz Saif | 1 | Done
ST-102 | Design | Design JWT token structure (claims: email, company_id) and refresh flow | Md. Nazmuz Saif | 2 | Done
ST-102 | Backend | Configure djangorestframework-simplejwt; build CustomTokenObtainPairSerializer; wire login/refresh endpoints | Md. Nazmuz Saif | 3 | Done
ST-102 | Frontend | Build Login page (form, error display, token storage) | Md. Nazmuz Saif | 3 | Done
ST-102 | Self-Test | Self-test login with valid and invalid credentials | Md. Nazmuz Saif | 1 | Done
ST-103 | Backend | Add is_active check to Company model and login serializer; build IsCompanyActive permission class | Md. Nazmuz Saif | 3 | Done
ST-103 | Self-Test | Self-test login attempt from a suspended-company account | Md. Nazmuz Saif | 1 | Done
ST-104 | Design | Design Department schema (company-scoped) | Md. Nazmuz Saif | 1 | Done
ST-104 | Database | Create Department model and migration | Md. Nazmuz Saif | 1 | Done
ST-104 | Backend | Build DepartmentSerializer + DepartmentViewSet (company-filtered queryset) | Md. Nazmuz Saif | 2 | Done
ST-104 | Frontend | Build Departments page (list, create, edit, delete) | Md. Nazmuz Saif | 3 | Done
ST-104 | Self-Test | Self-test Department CRUD and cross-tenant isolation | Md. Nazmuz Saif | 1 | Done
ST-105 | Design | Design Designation schema (company-scoped, label-only) | Md. Nazmuz Saif | 1 | Done
ST-105 | Database | Create Designation model and migration | Md. Nazmuz Saif | 1 | Done
ST-105 | Backend | Build DesignationSerializer + DesignationViewSet | Md. Nazmuz Saif | 2 | Done
ST-105 | Frontend | Build Designations page (list, create, edit, delete) | Md. Nazmuz Saif | 2 | Done
ST-105 | Self-Test | Self-test Designation CRUD, scoped to own company | Md. Nazmuz Saif | 1 | Done
ST-106 | Design | Design self-referencing Employee hierarchy (reports_to) and circular-reference rule | Md. Nazmuz Saif | 2 | Done
ST-106 | Database | Create Employee model and migration with self-referencing reports_to FK | Md. Nazmuz Saif | 2 | Done
ST-106 | Backend | Build EmployeeSerializer + EmployeeViewSet; add circular-reference guard on reports_to | Md. Nazmuz Saif | 4 | Done
ST-106 | Frontend | Build Employees page (list, create, edit — manager/reports-to dropdown) | Md. Nazmuz Saif | 4 | Done
ST-106 | Self-Test | Self-test hierarchy assignment across levels and the circular-reference block | Md. Nazmuz Saif | 1 | Done
Overall Testing — QA Pass (Md. Tahsin Rahman Khan)
Story ID | Test Case No. | Test Case | Owner | Estimate (hrs) | Result
ST-101 | TC-01 | Register new company with valid data — expect Company, Settings, CEO Designation, User, Employee all created and a valid JWT returned | Md. Tahsin Rahman Khan | 1 | to do
ST-101 | TC-02 | Submit registration with a missing required field — expect a validation error and no partial records created | Md. Tahsin Rahman Khan | 1 | to do
ST-102 | TC-03 | Log in with valid credentials — expect access + refresh token returned | Md. Tahsin Rahman Khan | 1 | to do
ST-102 | TC-04 | Log in with invalid credentials — expect a generic error message, no token issued | Md. Tahsin Rahman Khan | 1 | to do
ST-103 | TC-05 | Attempt login as a user of a suspended company — expect a specific error and no token issued | Md. Tahsin Rahman Khan | 1 | to do
ST-104 | TC-06 | Create a Department — expect it visible only within the creating company's list | Md. Tahsin Rahman Khan | 1 | to do
ST-104 | TC-07 | Attempt to access another company's Department by ID — expect HTTP 404 | Md. Tahsin Rahman Khan | 1 | to do
ST-105 | TC-08 | Create, edit, and delete a Designation — expect changes scoped to own company only | Md. Tahsin Rahman Khan | 1 | to do
ST-106 | TC-09 | Assign an Employee's manager across a 3+ level hierarchy — expect the correct chain stored | Md. Tahsin Rahman Khan | 1 | to do
ST-106 | TC-10 | Attempt to set an Employee as their own manager — expect the request rejected | Md. Tahsin Rahman Khan | 1 | to do
Coordination Tasks (Montasim Kabir Mahin)
Task | Owner | Estimate (hrs) | Status
Sprint 1 planning session — select stories from backlog, confirm scope | Montasim Kabir Mahin | 2 | Done
Daily coordination and progress tracking | Montasim Kabir Mahin | 3 | Done
Sprint 1 review and retrospective facilitation | Montasim Kabir Mahin | 2 | Done
| Total Implementation Hours |  |  | 54
| Total QA Hours |  |  | 10
Total Coordination Hours |  | 7

## Sprint 2
Ordinis — Sprint 2 Planning
Sprint Duration: Sep 10 – Sep 23
Sprint Goal: Deliver the RBAC engine (Roles as Permission bundles, independent of Designation) and recursive hierarchy resolution, completing the Core Engine's access-control foundation.
Selected Stories for this Sprint
Story ID | User Story | Owner | Story Points | Acceptance Criteria
ST-107 | As a Department Head, I want the system to resolve my full list of subordinates automatically, so that I can see my whole team regardless of hierarchy depth. | Md. Nazmuz Saif | 5 | - Given an Employee, returns all direct and indirect subordinates - Given an Employee, returns the full chain of managers up to the top - Works for flat, 3-level, and 4+ level structures - Verified with real multi-level test data
ST-108 | As a CEO, I want to create custom Roles as bundles of Permissions, so that access rights are independent of job titles. | Montasim Kabir Mahin | 5 | - CEO can create a Role with a name and a list of Permission codenames - A Role is scoped to the CEO's own company - Roles are retrievable independent of any Designation
ST-109 | As a CEO, I want to assign one or more Roles to any Employee, so that I can grant exactly the access that person needs. | Sadia Jahan Disha | 3 | - CEO can assign a Role to any Employee in their company - An Employee can hold more than one Role at once - CEO can revoke a Role from an Employee
ST-110 | As the System, I want every protected action to check a specific Permission codename, so that access control never depends on a hardcoded job-title check. | Fawjiya Fahima Eifa | 5 | - Employee.has_permission(codename) correctly reflects the Employee's assigned Roles' Permissions - A protected endpoint rejects the request if the acting Employee lacks the required permission - Verified: an Employee without a Role cannot perform a Role-gated action
Carried Over from Sprint 1
Story ID | Category | Task | Owner | Estimate (hrs) | Status
(none — Sprint 1 fully completed)
Task Breakdown — one owner does the full story (Design → Database → Backend → Frontend → Self-Test)
Story ID | Category | Task | Owner | Estimate (hrs) | Status
ST-107 | Design | Design recursive traversal approach for subordinate/manager resolution over reports_to | Md. Nazmuz Saif | 2 | Done
ST-107 | Backend | Implement get_all_subordinates(employee) and get_all_managers(employee) service functions | Md. Nazmuz Saif | 4 | Done
ST-107 | Frontend | Show subordinate list on the Employee detail view | Md. Nazmuz Saif | 2 | Done
ST-107 | Self-Test | Self-test recursive resolution against a 4-level test hierarchy | Md. Nazmuz Saif | 1 | Done
ST-108 | Design | Design Permission/Role/RolePermission schema, formalizing the Designation-vs-Role separation | Montasim Kabir Mahin | 2 | Done
ST-108 | Database | Create Permission and Role models and migrations | Montasim Kabir Mahin | 1 | Done
ST-108 | Backend | Build PermissionSerializer (read-only) and RoleSerializer/ViewSet | Montasim Kabir Mahin | 3 | Done
ST-108 | Frontend | Build Roles management page (create Role, select Permissions) | Montasim Kabir Mahin | 3 | Done
ST-108 | Self-Test | Self-test Role creation/retrieval and company-level scoping | Montasim Kabir Mahin | 1 | Done
ST-109 | Design | Design EmployeeRole schema (Employee <-> Role assignment) | Sadia Jahan Disha | 1 | Done
ST-109 | Database | Create EmployeeRole model and migration | Sadia Jahan Disha | 1 | Done
ST-109 | Backend | Build EmployeeRoleSerializer/ViewSet (assign/revoke) | Sadia Jahan Disha | 2 | Done
ST-109 | Frontend | Add assign/revoke Role controls to the Employee page | Sadia Jahan Disha | 2 | Done
ST-109 | Self-Test | Self-test assigning multiple Roles and revoking a Role | Sadia Jahan Disha | 1 | Done
ST-110 | Design | Design the HasPermission / PermissionRequiredMixin enforcement approach | Fawjiya Fahima Eifa | 2 | Pause
ST-110 | Backend | Implement Employee.has_permission(), HasPermission DRF permission class, and PermissionRequiredMixin; apply across organization and rbac ViewSets | Fawjiya Fahima Eifa | 5 | Pause
ST-110 | Frontend | Hide/disable UI controls the current user lacks permission for | Fawjiya Fahima Eifa | 3 | Pause
ST-110 | Self-Test | Self-test that a permission-gated action is blocked without the permission and allowed with it | Fawjiya Fahima Eifa | 1 | Pause
Overall Testing — QA Pass (Md. Tahsin Rahman Khan)
Story ID | Test Case No. | Test Case | Owner | Estimate (hrs) | Result
ST-107 | TC-11 | Get subordinates for a mid-level manager in a 4-level tree — expect the correct full descendant list | Md. Tahsin Rahman Khan | 1 | to do
ST-107 | TC-12 | Get the manager chain for a leaf-level Employee — expect the correct full ancestor chain | Md. Tahsin Rahman Khan | 1 | to do
ST-108 | TC-13 | Create a Role with a chosen Permission set — expect it retrievable with the correct Permissions | Md. Tahsin Rahman Khan | 1 | to do
ST-108 | TC-14 | Create a Role in Company A — expect it invisible to Company B | Md. Tahsin Rahman Khan | 1 | to do
ST-109 | TC-15 | Assign two Roles to one Employee — expect both retained simultaneously | Md. Tahsin Rahman Khan | 1 | to do
ST-109 | TC-16 | Revoke one Role from an Employee — expect the associated permission no longer granted | Md. Tahsin Rahman Khan | 1 | to do
ST-110 | TC-17 | Employee without the required permission attempts a protected action — expect the request blocked | Md. Tahsin Rahman Khan | 1 | to do
ST-110 | TC-18 | Employee with the correct permission performs the same action — expect it allowed | Md. Tahsin Rahman Khan | 1 | to do
Coordination Tasks (Montasim Kabir Mahin)
Task | Owner | Estimate (hrs) | Status
Sprint 2 planning session — select stories from backlog, confirm scope | Montasim Kabir Mahin | 2 | Done
Daily coordination and progress tracking | Montasim Kabir Mahin | 3 | Done
Sprint 2 review and retrospective facilitation | Montasim Kabir Mahin | 2 | Done
| Total Implementation Hours |  |  | 37
| Total QA Hours |  |  | 8
Total Coordination Hours |  | 7

## Sprint 3
Ordinis — Sprint 3 Planning
Sprint Duration: Sep 30 – Oct 7
Sprint Goal: Close the Sprint 2 RBAC/tenant-safety gaps, then deliver the Approval Chain and approve/reject engine, the shared UI kit and app shell, Task create/submit, delegation, salary-data restriction, and check-in/out.
Selected Stories for this Sprint
Story ID | User Story |  | Owner | Story Points | Acceptance Criteria
ST-111 | PB-11: As the System, I want the unfinished Sprint 2 RBAC work and the gaps left in PB-01, PB-07, and PB-10 closed, so that every protected action is really permission-checked and no company can reach another company's data. |  | Md. Nazmuz Saif | 8 | - HasPermission blocks a gated action when the Employee lacks the Permission - A user without a company can never be attached to another company (get_effective_company removed) - A new company's CEO gets a full-access CEO Role at registration - An Employee cannot be their own manager or create a reports_to cycle - Registration page, subordinate list, and Role assign/revoke on the Employee page exist - Employee removal ends the person's access; employee_code is unique per company; JWT refresh works
ST-112 | PB-12: As a CEO, I want to define a multi-step Approval Chain for leave requests, so that my company's actual approval process is enforced by the system. |  | Md. Nazmuz Saif | 5 | - CEO can create a chain with ordered steps, each tied to a Role - Step order is unique inside a chain - Chain is scoped to own company (cross-company access returns 404) - Chain and steps can be edited and deleted
ST-113 | PB-13: As an Approver, I want to approve or reject a pending request with a comment, so that decisions and reasons are recorded. |  | Md. Nazmuz Saif | 3 | - Only a holder of the current step's Role can act - Approve moves the request to the next step; the last approval completes it - Reject ends the request; a comment is stored with every action - The same step cannot be acted on twice
ST-114 | PB-16: As a User, I want every screen to use the same status badges, metric cards, empty states, and chart cards, so that the product looks consistent and is easy to learn. |  | Md. Nazmuz Saif | 3 | - StatusPill, MetricCard, EmptyState, and ChartCard components exist - Status is shown by color and text, never color alone - All four follow the design system colors and 150–300ms animations - A showcase page at /dev/ui-kit displays every component
ST-115 | PB-20: As a User, I want a polished app shell (grouped sidebar, navbar, notification dropdown, company switcher, plan badge), so that the product feels professional and is easy to navigate. |  | Md. Nazmuz Saif | 5 | - Sidebar has collapsible groups (Organization, Workflow, Tasks, Attendance, Finance) and highlights the active item - A menu item is hidden when the user lacks the Permission for it - Top bar shows the page title, search box, company name, notification bell, and user menu - The bell opens a dropdown with an empty state when there are no notifications - The plan badge next to the logo shows the plan name only when the server provides one (never hard-coded)
ST-116 | PB-14 + PB-15: As a Department Head, I want to create Tasks and assign them with a priority and deadline, and as an Employee I want to submit a Task only through valid status changes, so that work and progress are tracked correctly. |  | Montasim Kabir Mahin | 8 | - Task has title, assignee, priority, deadline, and status (default Not Started) - Assignee must belong to the same company; assigned-by is set by the server - Only users with create_task can create, edit, or delete - Only valid status changes are accepted; an invalid one returns a clear error - Only the assignee can submit a Task
ST-117 | PB-17: As a Department Head, I want to delegate my approval authority to someone else for a date range, so that requests are not stuck when I'm on leave. |  | Md. Tahsin Rahman Khan | 3 | - Delegation has delegate, start date, and end date - End date cannot be before start date; cannot delegate to self - Delegate must be in the same company
ST-118 | PB-18: As an Accountant, I want to define a Salary Structure per employee and keep salary and financial data restricted to users with finance permission, so that confidential pay data stays private regardless of hierarchy. |  | Fawjiya Fahima Eifa | 3 | - A Salary Structure (base salary and allowances) can be defined per Employee - Salary Structure endpoints require the finance Permission - Access does not depend on the reporting hierarchy - Salary UI is hidden for users without the Permission
ST-119 | PB-19: As an Employee, I want to check in and check out once per day, so that my attendance is recorded accurately. |  | Sadia Jahan Disha | 3 | - One check-in and one check-out per day, using the company's local time - A second check-in on the same day is rejected with a clear message - Check-out before check-in is rejected - Today's status is shown on the Attendance page
Carried Over from Sprint 2
Story ID | Category | Task | Owner | Estimate (hrs) | Status
ST-110 | Design | Design the HasPermission / PermissionRequiredMixin enforcement approach | Md. Nazmuz Saif | 2 | Done (in ST-111)
ST-110 | Backend | Implement HasPermission (real permission check) and apply it to gated actions | Md. Nazmuz Saif | 5 | Done (in ST-111)
ST-110 | Frontend | Hide/disable UI controls the current user lacks permission for | Md. Nazmuz Saif | 3 | Done (in ST-111)
ST-110 | Self-Test | Self-test that a gated action is blocked without the permission | Md. Nazmuz Saif | 1 | Done (in ST-111)
Task Breakdown — one owner does the full story (Design → Database → Backend → Frontend → Self-Test)
Story ID | Category | Task | Owner | Estimate (hrs) | Status
ST-111 | Design | Design permission-enforcement flow, CEO Role bootstrap at registration, and tenant-safe company resolution | Md. Nazmuz Saif | 2 | Done
ST-111 | Database | Seed the full Permission set and verify all migrations on a fresh database | Md. Nazmuz Saif | 2 | Done
ST-111 | Backend | Fix HasPermission and IsCompanyActive; remove get_effective_company from mixins, views, serializers, and MeView | Md. Nazmuz Saif | 4 | Done
ST-111 | Backend | Create the CEO Role inside the atomic company registration; add PermissionRequiredMixin to RoleViewSet; move RBAC into the rbac app | Md. Nazmuz Saif | 4 | Done
ST-111 | Backend | Block self-manager and reports_to cycles on Employee create/update | Md. Nazmuz Saif | 2 | Done
ST-111 | Frontend | Build the Company Registration page (form, validation, API call, auto-login) | Md. Nazmuz Saif | 3 | Done
ST-111 | Frontend | Add subordinate list to Employee detail and Role assign/revoke to the Employee page; hide controls by permission | Md. Nazmuz Saif | 5 | Done
ST-111 | Self-Test | Self-test 403 without permission, 200 with it, cross-company access, cycle block, and fresh-DB registration | Md. Nazmuz Saif | 2 | Done
ST-112 | Design | Design ApprovalChain and ApprovalStep schema (ordered steps, approver Role) | Md. Nazmuz Saif | 2 | Done
ST-112 | Database | Create the approvals app models and migrations; seed the chain-management Permission | Md. Nazmuz Saif | 2 | Done
ST-112 | Backend | Build ApprovalChain/ApprovalStep serializers and ViewSets (company-scoped, step order unique) | Md. Nazmuz Saif | 4 | Done
ST-112 | Frontend | Build the Approval Chains page (create chain, add ordered steps with Role, edit, delete) | Md. Nazmuz Saif | 4 | Done
ST-112 | Self-Test | Self-test chain creation, duplicate step order, and cross-company access | Md. Nazmuz Saif | 1 | Done
ST-113 | Design | Design ApprovalInstance and ApprovalAction flow (step pointer, approve/reject rules) | Md. Nazmuz Saif | 1 | Done
ST-113 | Database | Create ApprovalInstance (generic relation) and ApprovalAction models and migrations | Md. Nazmuz Saif | 1 | Done
ST-113 | Backend | Build approve/reject actions: step-Role check, step advance, reject ends request, comment stored, double action blocked | Md. Nazmuz Saif | 3 | Done
ST-113 | Frontend | Build the pending-approvals list with an approve/reject dialog and comment box | Md. Nazmuz Saif | 3 | Done
ST-113 | Self-Test | Self-test full multi-step approval, a reject, and an unauthorized approver | Md. Nazmuz Saif | 1 | Done
ST-114 | Design | Design the UI component kit (props, colors, empty and loading states) from the design system | Md. Nazmuz Saif | 1 | Done
ST-114 | Frontend | Build StatusPill, MetricCard, EmptyState, and ChartCard components and the /dev/ui-kit showcase page | Md. Nazmuz Saif | 4 | Done
ST-114 | Self-Test | Self-test every component in the showcase page at desktop and mobile widths | Md. Nazmuz Saif | 1 | Done
ST-115 | Design | Design the grouped sidebar structure, top bar layout, and permission-based menu rules from the design system | Md. Nazmuz Saif | 2 | Done
ST-115 | Frontend | Build the collapsible grouped Sidebar with active-item highlight and permission-based items | Md. Nazmuz Saif | 4 | Done
ST-115 | Frontend | Build the top bar: page title, search box, company name, notification bell dropdown with empty state, and user menu | Md. Nazmuz Saif | 4 | Done
ST-115 | Frontend | Add the PlanBadge component (shows the plan name only when the server provides one; nothing hard-coded) | Md. Nazmuz Saif | 2 | Done
ST-115 | Self-Test | Self-test sidebar groups, hidden items for a low-permission user, and the bell dropdown | Md. Nazmuz Saif | 2 | Done
ST-116 | Design | Design the Task schema (assignee, assigned-by, priority, deadline, status) and the allowed status-transition map | Montasim Kabir Mahin | 2 | Done
ST-116 | Database | Create the tasks app Task model and migration; seed the create_task Permission | Montasim Kabir Mahin | 2 | Done
ST-116 | Backend | Build TaskSerializer and TaskViewSet (company-scoped, assigned-by set by server, same-company assignee check) | Montasim Kabir Mahin | 3 | Done
ST-116 | Backend | Build the submit action with transition validation and an assignee-only check | Montasim Kabir Mahin | 2 | Done
ST-116 | Frontend | Build the Tasks page (list, create, edit, delete; priority badge, deadline) with a Submit button for the assignee | Montasim Kabir Mahin | 5 | Done
ST-116 | Self-Test | Self-test task CRUD, cross-company assignee, a valid submit, an invalid transition, and a non-assignee submit | Montasim Kabir Mahin | 2 | Done
ST-117 | Design | Design DelegationRule schema (delegator, delegate, date range) | Md. Tahsin Rahman Khan | 1 | Done
ST-117 | Database | Create DelegationRule model and migration | Md. Tahsin Rahman Khan | 1 | Done
ST-117 | Backend | Build DelegationRule serializer and ViewSet with date-range, self-delegation, and same-company validation | Md. Tahsin Rahman Khan | 2 | Done
ST-117 | Frontend | Build the Delegation page (create, list, delete) | Md. Tahsin Rahman Khan | 2 | Done
ST-117 | Self-Test | Self-test valid delegation, reversed dates, and self-delegation | Md. Tahsin Rahman Khan | 1 | Done
ST-118 | Design | Design SalaryStructure schema and finance-Permission gating (hierarchy-independent) | Fawjiya Fahima Eifa | 1 | Done
ST-118 | Database | Create the payroll app SalaryStructure model and migration; seed the finance Permission | Fawjiya Fahima Eifa | 1 | Incomplete
ST-118 | Backend | Build SalaryStructure serializer and ViewSet gated by the finance Permission (company-scoped) | Fawjiya Fahima Eifa | 2 | Incomplete
ST-118 | Frontend | Build the Salary Structures page, hidden for users without the Permission | Fawjiya Fahima Eifa | 2 | Done
ST-118 | Self-Test | Self-test access with and without the finance Permission | Fawjiya Fahima Eifa | 1 | Incomplete
ST-119 | Design | Design the Attendance schema and the one-check-in-per-day rule (company local time) | Sadia Jahan Disha | 1 | Done
ST-119 | Database | Create the attendance app Attendance model and migration (unique per employee per day) | Sadia Jahan Disha | 1 | Done
ST-119 | Backend | Build check-in and check-out actions with duplicate and out-of-order validation | Sadia Jahan Disha | 2 | Done
ST-119 | Frontend | Build the Attendance page with Check In / Check Out buttons and today's status | Sadia Jahan Disha | 3 | Done
ST-119 | Self-Test | Self-test check-in, duplicate check-in, and check-out before check-in | Sadia Jahan Disha | 1 | Done
Cross-Test Assignment — every story is tested by a member who did not write it
Story ID |  | Story | Code Owner |  | Selenium Tester
ST-111 |  | Sprint 2 RBAC carry-over | Md. Nazmuz Saif |  | Montasim Kabir Mahin
ST-112 |  | Approval Chain | Md. Nazmuz Saif |  | Sadia Jahan Disha
ST-113 |  | Approve / reject | Md. Nazmuz Saif |  | Fawjiya Fahima Eifa
ST-114 |  | UI component kit | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-115 |  | App shell | Md. Nazmuz Saif |  | Sadia Jahan Disha
ST-116 |  | Task create, assign, submit | Montasim Kabir Mahin |  | Md. Nazmuz Saif
ST-117 |  | Approval delegation | Md. Tahsin Rahman Khan |  | Montasim Kabir Mahin
ST-118 |  | Salary data restriction | Fawjiya Fahima Eifa |  | Md. Tahsin Rahman Khan
ST-119 |  | Check-in / check-out | Sadia Jahan Disha |  | Fawjiya Fahima Eifa
Overall Testing — Selenium Cross-Review QA Pass (each tester tests another member's story)
Story ID | Test Case No. | Test Case | Tester | Estimate (hrs) | Result
ST-111 | TC-19 | [Selenium] Log in as an Employee without the manage_departments Permission and try to add a Department — expect an error message and no record created | Montasim Kabir Mahin | 1.5 | Passed
ST-111 | TC-20 | [Selenium] Log in as a CEO right after registration and add a Department — expect success (CEO Role assigned automatically) | Montasim Kabir Mahin | 1.5 | Passed
ST-111 | TC-21 | [Selenium] Register a new company from the registration page — expect a redirect to the dashboard as CEO of that company only | Montasim Kabir Mahin | 1.5 | Passed
ST-111 | TC-22 | [Selenium] Try to set an Employee as their own manager or create a reports_to cycle — expect the request blocked with a message | Montasim Kabir Mahin | 1.5 | Passed
ST-111 | TC-23 | [Selenium] Open an Employee detail page — expect the subordinate list; assign then revoke a Role — expect the page to update | Montasim Kabir Mahin | 1.5 | Passed
ST-112 | TC-24 | [Selenium] Create an Approval Chain with three ordered steps — expect the steps saved in order | Sadia Jahan Disha | 1.5 | Passed
ST-112 | TC-25 | [Selenium] Add a step with a duplicate order or no Role — expect a validation error | Sadia Jahan Disha | 1.5 | Passed
ST-112 | TC-26 | [Selenium] Log in as Company B and open Company A's chain by ID — expect HTTP 404 | Sadia Jahan Disha | 1.5 | Passed
ST-113 | TC-27 | [Selenium] Approve as the holder of the current step's Role — expect the request to move to the next step | Fawjiya Fahima Eifa | 1.5 | Passed
ST-113 | TC-28 | [Selenium] Reject with a comment — expect the request to end and the comment to be shown in the history | Fawjiya Fahima Eifa | 1.5 | Passed
ST-113 | TC-29 | [Selenium] Try to approve without the step's Role, or act on the same step twice — expect the action blocked | Fawjiya Fahima Eifa | 1.5 | Passed
ST-114 | TC-30 | [Selenium] Open /dev/ui-kit — expect Success, Warning, and Failed status pills, each with color and text | Md. Tahsin Rahman Khan | 1.5 | Passed
ST-114 | TC-31 | [Selenium] Open /dev/ui-kit — expect a MetricCard with value and delta, and an EmptyState whose action button is clickable | Md. Tahsin Rahman Khan | 1.5 | Passed
ST-115 | TC-32 | Click a sidebar group header — expect its links to expand and collapse | Sadia Jahan Disha | 1.5 | Passed
ST-115 | TC-33 | Click a sidebar group header — expect its links to expand and collapse | Sadia Jahan Disha | 1.5 | Passed
ST-115 | TC-34 | Click a sidebar group header — expect its links to expand and collapse | Sadia Jahan Disha | 1.5 | Passed
ST-115 | TC-35 | Click the notification bell — expect a dropdown with an empty state; click outside — expect it to close | Sadia Jahan Disha | 1.5 | Passed
ST-116 | TC-36 | [Selenium] Create a Task with priority and deadline for an Employee — expect it in the Tasks list | Md. Nazmuz Saif | 1.5 | Passed
ST-116 | TC-37 | [Selenium] Assign a Task to an Employee of another company — expect the request rejected | Md. Nazmuz Saif | 1.5 | Passed
ST-116 | TC-38 | [Selenium] Edit and delete a Task; log in without create_task — expect no create/edit/delete buttons | Md. Nazmuz Saif | 1.5 | Passed
ST-116 | TC-39 | [Selenium] As the assignee, submit an In Progress Task — expect the status to become Submitted | Md. Nazmuz Saif | 1.5 | Passed
ST-116 | TC-40 | [Selenium] Try a move that is not allowed (Completed to Not Started) — expect a clear error | Md. Nazmuz Saif | 1.5 | Passed
ST-116 | TC-41 | [Selenium] As a different Employee, try to submit someone else's Task — expect the request blocked | Md. Nazmuz Saif | 1.5 | Passed
ST-117 | TC-42 | [Selenium] Create a delegation with a valid date range — expect it in the list | Montasim Kabir Mahin | 1.5 | Passed
ST-117 | TC-43 | [Selenium] Enter an end date before the start date — expect a validation error | Montasim Kabir Mahin | 1.5 | Passed
ST-117 | TC-44 | [Selenium] Delegate to yourself — expect the request rejected | Montasim Kabir Mahin | 1.5 | Passed
ST-118 | TC-45 | [Selenium] Log in without the finance Permission and open Salary Structures — expect no menu item and HTTP 403 from the API | Md. Tahsin Rahman Khan | 1.5 | Passed
ST-118 | TC-46 | [Selenium] Log in with the finance Permission and create and edit a Salary Structure — expect success | Md. Tahsin Rahman Khan | 1.5 | Failed
ST-118 | TC-47 | [Selenium] Log in as a manager above the Accountant in the hierarchy but without the finance Permission — expect salary data still blocked | Md. Tahsin Rahman Khan | 1.5 | Passed
ST-119 | TC-48 | [Selenium] Click Check In — expect today's status to show the check-in time | Fawjiya Fahima Eifa | 1.5 | Passed
ST-119 | TC-49 | [Selenium] Click Check In a second time on the same day — expect a clear error message | Fawjiya Fahima Eifa | 1.5 | Passed
ST-119 | TC-50 | [Selenium] Log in as a new Employee and click Check Out before Check In — expect the request blocked | Fawjiya Fahima Eifa | 1.5 | Passed
Coordination Tasks (Montasim Kabir Mahin)
Task | Owner | Estimate (hrs) | Status
Sprint 3 planning session — select stories from backlog, confirm scope | Montasim Kabir Mahin | 2 | Done
Daily coordination and progress tracking | Montasim Kabir Mahin | 3 | Done
Cross-test hand-off tracking — confirm each story is tested by a non-owner | Montasim Kabir Mahin | 1 | Done
Sprint 3 review and retrospective facilitation | Montasim Kabir Mahin | 2 | Done
| Total Implementation Hours |  |  | 104
| Total QA Hours |  |  | 48
Total Coordination Hours |  | 8

## Sprint 4
Ordinis — Sprint 4 Planning
Sprint Duration: Oct 7 – Oct 14
Sprint Goal: Finish the Sprint 3 Salary Structure carry-over, then deliver paginated and documented APIs, Role dashboards, the Break-Glass support process and platform admin panel, the Task Kanban board with daily progress, the Action Inbox, Payslip generation, and leave application with balance check.
Selected Stories for this Sprint
Story ID | User Story |  | Owner | Story Points | Acceptance Criteria
ST-120 | PB-40: As an Accountant, I want the unfinished Sprint 3 Salary Structure work (database, API, self-test and the Edit/Delete screen) completed, so that confidential pay data can be defined, edited and deleted per employee and stays restricted to users with the finance Permission. |  | Md. Nazmuz Saif | 3 | - A Salary Structure (base salary and allowances) can be created, edited and deleted per Employee - Every Salary Structure endpoint requires the finance Permission, whatever the reporting hierarchy - One structure per Employee; a negative base salary or allowance is rejected - The page is hidden for users without the Permission; Edit and Delete work on the page - TC-46 (create and edit), which Failed in Sprint 3, passes when run again
ST-121 | PB-21: As a Developer, I want all list endpoints paginated and the project set up with requirements, environment example, and README, so that the system scales and can be installed by anyone. |  | Md. Nazmuz Saif | 3 | - Every list endpoint returns pages (page size 20) and the frontend lists still work - requirements.txt installs everything on a clean machine - .env.example lists every environment variable with no secrets - README explains install, migrate, run backend and frontend, and run the tests
ST-122 | PB-22: As a User, I want a dashboard made for my Role (CEO, Manager, HR, Accountant, Employee), so that I see only what matters to my work. |  | Md. Nazmuz Saif | 8 | - After login the user lands on a dashboard; the Dashboard menu item is no longer "Soon" - What a dashboard shows is decided by the user's Permissions, not by the Designation name - Each dashboard has a row of MetricCards with real numbers from the API and at least one chart - A user never sees numbers they lack the Permission for (for example salary data) - Loading and empty states use the UI kit
ST-123 | PB-23: As the Platform Owner, I want a Break-Glass access process for support, so that I can help a client without having default access to their data. |  | Md. Nazmuz Saif | 5 | - A Platform Admin sends a Support Access Request with a reason - The company CEO sees the request and approves or denies it - Approval gives time-limited access that expires on its own - Without an approved, unexpired request the Platform Admin cannot read the company's data - Every use is recorded in an Impersonation Log the company can read
ST-124 | PB-24: As the Platform Owner, I want an admin panel for companies, support tickets, and Break-Glass requests, so that I can operate the platform without seeing client data by default. |  | Md. Nazmuz Saif | 5 | - The panel lists companies, support tickets, and Break-Glass requests - A company can be suspended and activated; users of a suspended company cannot log in - The panel shows no employee, task, or salary data - Only Platform Admin accounts can open it; everybody else is blocked and does not see the menu item
ST-125 | PB-25 + PB-26: As a Department Head, I want to see Tasks on a Kanban board (To Do, In Progress, Review, Done), and as an Employee I want to log daily progress on a multi-day task, so that my manager can see progress at a glance without me uploading code or files. |  | Montasim Kabir Mahin | 8 | - The Kanban board shows the four columns with a count on each and a card per Task (title, priority, assignee, deadline) - A card can only move along the allowed status path; a wrong move is rejected with a clear message - The assignee can add a daily progress entry (text, progress percent, optional blocker, optional external link); no file or code upload - The entries show as a timeline on the Task; only the assignee can add them; another company's Task is not reachable
ST-126 | PB-27: As a User, I want a personalized Action Inbox combining my pending tasks, approvals, and notifications, so that I know what needs my attention in one place. |  | Md. Tahsin Rahman Khan | 5 | - One list shows my open Tasks, the approvals waiting for me, and my unread notifications - A Notification is created when a Task is assigned to me or an approval reaches me - Other users' and other companies' items never appear; each item opens its page - Marking a notification read removes it from the unread list; an empty inbox shows an empty state
ST-127 | PB-28: As an Accountant, I want to generate a Payslip for a given month without creating duplicates, so that payroll runs stay accurate. |  | Sadia Jahan Disha | 5 | - A Payslip for an Employee and month shows gross, deductions, and net, calculated from the Salary Structure - A second Payslip for the same Employee and month is rejected (also enforced in the database) - Generating needs the finance Permission, whatever the reporting hierarchy - An Employee without a Salary Structure gets a clear message; an Employee can open only their own Payslip
ST-128 | PB-29: As an Employee, I want to apply for leave and have my balance validated automatically, so that I can't accidentally over-request leave. |  | Fawjiya Fahima Eifa | 5 | - A company can define Leave Types with days allowed per year - An Employee can apply with leave type, start date, end date, and reason; the request starts as Pending - A request above the remaining balance is rejected with a message that shows the remaining days - An end date before the start date is rejected; an Employee sees only their own requests
Carried Over from Sprint 3
Story ID | Category | Task | Owner | Estimate (hrs) | Status
ST-118 | Database | Create the payroll app SalaryStructure model and migration; seed the finance Permission | Fawjiya Fahima Eifa | 1 | Done (in ST-120)
ST-118 | Backend | Build SalaryStructure serializer and ViewSet gated by the finance Permission | Fawjiya Fahima Eifa | 2 | Done (in ST-120)
ST-118 | Self-Test | Self-test access with and without the finance Permission | Fawjiya Fahima Eifa | 1 | Done (in ST-120)
ST-118 | Selenium | TC-46 (create and edit a Salary Structure) Failed in Sprint 3 and is run again as TC-51 | Md. Tahsin Rahman Khan | 1.5 | Done (in ST-120)
Task Breakdown — one owner does the full story (Design → Database → Backend → Frontend → Self-Test)
Story ID | Category | Task | Owner | Estimate (hrs) | Status
ST-120 | Database | Create the payroll app SalaryStructure model and migration; seed the finance Permission | Md. Nazmuz Saif | 1 | Done
ST-120 | Backend | Build SalaryStructure serializer and ViewSet gated by the finance Permission (no hierarchy rule, one structure per Employee) | Md. Nazmuz Saif | 2 | Done
ST-120 | Frontend | Fix the Salary Structures page: Edit and Delete work, statuses show correctly, UI kit components are used, page is hidden without the Permission | Md. Nazmuz Saif | 2 | Done
ST-120 | Self-Test | Self-test create, edit, delete, access with and without the finance Permission, and the manager-above-Accountant case | Md. Nazmuz Saif | 1 | Done
ST-121 | Design | Design the pagination format and what changes in the frontend lists | Md. Nazmuz Saif | 1 | Done
ST-121 | Backend | Wire pagination into every list endpoint and keep the standard response format | Md. Nazmuz Saif | 2 | Done
ST-121 | Backend | Write requirements.txt, .env.example, and the README (install, migrate, run, test) | Md. Nazmuz Saif | 2 | Done
ST-121 | Frontend | Update every frontend list service and page to read paged results and add page controls | Md. Nazmuz Saif | 3 | Done
ST-121 | Self-Test | Self-test a long list on two pages and a clean install from the README | Md. Nazmuz Saif | 1 | Done
ST-122 | Design | Design the five Role dashboards (which MetricCards and charts, which Permission each needs) | Md. Nazmuz Saif | 2 | Done
ST-122 | Backend | Build the dashboard summary endpoint(s) that return only what the user's Permissions allow | Md. Nazmuz Saif | 3 | Done
ST-122 | Frontend | Build the CEO, Manager, HR, Accountant, and Employee dashboards with MetricCards and charts (violet palette) | Md. Nazmuz Saif | 8 | Done
ST-122 | Frontend | Land on the dashboard after login and turn the Dashboard menu item into a link | Md. Nazmuz Saif | 2 | Done
ST-122 | Self-Test | Self-test each dashboard, a user without the Permission, loading and empty states, desktop and mobile | Md. Nazmuz Saif | 2 | Done
ST-123 | Design | Design the Break-Glass flow (request, approve or deny, expiry, log) and the Platform Admin account | Md. Nazmuz Saif | 2 | Done
ST-123 | Database | Create SupportAccessRequest and ImpersonationLog models and migrations; mark Platform Admin accounts | Md. Nazmuz Saif | 2 | Done
ST-123 | Backend | Build request, approve, deny, automatic expiry, gated company-data access, and the access log | Md. Nazmuz Saif | 5 | Done
ST-123 | Frontend | Build the CEO screen to review requests and read the Impersonation Log | Md. Nazmuz Saif | 3 | Done
ST-123 | Self-Test | Self-test approve, deny, expiry, access without an approved request, and the log entries | Md. Nazmuz Saif | 2 | Done
ST-124 | Design | Design the admin panel pages and the rule that no client data is shown | Md. Nazmuz Saif | 1 | Done
ST-124 | Backend | Build the Platform Admin endpoints (companies, suspend and activate, support tickets, requests), allowed only for Platform Admins | Md. Nazmuz Saif | 3 | Done
ST-124 | Frontend | Build the admin panel pages with menu item shown only to Platform Admins | Md. Nazmuz Saif | 5 | Done
ST-124 | Self-Test | Self-test suspend and activate, a CEO opening the panel, and that no client data shows | Md. Nazmuz Saif | 2 | Done
ST-125 | Design | Design the Kanban columns and status mapping and the TaskProgressLog schema | Montasim Kabir Mahin | 2 | Done
ST-125 | Database | Create the TaskProgressLog model and migration | Montasim Kabir Mahin | 1 | Done
ST-125 | Backend | Build the progress log endpoints (assignee only) and the Kanban data with allowed moves | Montasim Kabir Mahin | 3 | Done
ST-125 | Frontend | Build the Kanban board and the progress timeline on the Task | Montasim Kabir Mahin | 6 | Done
ST-125 | Self-Test | Self-test card moves, an invalid move, adding progress as the assignee and as someone else | Montasim Kabir Mahin | 2 | Done
ST-126 | Design | Design the Notification schema and the Action Inbox sources | Md. Tahsin Rahman Khan | 1 | Done
ST-126 | Database | Create the Notification model and migration | Md. Tahsin Rahman Khan | 1 | Done
ST-126 | Backend | Build notification creation (Task assigned, approval reached), mark-read, and the inbox aggregation | Md. Tahsin Rahman Khan | 4 | Done
ST-126 | Frontend | Build the Action Inbox page and connect the notification bell | Md. Tahsin Rahman Khan | 4 | Done
ST-126 | Self-Test | Self-test each inbox source, mark read, and that nobody else's items appear | Md. Tahsin Rahman Khan | 1 | Done
ST-127 | Design | Design the Payslip schema, the calculation, and the one-per-month rule | Sadia Jahan Disha | 1 | Done
ST-127 | Database | Create the Payslip model and migration with a unique Employee and month | Sadia Jahan Disha | 1 | Done
ST-127 | Backend | Build generate_payslip with duplicate prevention and the finance Permission check | Sadia Jahan Disha | 4 | Done
ST-127 | Frontend | Build the Payslip generate and view pages | Sadia Jahan Disha | 3 | Done
ST-127 | Self-Test | Self-test generate, duplicate, no Salary Structure, and own-Payslip-only access | Sadia Jahan Disha | 1 | Done
ST-128 | Design | Design the LeaveType and LeaveRequest schema and the balance calculation | Fawjiya Fahima Eifa | 1 | Done
ST-128 | Database | Create the LeaveType and LeaveRequest models and migrations | Fawjiya Fahima Eifa | 2 | Done
ST-128 | Backend | Build apply_leave with balance validation and date checks | Fawjiya Fahima Eifa | 4 | Done
ST-128 | Frontend | Build the leave application page and the My Leave list | Fawjiya Fahima Eifa | 4 | Done
ST-128 | Self-Test | Self-test an in-balance request, an over-balance request, and reversed dates | Fawjiya Fahima Eifa | 1 | Done
Cross-Test Assignment — every story is tested by a member who did not write its code
Story ID |  | Story | Code Owner |  | Selenium Tester
ST-120 |  | Salary Structure carry-over | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-121 |  | Pagination and project setup | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-122 |  | Role dashboards | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-123 |  | Break-Glass support access | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-124 |  | Platform admin panel | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-125 |  | Kanban board and daily progress | Montasim Kabir Mahin |  | Md. Nazmuz Saif
ST-126 |  | Action Inbox | Md. Tahsin Rahman Khan |  | Montasim Kabir Mahin
ST-127 |  | Payslip generation | Sadia Jahan Disha |  | Fawjiya Fahima Eifa
ST-128 |  | Leave application with balance check | Fawjiya Fahima Eifa |  | Sadia Jahan Disha
Overall Testing — Selenium Cross-Review QA Pass (each tester tests another member's code)
Story ID | Test Case No. | Test Case | Tester | Estimate (hrs) | Result
ST-120 | TC-51 | [Selenium] Log in with the finance Permission, create a Salary Structure and edit it — expect the saved values in the list (TC-46 run again) | Md. Tahsin Rahman Khan | 1.5 | Passed
ST-120 | TC-52 | [Selenium] Delete a Salary Structure — expect it gone from the list; log in without the Permission — expect no menu item | Md. Tahsin Rahman Khan | 1.5 | Passed
ST-121 | TC-53 | [Selenium] Open a list with more than one page — expect page controls and that the next page loads | Md. Tahsin Rahman Khan | 1.5 | Passed
ST-122 | TC-54 | [Selenium] Log in as a CEO — expect the dashboard with MetricCards showing numbers and a chart | Md. Tahsin Rahman Khan | 1.5 | Passed
ST-122 | TC-55 | [Selenium] Log in as an Employee — expect only Employee metrics and no salary or company-wide numbers | Md. Tahsin Rahman Khan | 1.5 | Passed
ST-122 | TC-56 | [Selenium] Log in as an Accountant — expect finance metrics and no Task management numbers | Md. Tahsin Rahman Khan | 1.5 | Passed
ST-123 | TC-57 | [Selenium] As a Platform Admin send a Support Access Request with a reason — expect it Pending; as the CEO see it in the list | Md. Tahsin Rahman Khan | 1.5 | Passed
ST-123 | TC-58 | [Selenium] As the CEO approve the request — expect an expiry time and a log entry; without an approved request — expect access blocked | Md. Tahsin Rahman Khan | 1.5 | Passed
ST-124 | TC-59 | [Selenium] As a Platform Admin open the panel and suspend a company — expect its users cannot log in; activate it — expect they can | Md. Tahsin Rahman Khan | 1.5 | Passed
ST-124 | TC-60 | [Selenium] As a CEO open the admin panel address — expect access blocked and no menu item | Md. Tahsin Rahman Khan | 1.5 | Passed
ST-125 | TC-61 | [Selenium] Open the Kanban board — expect the four columns with counts and Task cards | Md. Nazmuz Saif | 1.5 | Passed
ST-125 | TC-62 | [Selenium] As the assignee add a daily progress entry — expect it on the Task timeline | Md. Nazmuz Saif | 1.5 | Passed
ST-125 | TC-63 | [Selenium] As a different Employee try to add progress to someone else's Task — expect it blocked | Md. Nazmuz Saif | 1.5 | Passed
ST-126 | TC-64 | [Selenium] Assign a Task and send an approval to a user — expect both in that user's Action Inbox | Montasim Kabir Mahin | 1.5 | Passed
ST-126 | TC-65 | [Selenium] Mark a notification read — expect it leaves the unread list; expect no items of other users | Montasim Kabir Mahin | 1.5 | Passed
ST-127 | TC-66 | [Selenium] Generate a Payslip with the finance Permission — expect gross, deductions, and net | Fawjiya Fahima Eifa | 1.5 | Passed
ST-127 | TC-67 | [Selenium] Generate the same month again — expect a clear duplicate message | Fawjiya Fahima Eifa | 1.5 | Passed
ST-128 | TC-68 | [Selenium] Apply for leave within the balance — expect it listed as Pending | Sadia Jahan Disha | 1.5 | Passed
ST-128 | TC-69 | [Selenium] Apply for more days than the balance — expect a clear message with the remaining days | Sadia Jahan Disha | 1.5 | Passed
ST-128 | TC-70 | [Selenium] Enter an end date before the start date — expect a validation message | Sadia Jahan Disha | 1.5 | Passed
Coordination Tasks (Montasim Kabir Mahin)
Task | Owner | Estimate (hrs) | Status
Sprint 4 planning session — select stories from backlog, confirm scope | Montasim Kabir Mahin | 2 | Done
Daily coordination and progress tracking | Montasim Kabir Mahin | 3 | Done
Cross-test hand-off tracking — confirm each story is tested by a non-owner | Montasim Kabir Mahin | 1 | Done
Sprint 4 review and retrospective facilitation | Montasim Kabir Mahin | 2 | Done
| Total Implementation Hours |  |  | 104
| Total QA Hours |  |  | 30
Total Coordination Hours |  | 8

## Sprint 5
Ordinis — Sprint 5 Planning
Sprint Duration: Oct 14 – Oct 21
Sprint Goal: Finish the product. Connect leave to the Approval Chain, add the Audit Log, Analytics, Billing and the attendance calendar, then fill the system with demo data, build the regression suite, update every document and rehearse the full demo.
Selected Stories for this Sprint
Story ID | User Story |  | Owner | Story Points | Acceptance Criteria
ST-129 | As an Employee, I want my leave request to follow my company's Approval Chain, and approvers to approve or reject it, so that leave is decided by the right people in the right order. (PB-30) |  | Md. Nazmuz Saif | 5 | - Applying for leave starts the company's leave Approval Chain; the request stays Pending until its last step is approved - Each step's approvers (role holders and their active delegates) see the request in Pending Approvals and in their Action Inbox; the applicant never decides their own request - Approving the last step makes the leave Approved; a rejection with a comment makes it Rejected; both send a Notification to the applicant and a Rejected leave gives its days back - If the company has no leave chain, or a step has no approver, the request goes to the CEO instead of getting stuck - A decided request cannot be decided again; another company's request is not reachable
ST-130 | As a Presenter, I want a command that fills the system with realistic demo data, so that every screen looks real during the demo. (PB-31) |  | Md. Nazmuz Saif | 3 | - One command creates a demo company with a CEO, departments, designations, a multi-level hierarchy, Roles, and a sample user for every dashboard (CEO, Manager, HR, Accountant, Employee) - It adds Tasks in all four Kanban columns with progress entries, a month of attendance, leave types and leave requests in every status, salary structures and payslips, an approval chain with requests waiting, and notifications - Running it twice never duplicates data; a --reset option removes only the demo company; it refuses to run with production settings - Every screen shows real-looking data after the command
ST-131 | As a Developer, I want a Selenium regression suite and backend tests, so that changes cannot silently break working features. (PB-32) |  | Md. Nazmuz Saif | 5 | - One command runs every backend test and one command runs every Selenium test case (TC-01 onward) against the demo company, printing pass or fail for each test case - Every API endpoint has tests for: login required, the Permission check, and another company's data returning 404 - A shared Selenium helper (login that works after the dashboard redirect, one place for the frontend address, test users) replaces the copies in each test file - The README explains how to run both suites
ST-132 | As a Reviewer, I want the SRS, SDS, and structure documents to match the delivered system, so that the documents are trustworthy. (PB-33) |  | Md. Nazmuz Saif | 3 | - The SRS, SDS, project structure, ER diagram, design system and the other project documents describe only what the delivered system really has - The SDS data dictionary and API table match the code (models, fields, endpoints); anything not built is marked as future work - The SRS traceability table marks every requirement Done, Partly or Not built, with the story that delivered it - The documents are checked against the latest code by someone other than the author
ST-133 | As a Team, I want a full demo rehearsal with a bug-fix buffer, so that the final presentation runs smoothly. (PB-34) |  | Md. Nazmuz Saif | 5 | - A written demo script walks every role through the main features in order, in about 15 minutes - The script is rehearsed end to end twice on a clean install with demo data; every slip is logged and then fixed or listed as known - At least 6 hours stay free as a bug-fix buffer, and no new feature is added after the first rehearsal - The final build passes both test suites, npm run lint and npm run build
ST-134 | As a CEO, I want an Analytics page with attendance and task-completion charts, so that I can see my company's health. (PB-35) |  | Montasim Kabir Mahin | 5 | - The CEO opens an Analytics page with a row of MetricCards (attendance rate, task completion rate, overdue tasks, average team workload) - A line chart shows the attendance rate over the last 6 months and a grouped bar chart shows completed and pending Tasks by department - All numbers come from the real attendance and task data of the user's own company; a month without data shows 0, not an error - Users without the analytics Permission never see the menu item or the numbers; the page has loading and empty states
ST-135 | As a CEO, I want every sensitive action logged in an append-only Audit Log, and an Audit Log page with module filter and export, so that I have a tamper-proof history of who did what and when. (PB-36 + PB-37) |  | Md. Tahsin Rahman Khan | 8 | - Every create, update and delete through the API, plus Break-Glass reads, payslip generation and leave decisions, writes an Audit Log row with actor, action, module, object, company and time - The Audit Log is append-only: no edit or delete endpoint exists, and the model refuses update and delete - The CEO sees only the log of their own company; a user without the Permission is blocked - The Audit Log page shows User, Action, Module, Date & Time and a Status pill, with a Module filter, an Export button and paging; it has no edit or delete action
ST-136 | As a CEO, I want a Billing page showing my plan, employee limit, and invoices, so that I can manage my subscription. (PB-38) |  | Sadia Jahan Disha | 3 | - The Billing page shows the company's plan (name, price, employee limit), the current employee count with a usage bar, and the invoice list - Plans are seeded (Basic 10 employees, Professional 50, Enterprise unlimited) and a new company starts on Basic - Adding an Employee beyond the plan's limit is refused with a clear "upgrade your plan" message - Only users with the billing Permission see the page and its data; another company's invoices are not reachable
ST-137 | As an Employee, I want a monthly attendance calendar with summary cards, so that I can see my attendance history at a glance. (PB-39) |  | Fawjiya Fahima Eifa | 3 | - A month calendar shows a colored dot per day (Present, Absent, On Leave) with previous and next month buttons - Summary cards show Present, Absent and On Leave days and the attendance rate of the month - Days of Approved leave show as On Leave; weekends and future days show no status - An employee sees only their own calendar
Carried Over from Sprint 4
Story ID | Category | Task | Owner | Estimate (hrs) | Status
— | — | Nothing was carried over: every Sprint 4 story is Done and every test case Passed | — | 0 | Done
Task Breakdown (Implementation)
Story ID | Category | Task | Owner | Estimate (hrs) | Status
ST-129 | Design | Design how a leave request starts an Approval Instance of the leave chain, what approve and reject do, and the CEO fallback when no chain or approver exists | Md. Nazmuz Saif | 1 | Done
ST-129 | Backend | Connect apply_leave to start_approval; on the last approval set the leave Approved, on rejection set it Rejected and give the days back; block the applicant from deciding their own leave | Md. Nazmuz Saif | 5 | Done
ST-129 | Backend | Notify the applicant when the leave is decided and show the leave in the approvers' Pending Approvals and Action Inbox; add the CEO fallback | Md. Nazmuz Saif | 2 | Done
ST-129 | Frontend | Show the approval progress (current step, who decided, comment) on the My Leave page and the leave details on Pending Approvals | Md. Nazmuz Saif | 3 | Done
ST-129 | Self-Test | Self-test a one-step and a two-step chain, a rejection with a comment, no chain configured, the applicant's own request, and another company | Md. Nazmuz Saif | 2 | Done
ST-130 | Design | Design the demo story: the company, one account per role, and the data each screen needs | Md. Nazmuz Saif | 1 | Done
ST-130 | Backend | Write the seed_demo_data command: safe to run twice, a --reset for the demo company only, refuses production settings | Md. Nazmuz Saif | 5 | Done
ST-130 | Self-Test | Run the command on an empty database and twice in a row, log in as every demo role and check each screen has data | Md. Nazmuz Saif | 2 | Done
ST-131 | Design | Decide what the regression suite covers and how a Selenium run starts from known demo data | Md. Nazmuz Saif | 1 | Done
ST-131 | Backend | Add the missing backend tests so every endpoint is tested for login required, the Permission check, and another company's data returning 404 | Md. Nazmuz Saif | 6 | Done
ST-131 | Backend | Build the shared Selenium helper (login after the dashboard redirect, frontend address, test users) and one command that runs every Selenium test case | Md. Nazmuz Saif | 3 | Done
ST-131 | Self-Test | Run both suites from a clean checkout and fix what breaks; write the README steps | Md. Nazmuz Saif | 3 | Done
ST-132 | Design | Compare the SRS, SDS, structure, ER diagram, design-system and other project documents with the final code and list every difference | Md. Nazmuz Saif | 2 | Done
ST-132 | Design | Update the documents to match the delivered system and mark what was not built as future work | Md. Nazmuz Saif | 4 | Done
ST-132 | Self-Test | Check that every model and endpoint named in the documents exists in the code | Md. Nazmuz Saif | 1 | Done
ST-133 | Design | Write the demo script: every role, in order, about 15 minutes, with the data each step needs | Md. Nazmuz Saif | 2 | Done
ST-133 | Self-Test | Rehearsal 1: follow the script end to end on a clean install with demo data and log every slip | Md. Nazmuz Saif | 3 | Done
ST-133 | Backend | Bug-fix buffer: fix the backend problems found in rehearsal 1 | Md. Nazmuz Saif | 3 | Done
ST-133 | Frontend | Bug-fix buffer: fix the screen problems found in rehearsal 1 | Md. Nazmuz Saif | 3 | Done
ST-133 | Self-Test | Rehearsal 2: run the script again, then both test suites, npm run lint and npm run build, and tag the final build | Md. Nazmuz Saif | 3 | Done
ST-134 | Design | Design the Analytics page: which MetricCards and charts, how attendance rate and task completion are calculated, and the Permission that guards it | Montasim Kabir Mahin | 2 | Done
ST-134 | Database | Create the CompanyHealthSnapshot model and migration (one row per company and day) | Montasim Kabir Mahin | 1 | Done
ST-134 | Backend | Build the analytics service and endpoints (monthly attendance rate, completed and pending Tasks by department) limited to the user's own company | Montasim Kabir Mahin | 3 | Done
ST-134 | Frontend | Build the Analytics page with MetricCards, a line chart and a grouped bar chart, with loading and empty states | Montasim Kabir Mahin | 4 | Done
ST-134 | Self-Test | Self-test with and without data, a user without the Permission, and another company | Montasim Kabir Mahin | 1 | Done
ST-135 | Design | Design which actions are logged, what each row holds, the append-only rule and the page layout | Md. Tahsin Rahman Khan | 1 | Done
ST-135 | Database | Create the AuditLog model and migration with a guard that refuses update and delete | Md. Tahsin Rahman Khan | 2 | Done
ST-135 | Backend | Write an Audit Log row for every create, update and delete through the API, Break-Glass reads, payslip generation and leave decisions; add the list endpoint, Module filter and export, limited to the company and the Permission | Md. Tahsin Rahman Khan | 5 | Done
ST-135 | Frontend | Build the Audit Log page: table, Module filter, status pills, Export button and paging, read-only with no edit or delete action | Md. Tahsin Rahman Khan | 5 | Done
ST-135 | Self-Test | Self-test rows after create, update and delete, refused update and delete of a log row, the filter, the export, and another company | Md. Tahsin Rahman Khan | 2 | Done
ST-136 | Design | Design the Billing page and how the plan limit is checked when an Employee is created | Sadia Jahan Disha | 1 | Done
ST-136 | Database | Create the SubscriptionPlan, Subscription and Invoice models and migration; seed Basic (10), Professional (50) and Enterprise | Sadia Jahan Disha | 2 | Done
ST-136 | Backend | Build the billing endpoints and enforce the plan's employee limit when an Employee is created | Sadia Jahan Disha | 3 | Done
ST-136 | Frontend | Build the Billing page: plan card, employee usage bar and invoice table | Sadia Jahan Disha | 3 | Done
ST-136 | Self-Test | Self-test the limit at exactly full, over the limit, the Permission, and another company | Sadia Jahan Disha | 1 | Done
ST-137 | Design | Design the monthly calendar: day statuses (Present, Absent, On Leave), weekends, future days and the summary cards | Fawjiya Fahima Eifa | 1 | Done
ST-137 | Backend | Build the monthly attendance summary endpoint for the logged-in employee | Fawjiya Fahima Eifa | 2 | Done
ST-137 | Frontend | Build the calendar grid with colored dots, month navigation and the summary cards | Fawjiya Fahima Eifa | 4 | Done
ST-137 | Self-Test | Self-test months with no data, a month with approved leave, and that another employee's days never show | Fawjiya Fahima Eifa | 1 | Done
Cross-Test Assignment (every story is tested by someone other than its owner)
Story ID |  | Story | Code Owner |  | Selenium Tester
ST-129 |  | Leave follows the Approval Chain | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-130 |  | Demo data command | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-131 |  | Regression suite and backend tests | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-132 |  | Documents match the system | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-133 |  | Demo rehearsal and bug-fix buffer | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-134 |  | Analytics page | Montasim Kabir Mahin |  | Md. Nazmuz Saif
ST-135 |  | Audit Log and Audit Log page | Md. Tahsin Rahman Khan |  | Montasim Kabir Mahin
ST-136 |  | Billing page | Sadia Jahan Disha |  | Fawjiya Fahima Eifa
ST-137 |  | Monthly attendance calendar | Fawjiya Fahima Eifa |  | Sadia Jahan Disha
Overall Testing — Selenium Cross-Review QA Pass (each tester tests another member's story)
Story ID | Test Case No. | Test Case | Tester | Estimate (hrs) | Result
ST-129 | TC-71 | [Selenium] Apply for leave as an Employee when the company has a leave Approval Chain — expect the request Pending and visible in the approver's Pending Approvals page and Action Inbox | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-129 | TC-72 | [Selenium] As the approver approve the last step — expect the leave Approved, a Notification for the applicant, and the days used in the leave balance | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-129 | TC-73 | [Selenium] As the approver reject a leave request with a comment — expect it Rejected, the days back in the balance, and the comment shown to the applicant | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-130 | TC-74 | [Selenium] After running the demo data command log in as the CEO, a Manager, HR, an Accountant and an Employee — expect each dashboard to show real numbers and charts | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-130 | TC-75 | [Selenium] Run the demo data command a second time — expect no duplicate Employees, Departments or Tasks on their pages | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-131 | TC-76 | [Selenium] Run the single regression command from a clean checkout — expect a pass or fail line for every test case, and a non-zero exit code when one test is made to fail | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-132 | TC-77 | [Review] Compare every endpoint in the SDS API table with the running API — expect none missing and none extra | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-132 | TC-78 | [Review] Open the SRS requirements traceability table — expect every requirement marked Done, Partly or Not built, each with the story that delivered it | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-133 | TC-79 | [Rehearsal] Follow the demo script on a clean install with demo data — expect every step to work and the whole run to take about 15 minutes | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-133 | TC-80 | [Rehearsal] Run both test suites, npm run lint and npm run build on the final build — expect everything to pass | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-134 | TC-81 | [Selenium] Log in as a CEO and open Analytics — expect MetricCards, the attendance line chart and the tasks-by-department bar chart | Md. Nazmuz Saif | 1.5 | Passed
ST-134 | TC-82 | [Selenium] Log in as an Employee without the analytics Permission — expect no Analytics menu item and the page address blocked | Md. Nazmuz Saif | 1.5 | Passed
ST-135 | TC-83 | [Selenium] Create, edit and delete a Department as the CEO — expect three new rows on the Audit Log page with the right actor and action | Montasim Kabir Mahin | 1.5 | Not Run
ST-135 | TC-84 | [Selenium] Filter the Audit Log by Module and press Export — expect only that module's rows and a downloaded file with the same rows | Montasim Kabir Mahin | 1.5 | Not Run
ST-135 | TC-85 | [Selenium] Open the Audit Log as an Employee without the Permission, and as another company's CEO — expect no access and none of this company's rows | Montasim Kabir Mahin | 1.5 | Not Run
ST-136 | TC-86 | [Selenium] Log in as a CEO and open Billing — expect the plan, the employee limit with usage, and the invoice list | Fawjiya Fahima Eifa | 1.5 | Not Run
ST-136 | TC-87 | [Selenium] Add an Employee when the plan's limit is reached — expect an "upgrade your plan" message and no new Employee | Fawjiya Fahima Eifa | 1.5 | Not Run
ST-137 | TC-88 | [Selenium] Open the monthly attendance calendar — expect a colored dot per day and the Present, Absent, On Leave and rate cards matching the month | Sadia Jahan Disha | 1.5 | Not Run
ST-137 | TC-89 | [Selenium] Move to the previous month and look at a day of approved leave — expect the calendar to change month and show that day as On Leave | Sadia Jahan Disha | 1.5 | Not Run
Coordination Tasks (Mahin)
Task | Owner | Estimate (hrs) | Status
Sprint 5 planning session — select the last stories from the backlog, confirm scope and the date after which no new feature is added | Montasim Kabir Mahin | 2 | To Do
Daily coordination and progress tracking | Montasim Kabir Mahin | 3 | To Do
Cross-test hand-off tracking — confirm each story is tested by a non-owner | Montasim Kabir Mahin | 1 | To Do
Demo day planning — confirm who presents which part and when the two rehearsals happen | Montasim Kabir Mahin | 2 | To Do
Sprint 5 review and final retrospective facilitation | Montasim Kabir Mahin | 2 | To Do
| Total Implementation Hours |  |  | 99
| Total QA Hours |  |  | 28.5
Total Coordination Hours |  | 10

## Sprint 6 Brief
Ordinis — Sprint 6 Brief (read this first)
Written so that a new conversation can pick up Sprint 6 from this workbook alone. Dates: Oct 21 – Nov 4. Stories ST-138 to ST-155, backlog PB-41 to PB-58, test cases TC-90 to TC-132.
1. Context
Purpose of this tab |  | Start here. Then read the Sprint 6 tab (stories, tasks, test cases, cross-test table) and the Gap Register tab (the 23 gaps Saif listed on Oct 20, plus 8 more found while analysing them; every gap points to the story that fixes it). The Product Backlog tab has PB-41 to PB-58 for these stories.
The project in short |  | Ordinis is a multi-tenant Organization Operating System: a Django REST Framework backend (14 apps, SQLite in development) and a React + Vite + Tailwind frontend. Each company builds its own hierarchy, Roles and Permissions, approval chains, tasks, attendance and leave, payroll and billing. A Platform Admin runs the platform and can see a company only through the Break-Glass process (request, company approval, time limit, read-only, logged). Rules that must hold in every story: every query is filtered by company and another company's id is a 404; access is checked by Permission codename, never by job title; business rules live in services.py; every API answers in the standard envelope {success, data, message} or {success, error: {code, message, field_errors}}.
State at the end of Sprint 5 |  | Treated as fully complete, as Saif stated on Oct 20: ST-129 to ST-137 Done and TC-71 to TC-89 Passed, including Analytics (ST-134) and the monthly attendance calendar (ST-137). At the last verified build the backend had 568 passing tests, makemigrations --check was clean, and generate_docs and check_docs matched the code. The Sprint 5 tab and the Sprint 5 rows of the Product Backlog were left exactly as they were; update their statuses when they are really true.
Sprint 6 goal |  | Make the product ready to run as a business and to manage: fix the Roles bugs, give people real names, profiles and safe passwords, add detail pages and team attendance, finish billing (timeline, registration with plan choice, manual payment approval, renewal, upgrade) and give the Platform Admin company details, notes, requests and a dashboard.
Size and the five-sprint rule |  | 18 stories and 102 story points, against 9 stories and 40 points in Sprint 5, so it is planned as 15 days. Implementation is about 232 hours (workload table at the bottom). The course plan fixed five sprints, so Sprint 6 is an extra improvement sprint after them; decide how to present it.
2. How the stories are ordered and owned
Order |  | The stories on the Sprint 6 tab are listed in the order they are implemented, one after another. Every story needs only stories above it, so you can start at the top and work down without jumping. The order table in section 3 shows what each story needs and a target finish date.
Owners |  | One serial, as Saif asked: the first ten stories (ST-138 to ST-147) are Saif's, then two each for Mahin, Tahsin, Disha and Eifa in that order, so Eifa has the last two. Saif keeps the foundations and the money core (catalog, names and profile, passwords, subscription period, payments, registration). ST-155 (regression, documents, demo script) has to come last, so by this serial it is Eifa's; swap it with Saif if you prefer. Change the Owner column freely.
Standing rules (unchanged) |  | One story has one owner and is an isolated piece of work. Every story is tested with Selenium by someone other than its owner; tester rotation: Mahin's code is tested by Saif, Tahsin's by Mahin, Saif's by Tahsin, Eifa's by Disha, Disha's by Eifa. A story is Done only when its code is written, self-tested and its Selenium test cases pass. Commits carry their real date. Story IDs continue from ST-138, backlog from PB-41, test cases from TC-90. Migrations: add a new migration, never regenerate old ones. Documents: the generated parts come from python manage.py generate_docs and are checked by check_docs. Test commands: python regression.py backend and python regression.py selenium, plus npm run lint and npm run build. "docs" means a Word file.
3. Order table (implement from top to bottom)
Order | Story | Owner | Tier | Needs (stories above) | Target finish | Notes
1 | ST-138 — Permission catalog in code and Roles page bug fix | Md. Nazmuz Saif | Must | — | Oct 21 | First: every later Permission (team attendance, billing) is added to this catalog.
2 | ST-139 — Roles v2: sections, role detail and role edit | Md. Nazmuz Saif | Must | ST-138 | Oct 22 | Right after ST-138: the Roles page builds on the new catalog and descriptions.
3 | ST-140 — Names, profile data and the profile API | Md. Nazmuz Saif | Must | — | Oct 23 | Gives every later story real names and the profile API.
4 | ST-141 — My Profile page for every user | Md. Nazmuz Saif | Must | ST-140 | Oct 23 | UI for the profile API from ST-140.
5 | ST-142 — Password safety: change password and temporary password | Md. Nazmuz Saif | Must | ST-141, ST-140 | Oct 24 | Adds the password forms to the My Profile page from ST-141.
6 | ST-143 — Employee detail page v2 | Md. Nazmuz Saif | Must | ST-138, ST-140 | Oct 25 | Needs the catalog (ST-138) for effective Permissions and the names and profile fields (ST-140).
7 | ST-144 — Team attendance with employee dropdown | Md. Nazmuz Saif | Must | ST-138, ST-140 | Oct 26 | Needs the catalog (ST-138), names (ST-140) and the Sprint 5 calendar (ST-137).
8 | ST-145 — Subscription period, days left, reminders and restricted mode | Md. Nazmuz Saif | Must | — | Oct 27 | Start of the billing chain; keep register_company and seed data working.
9 | ST-146 — Duration pricing, manual payment submission and admin approval | Md. Nazmuz Saif | Must | ST-145 | Oct 28 | Core of billing: price, payment submission, approval, invoice. Needs the period fields from ST-145.
10 | ST-147 — Registration with plan choice, payment and waiting page | Md. Nazmuz Saif | Must | ST-145, ST-146 | Oct 29 | Its second test case needs the Payments page (ST-148); run it after ST-148 is done, or approve through the API.
11 | ST-148 — Platform Admin payments review and subscriptions timeline | Montasim Kabir Mahin | Must | ST-146 | Oct 29 | Gives the Platform Admin the UI to approve payments.
12 | ST-149 — Company Billing timeline, renewal and invoice detail | Montasim Kabir Mahin | Must | ST-145, ST-146 | Oct 31 | Includes the renewal invoice job (backend 3 h).
13 | ST-150 — Department and Designation detail pages | Md. Tahsin Rahman Khan | Must | ST-140 | Nov 1 | Needs names (ST-140).
14 | ST-151 — Plan upgrade request with extra amount | Md. Tahsin Rahman Khan | Should | ST-146 | Nov 2 | Reuses the payment and approval flow from ST-146.
15 | ST-152 — Platform Admin company detail page | Sadia Jahan Disha | Should | ST-145, ST-146 | Nov 2 | Subscription facts from ST-145, payment facts from ST-146.
16 | ST-153 — Platform Admin dashboard | Sadia Jahan Disha | Should | ST-146, ST-148 | Nov 3 | Needs real payments and invoices (ST-146) and the Payments page links (ST-148).
17 | ST-154 — Platform Admin notes, access request, support request and sidebar cleanup | Fawjiya Fahima Eifa | Must | — | Nov 4 | Independent quick wins; placed late because no other story needs it.
18 | ST-155 — Sprint 6 regression, documents and demo script | Fawjiya Fahima Eifa | Must | all Must stories | Nov 4 | Last: updates tests, documents and demo script, then the rehearsal.
Target finish |  | Spreads the story points evenly over the 15 days (Oct 21 is day 1, Nov 4 day 15). It is a pace to aim for, not a promise; a bigger story takes its own time.
4. Key design decisions (the reasons, so nobody re-argues them)
D1 Permission catalog in code |  | One list in rbac/catalog.py (codename, name, module, description) synced on migrate. A new Permission is one line and the CEO role receives it through the existing sync. A Permission is added only together with the feature it protects. A test checks that every codename used in the views is in the catalog.
D2 Names and profile |  | full_name lives on User (so the Platform Admin has one); phone, address, emergency contact and joined on live on Employee. The profile endpoint edits only a whitelist; it can never change email, department, designation, manager, Roles or salary.
D3 Temporary password |  | The CEO never types an employee's password. The system makes a one-time temporary password, shows it once, and the employee must change it at first login (PASSWORD_CHANGE_REQUIRED). Creating with an explicit password still works, so older tests keep passing.
D4 Who sees what on a person |  | Contact details only for the person, their managers and manage_employees; salary only with manage_finance; task titles on a Department page only for people who may see those tasks, others see counts. This keeps FR-13.
D5 Days left is computed |  | Days left = end date minus today in the company time zone. It is never stored or decremented by a job, so a missed job cannot make it wrong. The daily process_subscriptions command only sends reminders and sets the expired status; the same check also runs on every request.
D6 Restricted mode, not suspension |  | A company that is pending payment or expired can log in but only Billing, payment, profile, support and logout work (SUBSCRIPTION_RESTRICTED). Suspend (is_active false) stays a full block for misuse. Without this an unpaid company could not even reach the page where it pays.
D7 Manual payments |  | The amount is always computed on the server. A transaction id is unique per method. One pending submission per company. Approval is idempotent (locked row). A company can never approve its own payment. The invoice is created on approval, not when the form is submitted.
D8 Renewal |  | The renewal invoice is created 7 days before the end so the client sees what to pay; paying and approval extend from the old end date, so no days are lost.
D9 Pricing |  | Price = plan monthly price × months (1 to 36); 12 months costs the price of 10. Current plan prices are placeholders: Basic 1500, Professional 5000, Enterprise 15000 BDT a month (employee limits 10, 50, unlimited).
D10 Upgrade |  | Extra amount = (new monthly price − old monthly price) × days left ÷ 30, rounded to the taka; the end date does not change. A lower plan only at the next renewal and only if the team fits.
D11 Platform Admin privacy |  | The company detail page and the dashboard show counts, dates, money and the owner's contact only, never employee names, tasks, attendance or salary. Break-Glass remains the only way into company data.
D12 Reminders |  | In-app Notifications and a banner only (7, 3 and 1 days before the end); there is no email or SMS channel yet.
5. Defaults, cut line, risks
Defaults (one constant each) |  | Grace period 3 days after the end date; reminders at 7, 3 and 1 days; yearly discount 12 months for the price of 10; months 1 to 36; payment methods bKash, Nagad, bank and cash; no free trial (a new company must pay before it starts). Changing any of these touches only ST-145 and ST-146.
Cut line |  | Must stories carry the sprint: ST-138, ST-139, ST-140, ST-141, ST-142, ST-143, ST-144, ST-145, ST-146, ST-147, ST-148, ST-149, ST-150, ST-154, ST-155. Should stories can move to Sprint 7 without breaking anything above them: ST-151, ST-152, ST-153. Decide at the Oct 28 check (Mahin's coordination task).
Risks |  | 1) Because the order is strict, a slip delays the stories below it. Saif's ten come first and carry about 130 implementation hours; the teammates' eight stories wait for them, and ST-138, ST-140, ST-145 and ST-146 matter most. 2) The size: 232 implementation hours in 15 days. 3) Payments are verified by a person, not a gateway, so the Platform Admin must check the transaction before approving. 4) Registration changes make old tests and Selenium helpers fail until they are updated (X-08). 5) Time zones: days left and reminders use the company time zone.
Definition of Done |  | Code written and merged; the story's own tests pass; python regression.py backend still passes; npm run lint and npm run build pass; the Selenium test cases of the story pass for the tester; documents regenerate cleanly (generate_docs, check_docs); the story status is changed to Done only after that.
Out of scope for Sprint 6 |  | A real payment gateway (bKash or Nagad API), email or SMS, multi-factor authentication and password reset by email, field-level encryption, Projects, Expense and Reimbursement, and the Layer 3 modules. They stay future work.
How to start in a new conversation |  | Give the new conversation this workbook, the latest Ordinis-Submission.zip and the continuity instruction. Ask it to read this tab, then start with ST-138 (the first row of the order table), one step at a time, with a Django shell or test run after each step and a commit at the end of each session.
6. Workload by owner (formulas read the Sprint 6 tab)
Owner |  | Stories | Points | Implementation hours | QA hours | Stories (ids)
Md. Nazmuz Saif |  | 10 | 56 | 130 | 9 | ST-138, ST-139, ST-140, ST-141, ST-142, ST-143, ST-144, ST-145, ST-146, ST-147
Montasim Kabir Mahin |  | 2 | 13 | 25 | 7.5 | ST-148, ST-149
Md. Tahsin Rahman Khan |  | 2 | 13 | 27 | 33 | ST-150, ST-151
Sadia Jahan Disha |  | 2 | 10 | 23 | 9 | ST-152, ST-153
Fawjiya Fahima Eifa |  | 2 | 10 | 27 | 6 | ST-154, ST-155
Total |  | 18 | 102 | 232 | 64.5 | Sprint 5 for comparison: 9 stories, 40 points, 99 implementation hours, 28.5 QA hours

## Sprint 6
Ordinis — Sprint 6 Planning
Sprint Duration: Oct 21 – Nov 4
Sprint Goal: Fix the Roles bugs and give every person a real name, a profile and a safe password. Give every Role, Employee, Department and Designation a detail page, let managers see team attendance, and finish billing: subscription timeline, registration with plan choice and manual payment approval, renewals and plan upgrades. Give the Platform Admin company details, notes, access and support requests and a dashboard, then update the tests, documents and demo script.
Selected Stories for this Sprint
Story ID | User Story |  | Owner | Story Points | Acceptance Criteria
ST-138 | As a CEO, I want every Permission to have a clear name, a plain-language description and a module, kept in one place in the code, and the Roles page to offer only real Permissions, so that a Role I create keeps every Permission I tick and I know what each one allows. (PB-41) |  | Md. Nazmuz Saif | 5 | - A permission catalog in the code (rbac/catalog.py) lists every Permission with codename, name, module and a plain-language description; running migrate adds missing rows and refreshes names and descriptions, so a new Permission no longer needs its own migration; the CEO system Role still receives every Permission - The Permission model has a description field, and GET /api/v1/rbac/permissions/ returns codename, name, module and description - The Roles page builds its Permission list only from that API; the hardcoded list is removed (six of its names, such as approve_leave and view_finance, do not exist in the backend and were silently dropped) - Creating a Role with N Permissions saves exactly N, and the existing-Roles list shows all N grouped by module; if the server did not save a ticked Permission the page says so - A test fails when a ViewSet uses a permission_required codename that is not in the catalog
ST-139 | As a CEO, I want a Roles page with Permissions in sections, a detail page for each Role that explains what every Permission lets people do, and the ability to edit a Role, so that I can design access without guessing. (PB-42) |  | Md. Nazmuz Saif | 5 | - The create and edit Role form shows Permissions in collapsible module sections, each with its name, a one-line description and a Select all per section, and a counter of how many are chosen - Each Role has a detail page (/roles/:id) with its description, its Permissions grouped by module with their descriptions, and the employees who hold it - A Role can be edited (name, description, Permissions); the CEO system Role cannot be edited or deleted and the page says why; before saving the page says how many employees the change affects - The existing-Roles list shows the real Permission count and the first few names with +N more - Deleting a Role that employees still hold is refused with code ROLE_IN_USE and a clear message; the Role stays in the list
ST-140 | As an employee, I want my full name and profile details stored and editable by me, so that the system shows real names everywhere and I keep my own details current. (PB-43) |  | Md. Nazmuz Saif | 5 | - User gets full_name; Employee gets phone, address, emergency contact name and phone, and joined on; registration asks for the owner's full name; creating and editing an Employee takes the full name; seed_demo_data gives every demo person a name - GET and PATCH /api/v1/auth/profile/ work for the logged-in user, the Platform Admin included; only full name, phone, address and emergency contact can be changed; email, department, designation, manager, Roles and salary can never be changed through it - Every serializer that returns an employee email also returns the employee name, and every page shows the full name first (with code or email in small text) - Old rows without a name still work (the name may be empty and the page falls back to the email)
ST-141 | As any user (employee, CEO or Platform Admin), I want a My Profile page where I see and edit my own details, so that I keep my information current myself. (PB-44) |  | Md. Nazmuz Saif | 5 | - The user menu has My Profile; the page shows full name, email (read-only), designation, department, manager and company (read-only) and phone, address and emergency contact (editable); the Platform Admin sees the same page without the company fields - Saving shows success or the field errors from the server; leaving the page with unsaved changes asks first - A user opening another user's profile address is not possible: the page only ever loads the logged-in user's own data
ST-142 | As a CEO and as an employee, I want a safe way to change my password and a temporary password for new employees, so that nobody has to share a password. (PB-45) |  | Md. Nazmuz Saif | 5 | - POST /api/v1/auth/change-password/ needs the current password, applies the password rules and ends the user's other sessions (blacklists their other refresh tokens); the My Profile page has the form (current, new, confirm) and shows the server message for a wrong current password - When the CEO creates an Employee without typing a password, the system makes a one-time temporary password, returns it once, and the Employee must change it at first login: until then every endpoint except change-password, profile, me and logout answers 403 with code PASSWORD_CHANGE_REQUIRED; creating with an explicit password still works as before - After login with a temporary password the user is sent to My Profile and cannot open any other page until the password is changed - The Employee create form no longer gets email and password filled in by the browser, and after creating an Employee shows the temporary password once with a Copy button
ST-143 | As a CEO or HR user, I want an Employee detail page with the full profile and the Permissions that person really has, so that I can see exactly who someone is and what they can do. (PB-46) |  | Md. Nazmuz Saif | 5 | - The page shows full name, email, code, phone, address, emergency contact, joined on, department, designation, manager, direct reports and the chain of managers - A Permissions section lists each Role the person holds and under it the effective Permissions grouped by module with descriptions; a person with no Role shows No Permissions - Phone, address and emergency contact are visible only to the person, their managers and holders of manage_employees; everyone else sees name, designation and department; salary and payroll lines only with manage_finance - A user with manage_employees can edit these fields from the page
ST-144 | As a CEO or a manager with the Permission, I want to pick an employee from a dropdown and see their attendance for a month, so that I know how many days they came and at what times. (PB-47) |  | Md. Nazmuz Saif | 5 | - A new Permission view_team_attendance is added to the catalog with a description; the CEO role holds it; a user with it sees every employee of the company, a user without it sees only the people below them in the hierarchy; a user with no team sees no Team Attendance menu item - The Team Attendance page (Attendance group in the sidebar) has a searchable employee dropdown, a month picker with previous and next, the monthly calendar and the Present, Absent, On Leave and rate cards for that employee, and a table of each day's check-in, check-out and hours worked - The month shows days present and total hours; a day with no check-out shows no check-out - GET /attendance/attendance/team/?employee=&month= answers 404 (not 403) for an employee outside the user's scope or in another company - My Attendance still shows only the user's own data
ST-145 | As the Platform Owner, I want every company's subscription to have a start and end date, a days-left count, automatic reminders before it ends and a restricted mode after it ends, so that unpaid companies stop using the product without being locked out of paying. (PB-48) |  | Md. Nazmuz Saif | 8 | - Subscription gets current_period_start, current_period_end, billing_months and the status pending_payment, active, expired or cancelled; days left are computed from today's date in the company time zone, never stored or counted down by a job - python manage.py process_subscriptions (run daily) sends an in-app Notification to the CEO and to billing holders 7, 3 and 1 days before the end (once per threshold) and moves a subscription to expired 3 days after its end date; running it twice changes nothing more - Restricted mode: a company with status pending_payment or expired can log in, but every endpoint except login, refresh, logout, me, profile, change-password, billing, payments, plans and support answers 403 with code SUBSCRIPTION_RESTRICTED; the frontend then shows only the Billing pages and a banner; Suspend (is_active false) still blocks everything - The check also runs on every request, so a company past its end date is restricted even if the daily job did not run - seed_demo_data and the existing tests keep working: demo companies are active with long periods and the register_company test helper activates the subscription
ST-146 | As a company owner, I want to choose a plan for any number of months, pay by bKash, Nagad or bank transfer outside the system and submit the payment details, so that the platform team can check and approve it and my plan starts. (PB-49) |  | Md. Nazmuz Saif | 8 | - Price = plan monthly price × months, 1 to 36 months, and 12 months costs the price of 10; GET /billing/quote/?plan=&months= returns the amount, the discount and the period; the amount is always computed on the server - PaymentSubmission records company, plan, months, amount, method (bkash, nagad, bank, cash), payer name, payer number, transaction id, kind (new, renewal, upgrade), status (pending, approved, rejected), reviewed by, reviewed at and the review note; a transaction id can be used once per method; a company has one pending submission at a time - A new Permission manage_billing (in the catalog) lets a company submit and read its own payments; the Platform Admin lists all, approves, or rejects with a note - Approving is idempotent (locked row): it activates or extends the subscription (a renewal extends from the old end date, so no days are lost), creates the paid Invoice with the next number and notifies the company; rejecting notifies with the note; approving twice changes nothing - Every approval and rejection is audit-logged and written to PlatformActionLog; a company can never approve its own payment
ST-147 | As a new client, I want to register, choose a plan and duration, pay and submit my payment details, and wait for approval, so that my company starts only after my payment is checked. (PB-50) |  | Md. Nazmuz Saif | 5 | - Registering (company name, owner full name, email, password) creates the company in pending_payment and signs the owner in; the owner lands on Choose a plan: cards for Basic, Professional and Enterprise with employee limit and monthly price, and a months selector (1, 3, 6, 12 or custom 1 to 36) with a live total from the quote endpoint - Next opens the payment page: how to pay (bKash, Nagad, bank or manual instructions read from the server settings) and a form with method, payer name, payer number and transaction id, with the amount shown read-only - After submit a waiting page shows Waiting for approval and refreshes itself; a rejected payment shows the admin's note and a form to submit again; an approved one sends the owner to the dashboard - Companies registered before this change and the demo companies are unaffected
ST-148 | As the Platform Owner, I want a Payments page to review the payments companies submit and a Subscriptions page that shows every company's days left, so that I approve what I verified and see who expires soon. (PB-51) |  | Montasim Kabir Mahin | 5 | - The Payments page lists submissions (newest first, Pending by default) with company, plan, months, amount, method, payer, number, transaction id, kind and status, with filters; a detail panel; Approve (with confirm) and Reject (note required); after approval it shows the new end date and the invoice number - The Subscriptions page lists every company with plan, status, end date and days left (7 days or fewer amber, expired red), sorted by days left, with filters Expiring in 7 days and Expired or Restricted - The platform sidebar has Payments with a count of pending submissions, and Subscriptions - Only a Platform Admin can open these pages or call their endpoints
ST-149 | As a CEO, I want a Billing timeline showing how many days my plan has left, a Renew button with an invoice to pay, and a detail page for every invoice, so that I always know when and how much to pay. (PB-52) |  | Montasim Kabir Mahin | 8 | - The top of the Billing page is a timeline card: plan, start and end dates, a progress bar, N days left in large text and a status (Active, Expiring soon at 7 days or fewer, Restricted) - Seven days before the end the daily job creates the renewal Invoice (open, due on the end date), once only; Renew shows that invoice and its amount with the same payment form as registration, tied to the invoice; a pending banner shows after submit; after approval the invoice is Paid and the end date moves - The invoice list shows number, period, amount and status; each row opens /settings/billing/invoices/:id with number, company, plan, period, months, amount, currency, issue, due and paid dates, payment method, transaction id and status, and a Print button - Another company's invoice id is a 404; the timeline needs view_billing and paying needs manage_billing
ST-150 | As a CEO or Department Head, I want a detail page for each Department and each Designation, so that I can see who is in it, what they do and what work is running. (PB-53) |  | Md. Tahsin Rahman Khan | 8 | - A Department row opens /organization/departments/:id with the name, head, member count, and each member with name, designation, manager and number of open tasks; a task summary (not started, in progress, submitted, completed, overdue) and the running tasks with title, assignee, priority, deadline and progress - Task titles are shown only to people who may see them (the assignee's manager chain or a user with a company-wide task Permission); everybody else sees counts only - A Department can name a Head (an Employee of the same company); the Head shows on the page and in the list - A Designation row opens /organization/designations/:id with the title, the employees who hold it (with department) and the count - Deleting a Department or Designation that still has employees is refused with a clear message that says who is in it (today it silently clears their link) - Another company's Department or Designation id is a 404
ST-151 | As a CEO, I want to request a plan change, see the extra amount to pay, pay it and have the admin approve it, so that my plan changes only after payment. (PB-54) |  | Md. Tahsin Rahman Khan | 5 | - The Change plan page lists the plans with their employee limits; choosing a higher plan shows the extra amount = (new monthly price − current monthly price) × days left ÷ 30, rounded to the taka, from GET /billing/upgrade-quote/?plan=; the end date does not change - After paying outside the system the owner submits the payment form; it creates a PaymentSubmission of kind upgrade in status pending; a company has one pending submission at a time - Admin approval switches the plan at once and creates an invoice for the extra amount; rejection keeps the current plan - A lower plan can only start at the next renewal and is refused when the team is larger than the plan's limit (existing guard message); the Billing page's upgrade message links to this page
ST-152 | As the Platform Owner, I want a detail page for each company with its plan, subscription timeline, owner contact, size and support history, so that I can help a company without opening its data. (PB-55) |  | Sadia Jahan Disha | 5 | - /admin/companies/:id shows name, subdomain, industry, registered on, status with the last suspend or activate note, the owner (CEO) name, email and phone, the plan and subscription timeline (start, end, days left), employee count against the limit, an invoices and payments summary, counts of open tickets and access requests, and the last 10 platform actions on the company - It shows counts and contacts only, never employee names, tasks, attendance or salary (Break-Glass stays the only way in); Suspend or Activate (with note) and Request access are buttons on the page - Company rows in the list open this page; only a Platform Admin can open it
ST-153 | As the Platform Owner, I want a dashboard showing companies by state, revenue, dues and what needs my attention, so that I can see the health of the platform at a glance. (PB-56) |  | Sadia Jahan Disha | 5 | - /admin/dashboard is the Platform Admin home with MetricCards: companies total, active, restricted (pending payment or expired) and suspended; revenue this month and all time (paid invoices); due (open invoices); subscriptions ending in 7 days; pending payments; open tickets - Charts: revenue per month for the last 6 months (bars) and companies by state (donut); a Needs attention list (payments to approve, subscriptions ending, open tickets, pending access requests), each linking to its page - One endpoint GET /platform-admin/admin/summary/ whose query count does not grow with the number of companies; Platform Admin only
ST-154 | As the Platform Owner and as a company user, I want a note on every suspend or activate, a way to request access to a company, a way to send a support request from inside my company, and a sidebar without unfinished items, so that every action is explained and every menu item works. (PB-57) |  | Fawjiya Fahima Eifa | 5 | - Suspend and Activate ask for a required note (at least 10 characters), saved in PlatformActionLog.note and shown on the Activity page; resolving a ticket also needs a resolution note - The Companies page has Request access on each company: a form with the reason that creates a Support Access Request (existing API) and shows it on Access Requests as Pending - A company user gets a Help & Support page (Settings group): send a ticket with subject and description, and see their own tickets with status Open or Resolved and the resolution note - The sidebar has no item marked Soon: Projects, Payroll and Expenses are removed (the SRS keeps Projects and Expense as Not built)
ST-155 | As a Team, I want the tests, documents and demo script to match the Sprint 6 system and one more full rehearsal, so that the final build is ready to present. (PB-58) |  | Fawjiya Fahima Eifa | 5 | - python regression.py backend and python regression.py selenium pass, and npm run lint and npm run build pass; older Selenium tests that registered a company or typed a password are updated for the registration, names and menus of Sprint 6 - New requirements for profile and password, Permission descriptions and Role editing, Department and Designation detail, team attendance, subscription period and restricted mode, manual payment approval, plan change and the Platform Admin dashboard are in the traceability list with code evidence and show Done in SRS Section 7.2 - SRS, SDS (profile, catalog and billing sections), project structure, ER diagram and design system match the code (generate_docs and check_docs pass) - The demo script (Word) covers the new flows (register, pay and approve; profile; Role detail; Department detail; team attendance; billing timeline; Platform Admin dashboard) and has been rehearsed once on a clean install, with a bug-fix buffer
Carried Over from Sprint 5
Story ID | Category | Task | Owner | Estimate (hrs) | Status
— | — | Nothing is carried over: Sprint 5 is treated as complete (stated by Saif on Oct 20). If any Sprint 5 story turns out not to be Done, add it here as a story owned by Saif. | — | 0 | Done
Task Breakdown (Implementation)
Story ID | Category | Task | Owner | Estimate (hrs) | Status
ST-138 | Design | Design the catalog fields (codename, name, module, description), the sync step that runs on migrate before sync_system_roles, and the module groups | Md. Nazmuz Saif | 1 | To Do
ST-138 | Database | Add Permission.description with a migration and fill it for the 14 current Permissions | Md. Nazmuz Saif | 1 | To Do
ST-138 | Backend | Write rbac/catalog.py and the sync; return description from the Permission API; keep the CEO role holding every Permission | Md. Nazmuz Saif | 3 | To Do
ST-138 | Backend | Write the test that every permission_required codename used in the views exists in the catalog | Md. Nazmuz Saif | 2 | To Do
ST-138 | Frontend | Roles page: remove the hardcoded list, load Permissions from the API, group by module, fix the existing-Roles list so it shows every saved Permission | Md. Nazmuz Saif | 3 | To Do
ST-138 | Self-Test | Self-test a Role with all, one and no Permissions; migrate on a fresh and on an existing database; the CEO role holds every Permission | Md. Nazmuz Saif | 2 | To Do
ST-139 | Design | Design the sectioned picker, the Role detail page and the edit flow, including the locked CEO Role | Md. Nazmuz Saif | 1 | To Do
ST-139 | Backend | Return employee_count and the holders of a Role; refuse deleting a Role in use (ROLE_IN_USE) | Md. Nazmuz Saif | 2 | To Do
ST-139 | Frontend | Build the sectioned picker, the Role detail page, edit mode and the new Roles list | Md. Nazmuz Saif | 6 | To Do
ST-139 | Self-Test | Self-test edit add and remove, the locked CEO Role, delete in use, another company's Role | Md. Nazmuz Saif | 2 | To Do
ST-140 | Design | Design the profile fields, the editable whitelist and the display rule for names | Md. Nazmuz Saif | 1 | To Do
ST-140 | Database | Add full_name to User and the profile fields to Employee, with migrations (blank allowed for old rows) | Md. Nazmuz Saif | 2 | To Do
ST-140 | Backend | Profile endpoint with the whitelist; registration and Employee create/edit with the name | Md. Nazmuz Saif | 3 | To Do
ST-140 | Backend | Add employee_name next to every employee_email in the serializers; give the demo people names in seed_demo_data | Md. Nazmuz Saif | 2 | To Do
ST-140 | Frontend | Show the full name wherever a person appears (shared display helper, then every page) | Md. Nazmuz Saif | 3 | To Do
ST-140 | Self-Test | Self-test that email, roles and salary cannot be changed through the profile, old rows without a name, another company | Md. Nazmuz Saif | 2 | To Do
ST-141 | Design | Design the My Profile page for employees and for the Platform Admin | Md. Nazmuz Saif | 1 | To Do
ST-141 | Frontend | Build My Profile (view, edit, errors, unsaved-change warning) and the user-menu link | Md. Nazmuz Saif | 5 | To Do
ST-141 | Self-Test | Self-test the server field errors, the Platform Admin view, and that email cannot be edited | Md. Nazmuz Saif | 2 | To Do
ST-142 | Design | Design the temporary-password rule and the PASSWORD_CHANGE_REQUIRED gate | Md. Nazmuz Saif | 1 | To Do
ST-142 | Backend | Change-password endpoint with the token blacklist | Md. Nazmuz Saif | 4 | To Do
ST-142 | Backend | Temporary password, must_change_password and the PASSWORD_CHANGE_REQUIRED gate; keep the explicit-password path so older tests pass | Md. Nazmuz Saif | 4 | To Do
ST-142 | Frontend | Change-password form on My Profile, the forced redirect, the Employee create form (autocomplete off and new-password) and the one-time temporary password with Copy | Md. Nazmuz Saif | 4 | To Do
ST-142 | Self-Test | Self-test a wrong current password, the temporary password shown once, old tokens dead, the gate on every other endpoint | Md. Nazmuz Saif | 2 | To Do
ST-143 | Design | Design the detail page sections and who may see which field | Md. Nazmuz Saif | 1 | To Do
ST-143 | Backend | GET /employees/{id}/access/ (Roles and effective Permissions); hide contact fields unless self, manager chain or manage_employees (reuse can_view_employee_data) | Md. Nazmuz Saif | 4 | To Do
ST-143 | Frontend | Build the detail page with the profile, hierarchy and Permissions sections | Md. Nazmuz Saif | 5 | To Do
ST-143 | Self-Test | Self-test a person with no Role, several Roles, a colleague outside the reporting line, salary visibility, another company | Md. Nazmuz Saif | 2 | To Do
ST-144 | Design | Design the Team Attendance page and the scope rule (whole company with the Permission, otherwise subordinates) | Md. Nazmuz Saif | 1 | To Do
ST-144 | Backend | Add view_team_attendance to the catalog; build the team endpoint on month_calendar with check-in, check-out and hours; scope with get_all_subordinates | Md. Nazmuz Saif | 4 | To Do
ST-144 | Frontend | Build the page: dropdown, month navigation, calendar, cards and the day table; sidebar item shown only when allowed | Md. Nazmuz Saif | 5 | To Do
ST-144 | Self-Test | Self-test the CEO, a manager with a team, an employee with no team, an employee outside scope, another company | Md. Nazmuz Saif | 2 | To Do
ST-145 | Design | Design the states, the grace period, the restricted-mode allow-list and the reminder thresholds | Md. Nazmuz Saif | 2 | To Do
ST-145 | Database | Add the period fields and the new statuses to Subscription with a migration that gives old rows a period | Md. Nazmuz Saif | 2 | To Do
ST-145 | Backend | days_left helper, status transitions, process_subscriptions command and the billing_reminder Notification kind | Md. Nazmuz Saif | 4 | To Do
ST-145 | Backend | Restricted-mode permission class in the default permission classes with the allow-list; keep the test helper and seed data working | Md. Nazmuz Saif | 4 | To Do
ST-145 | Frontend | Restricted banner and a route guard that leaves only the Billing pages open | Md. Nazmuz Saif | 2 | To Do
ST-145 | Self-Test | Self-test the days left on boundary days and time zones, the job run twice, the grace period, the allow-list, and that Suspend still blocks login | Md. Nazmuz Saif | 3 | To Do
ST-146 | Design | Design the price rules, the payment states, the renewal date math and the invoice-on-approval rule | Md. Nazmuz Saif | 2 | To Do
ST-146 | Database | PaymentSubmission model with the unique transaction id and the one-pending rule, plus invoice fields for method and transaction id | Md. Nazmuz Saif | 2 | To Do
ST-146 | Backend | Quote endpoint and price rules; submit, list, approve and reject endpoints; extension and invoice creation; notifications | Md. Nazmuz Saif | 8 | To Do
ST-146 | Backend | Add manage_billing to the catalog; endpoint matrix coverage; audit log and PlatformActionLog entries | Md. Nazmuz Saif | 3 | To Do
ST-146 | Self-Test | Self-test approving twice, a duplicate transaction id, a tampered amount, another company, renewal date math, 1, 12 and 36 months | Md. Nazmuz Saif | 3 | To Do
ST-147 | Design | Design the four screens: choose a plan, pay, waiting and rejected | Md. Nazmuz Saif | 1 | To Do
ST-147 | Backend | Register creates pending_payment; the subscription status comes back in me; payment instructions come from server settings | Md. Nazmuz Saif | 3 | To Do
ST-147 | Frontend | Build the plan page with the months selector and live quote, the payment form, the waiting page with polling and the rejected state | Md. Nazmuz Saif | 6 | To Do
ST-147 | Self-Test | Self-test every duration, a wrong or missing field, resubmitting after a rejection, closing and reopening the browser while waiting | Md. Nazmuz Saif | 2 | To Do
ST-148 | Design | Design the Payments review page and the Subscriptions timeline | Montasim Kabir Mahin | 1 | To Do
ST-148 | Backend | Admin endpoint listing subscriptions with filters and days left, and the pending-payments count | Montasim Kabir Mahin | 2 | To Do
ST-148 | Frontend | Build the two pages, the confirm and reject dialogs and the sidebar badge | Montasim Kabir Mahin | 6 | To Do
ST-148 | Self-Test | Self-test approve, reject without and with a note, an already decided payment, the filters, a company user trying the endpoints | Montasim Kabir Mahin | 2 | To Do
ST-149 | Design | Design the timeline card, the renewal flow and the invoice detail page | Montasim Kabir Mahin | 1 | To Do
ST-149 | Backend | Extend process_subscriptions to create the renewal Invoice 7 days before the end (idempotent); invoice detail with payment info | Montasim Kabir Mahin | 3 | To Do
ST-149 | Frontend | Build the timeline card, the Renew flow with the pending banner, the invoice detail page and Print | Montasim Kabir Mahin | 8 | To Do
ST-149 | Self-Test | Self-test 8 days, 7 days, 1 day and 0 days left, the job run twice, a pending renewal, another company's invoice | Montasim Kabir Mahin | 2 | To Do
ST-150 | Design | Design both detail pages, the Head field and what a viewer without task access sees | Md. Tahsin Rahman Khan | 1 | To Do
ST-150 | Database | Add Department.head (an Employee of the same company) with a migration | Md. Tahsin Rahman Khan | 1 | To Do
ST-150 | Backend | GET /departments/{id}/overview/ and /designations/{id}/overview/ with hierarchy-scoped task details; refuse delete while in use | Md. Tahsin Rahman Khan | 4 | To Do
ST-150 | Frontend | Build the Department detail page, the Designation detail page, list links and the Head selector | Md. Tahsin Rahman Khan | 8 | To Do
ST-150 | Self-Test | Self-test a Department with no members, with overdue tasks, a viewer outside the chain, delete in use, another company | Md. Tahsin Rahman Khan | 2 | To Do
ST-151 | Design | Design the upgrade quote, the proration formula and the downgrade-at-renewal rule | Md. Tahsin Rahman Khan | 1 | To Do
ST-151 | Backend | Upgrade quote endpoint, upgrade approval through the ST-146 flow, downgrade rule | Md. Tahsin Rahman Khan | 4 | To Do
ST-151 | Frontend | Build the Change plan page, the quote and the payment form | Md. Tahsin Rahman Khan | 4 | To Do
ST-151 | Self-Test | Self-test a quote on day 1 and on the last day, same plan, a downgrade with a too-large team, a pending submission already open | Md. Tahsin Rahman Khan | 2 | To Do
ST-152 | Design | Design the company detail page and exactly what it may show | Sadia Jahan Disha | 1 | To Do
ST-152 | Backend | GET /platform-admin/admin/companies/{id}/ with the aggregated, privacy-safe data | Sadia Jahan Disha | 4 | To Do
ST-152 | Frontend | Build the detail page and link the company list rows | Sadia Jahan Disha | 4 | To Do
ST-152 | Self-Test | Self-test a company with no payments, a suspended company, that no employee-level data is returned, a company user calling it | Sadia Jahan Disha | 2 | To Do
ST-153 | Design | Design the dashboard cards, the two charts and the Needs attention list | Sadia Jahan Disha | 1 | To Do
ST-153 | Backend | Summary service and endpoint for companies by state, revenue, dues and the attention counts | Sadia Jahan Disha | 4 | To Do
ST-153 | Frontend | Build the dashboard with MetricCards, charts and the attention list; make it the Platform Admin home | Sadia Jahan Disha | 5 | To Do
ST-153 | Self-Test | Self-test with no companies, many companies (query count), revenue after an approval, a company user calling it | Sadia Jahan Disha | 2 | To Do
ST-154 | Design | Design the note dialogs, the Request access form and the Help & Support page | Fawjiya Fahima Eifa | 1 | To Do
ST-154 | Database | Add TicketResolution note (resolution_note) to SupportTicket with a migration | Fawjiya Fahima Eifa | 1 | To Do
ST-154 | Backend | Require the note in suspend, activate and resolve; return it in the Activity and ticket APIs | Fawjiya Fahima Eifa | 2 | To Do
ST-154 | Frontend | Note dialogs, Request access form, Help & Support page, sidebar cleanup | Fawjiya Fahima Eifa | 5 | To Do
ST-154 | Self-Test | Self-test a missing or short note, request access twice, a ticket from another company, the sidebar for every role | Fawjiya Fahima Eifa | 2 | To Do
ST-155 | Design | Update the demo script with the Sprint 6 flows, in order, with the data each step needs | Fawjiya Fahima Eifa | 2 | To Do
ST-155 | Backend | Add the new requirements to the traceability list with evidence and regenerate the documents | Fawjiya Fahima Eifa | 3 | To Do
ST-155 | Backend | Update the Selenium helpers and older tests for the registration and billing flow, names and the new menus | Fawjiya Fahima Eifa | 3 | To Do
ST-155 | Self-Test | Rehearsal: follow the script end to end on a clean install with demo data and log every slip | Fawjiya Fahima Eifa | 3 | To Do
ST-155 | Backend | Bug-fix buffer: fix the problems found in the rehearsal | Fawjiya Fahima Eifa | 3 | To Do
ST-155 | Self-Test | Run both test suites, npm run lint and npm run build on the final build and tag the release | Fawjiya Fahima Eifa | 2 | To Do
Cross-Test Assignment (every story is tested by someone other than its owner)
Story ID |  | Story | Code Owner |  | Selenium Tester
ST-138 |  | Permission catalog in code and Roles page bug fix | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-139 |  | Roles v2: sections, role detail and role edit | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-140 |  | Names, profile data and the profile API | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-141 |  | My Profile page for every user | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-142 |  | Password safety: change password and temporary password | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-143 |  | Employee detail page v2 | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-144 |  | Team attendance with employee dropdown | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-145 |  | Subscription period, days left, reminders and restricted mode | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-146 |  | Duration pricing, manual payment submission and admin approval | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-147 |  | Registration with plan choice, payment and waiting page | Md. Nazmuz Saif |  | Md. Tahsin Rahman Khan
ST-148 |  | Platform Admin payments review and subscriptions timeline | Montasim Kabir Mahin |  | Md. Nazmuz Saif
ST-149 |  | Company Billing timeline, renewal and invoice detail | Montasim Kabir Mahin |  | Md. Nazmuz Saif
ST-150 |  | Department and Designation detail pages | Md. Tahsin Rahman Khan |  | Montasim Kabir Mahin
ST-151 |  | Plan upgrade request with extra amount | Md. Tahsin Rahman Khan |  | Montasim Kabir Mahin
ST-152 |  | Platform Admin company detail page | Sadia Jahan Disha |  | Fawjiya Fahima Eifa
ST-153 |  | Platform Admin dashboard | Sadia Jahan Disha |  | Fawjiya Fahima Eifa
ST-154 |  | Platform Admin notes, access request, support request and sidebar cleanup | Fawjiya Fahima Eifa |  | Sadia Jahan Disha
ST-155 |  | Sprint 6 regression, documents and demo script | Fawjiya Fahima Eifa |  | Sadia Jahan Disha
Overall Testing — Selenium Cross-Review QA Pass (each tester tests another member's story)
Story ID | Test Case No. | Test Case | Tester | Estimate (hrs) | Result
ST-138 | TC-90 | [Selenium] As the CEO create a Role and tick one Permission from every module — expect the new Role card to list all of them, not four | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-138 | TC-91 | [Selenium] Open the Roles page — expect Permissions grouped by module, each with a description, and every name present in the backend | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-139 | TC-92 | [Selenium] As the CEO open a Role's detail page — expect Permissions grouped by module with descriptions and the list of employees who hold it | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-139 | TC-93 | [Selenium] Edit a Role: add and remove Permissions and save — expect the detail page and the Roles list to show the change; the CEO Role shows no Edit button | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-139 | TC-94 | [Selenium] Delete a Role that an Employee holds — expect a clear refusal and the Role still listed | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-140 | TC-95 | [Selenium] Register a new company with a full name — expect the top bar and the Employees list to show that name | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-140 | TC-96 | [API] PATCH the profile with a new phone and also with email, department and salary — expect only the phone changed and the other fields ignored or refused | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-141 | TC-97 | [Selenium] Open My Profile as an Employee, change the phone number, save and reload — expect the new number and no way to edit the email | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-141 | TC-98 | [Selenium] Open My Profile as the Platform Admin — expect the name and contact fields and no company fields | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-142 | TC-99 | [Selenium] As the CEO add an Employee without typing a password — expect a temporary password shown once, and the browser not filling the email or password fields | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-142 | TC-100 | [Selenium] Log in as that Employee — expect to be sent to My Profile to set a new password before anything else; change it with a wrong current password first — expect an error, then success | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-142 | TC-101 | [Selenium] Change a password, then use an older refresh token — expect it refused | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-143 | TC-102 | [Selenium] As the CEO open an Employee's detail page — expect the full profile and the Permissions grouped by module under each Role | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-143 | TC-103 | [Selenium] As an Employee open a colleague outside my reporting line — expect name and designation only, with no phone, address or salary | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-144 | TC-104 | [Selenium] As the CEO pick an employee in Team Attendance — expect that person's calendar, cards and a table of check-in and check-out times | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-144 | TC-105 | [Selenium] As a Department Head open Team Attendance — expect only the people in the team in the dropdown; as a plain Employee expect no menu item | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-145 | TC-106 | [Selenium] Log in as the CEO of a company whose subscription has expired — expect the restricted-mode banner and only the Billing page working; other pages show a clear message | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-145 | TC-107 | [Selenium] Run the daily command for a company 7 days before its end — expect a billing reminder in the CEO's notifications, and no second reminder when the command runs again | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-146 | TC-108 | [API] Ask for a quote for 1, 3 and 12 months — expect price times months, the 12-month discount, and a 40-month request refused | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-146 | TC-109 | [API] Submit the same transaction id twice and approve one submission twice — expect the second submission refused and no second invoice or extension | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-147 | TC-110 | [Selenium] Register a new company, choose Professional for 3 months and submit a bKash payment — expect the waiting page and no access to the dashboard | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-147 | TC-111 | [Selenium] As the Platform Admin approve that payment, then as the new owner reload — expect the dashboard and a paid invoice for 3 times the monthly price less any discount | Md. Tahsin Rahman Khan | 1.5 | Not Run
ST-148 | TC-112 | [Selenium] As the Platform Admin open Payments — expect pending submissions with details; approve one — expect it Approved with the new end date and invoice number | Md. Nazmuz Saif | 1.5 | Not Run
ST-148 | TC-113 | [Selenium] Reject a payment without a note — expect a refusal; with a note — expect Rejected and the note visible to the company | Md. Nazmuz Saif | 1.5 | Not Run
ST-148 | TC-114 | [Selenium] Open Subscriptions — expect companies sorted by days left with the expiring ones highlighted | Md. Nazmuz Saif | 1.5 | Not Run
ST-149 | TC-115 | [Selenium] Open Billing as the CEO — expect the timeline with days left, the end date, the status and the invoice list | Md. Nazmuz Saif | 1.5 | Not Run
ST-149 | TC-116 | [Selenium] Open an invoice — expect its full detail with payment method and transaction id; open another company's invoice address — expect not found | Md. Nazmuz Saif | 1.5 | Not Run
ST-149 | TC-117 | [Selenium] For a company 5 days from its end — expect Expiring soon and a renewal invoice, and after submitting the payment a pending banner | Md. Nazmuz Saif | 1.5 | Not Run
ST-150 | TC-118 | [Selenium] Open a Department as the CEO — expect its members with designation and open-task counts, the task summary and the running tasks | Montasim Kabir Mahin | 1.5 | Not Run
ST-150 | TC-119 | [Selenium] Open the same Department as an Employee outside the manager chain — expect counts but no task titles | Montasim Kabir Mahin | 1.5 | Not Run
ST-150 | TC-120 | [Selenium] Open a Designation — expect the employees who hold it; delete it while in use — expect a refusal | Montasim Kabir Mahin | 1.5 | Not Run
ST-151 | TC-121 | [Selenium] As the CEO on Basic choose Professional — expect the extra amount based on the days left and no change to the end date | Montasim Kabir Mahin | 1.5 | Not Run
ST-151 | TC-122 | [Selenium] Submit the upgrade payment, then approve it as Platform Admin — expect Professional, an invoice for the extra amount and the higher employee limit | Montasim Kabir Mahin | 1.5 | Not Run
ST-152 | TC-123 | [Selenium] As the Platform Admin open a company's detail page — expect plan, timeline, owner contact, counts and recent actions, and no employee names | Fawjiya Fahima Eifa | 1.5 | Not Run
ST-152 | TC-124 | [Selenium] Suspend the company from its detail page with a note — expect status Suspended and the note in the recent actions | Fawjiya Fahima Eifa | 1.5 | Not Run
ST-153 | TC-125 | [Selenium] Log in as the Platform Admin — expect the dashboard with company-state cards and revenue and due numbers that match the invoices | Fawjiya Fahima Eifa | 1.5 | Not Run
ST-153 | TC-126 | [Selenium] Approve a pending payment — expect the pending-payments card down by one and revenue up by that amount | Fawjiya Fahima Eifa | 1.5 | Not Run
ST-154 | TC-127 | [Selenium] As the Platform Admin suspend a company with a note — expect the note in Activity; suspend without a note — expect a refusal | Sadia Jahan Disha | 1.5 | Not Run
ST-154 | TC-128 | [Selenium] As the Platform Admin request access to a company from the Companies page — expect the request in Access Requests as Pending | Sadia Jahan Disha | 1.5 | Not Run
ST-154 | TC-129 | [Selenium] As an Employee send a ticket from Help & Support — expect it Open in my list; after the admin resolves it with a note expect Resolved and the note | Sadia Jahan Disha | 1.5 | Not Run
ST-154 | TC-130 | [Selenium] Open the sidebar as the CEO — expect no item marked Soon | Sadia Jahan Disha | 1.5 | Not Run
ST-155 | TC-131 | [Rehearsal] Follow the updated demo script on a clean install with demo data — expect every step to work | Sadia Jahan Disha | 1.5 | Not Run
ST-155 | TC-132 | [Rehearsal] Run both test suites, npm run lint and npm run build on the final build — expect all to pass | Sadia Jahan Disha | 1.5 | Not Run
Coordination Tasks (Mahin)
Task |  |  | Owner | Estimate (hrs) | Status
Sprint 6 planning session — confirm scope, the order of the stories (the order they are implemented), the owners and the cut line |  |  | Montasim Kabir Mahin | 2 | To Do
Daily coordination and progress tracking, with extra attention to the stories that others need: ST-138 (catalog), ST-140 (names and profile), ST-145 (subscription period) and ST-146 (payments) |  |  | Montasim Kabir Mahin | 4 | To Do
Cross-test hand-off tracking — confirm each story is tested by a non-owner and that no tester carries too many |  |  | Montasim Kabir Mahin | 2 | To Do
Mid-sprint check on Oct 28 — decide if the Should stories (ST-151, ST-152, ST-153) stay in Sprint 6 or move to Sprint 7 |  |  | Montasim Kabir Mahin | 1 | To Do
Sprint 6 review and retrospective facilitation |  |  | Montasim Kabir Mahin | 2 | To Do
| Total Story Points |  |  | 102
| Total Implementation Hours |  |  | 232
| Total QA Hours |  |  | 64.5
| Total Coordination Hours |  |  | 11

## Gap Register
Ordinis — Gap Register (gaps and bugs found after Sprint 5)
The 23 items Saif listed on Oct 20 (G-01 to G-23, same order as his list), checked against the code, plus 8 more found during the analysis (X-01 to X-08). Every row names the Sprint 6 story that fixes it.
Summary
Gaps from your list |  |  |  | 23
Extra findings |  |  |  | 8
Open |  |  |  | 31
Fixed |  |  |  | 0
High priority |  |  |  | 15
Bugs (G-03, G-08, X-02) |  |  |  | 3
Types: Bug = something is wrong now; Missing feature = not built; Enhancement = built but weak; Design gap = built in a way that cannot work; Gap = a missing piece. Size: S under 1 day, M about 1 to 2 days, L more. Update the Status column to Fixed only when the story is Done.
Gap ID | No. in your list | Area | Type | What is wrong or missing | What the code shows (root cause or current state) | Recommended fix and the better way | Priority | Size | Depends on | Sprint 6 story | Status
G-01 | 1 | Organization | Missing feature | The Department page has no detail view: who is in a department, what each person does, what work is running. | Departments have only list and create/edit/delete. Department has no head field and there is no overview endpoint. Task visibility follows the hierarchy rule (FR-13), so a detail page must not show everyone's tasks to everyone. | Department detail page with a GET /departments/{id}/overview/ endpoint: members with designation, manager and open-task counts, a task summary and the running tasks. Add Department.head. Task titles only to people who may see them; everybody else sees counts. | High | L | G-04 | ST-150 | Open
G-02 | 2 | Organization | Enhancement | The Designations page is only a list; it needs improving and probably a detail page. | List and CRUD only. Deleting a Designation silently clears the link on every employee who holds it (the foreign key is SET_NULL). | Designation detail page listing the people who hold it, with department. Refuse the delete while the Designation is in use and say who holds it. | Medium | S | G-04 | ST-150 | Open
G-03 | 3 | Organization | Bug | On the Employee page, creating an employee shows email and password already filled in by the browser. | The form inputs have no autocomplete attributes, so the browser password manager fills in the logged-in user's own saved login. | Set autocomplete off and new-password. Better way: the CEO never types an employee's password; the system makes a one-time temporary password shown once, and the employee must change it at first login. | Medium | S | G-09 | ST-142 | Open
G-04 | 4 | Profile | Missing feature | The Employee detail page is weak: it needs name and email, a full profile, and a permission-wise view of what the person can do. | No name exists anywhere: User has only an email and Employee only an employee code. The page shows hierarchy only. The Roles a person holds are not expanded into Permissions. | Add full_name (User) and profile fields (Employee: phone, address, emergency contact, joined on). Detail page with the profile, hierarchy and the effective Permissions per Role. Contact data only for the person, their managers and manage_employees; salary only with manage_finance. | High | L | G-05 | ST-140, ST-143 | Open
G-05 | 5 | RBAC | Enhancement | The Roles page offers only a few Permission checkboxes; they should be many and arranged in sections. | The catalog really has 14 Permissions. The page hardcodes 12 names and 6 of them do not exist in the backend. Permissions have no module sections on screen. | Permission catalog in code (codename, name, module, description) synced on migrate; a sectioned picker with Select all. Add a new Permission only together with the feature it protects, because a Permission that protects nothing is misleading. | High | M | G-08 | ST-138, ST-139 | Open
G-06 | 6 | RBAC | Missing feature | There is no page that explains what each Permission and each Role lets a person do; headings alone are not clear. | The Permission API returns only codename, name and module. There is no description and no Role detail page. | A plain-language description for every Permission and a Role detail page that groups Permissions by module with those descriptions and lists the people who hold the Role. | High | M | G-05 | ST-138, ST-139 | Open
G-07 | 7 | RBAC | Missing feature | A Role cannot be edited after it is created. | The API already allows PUT and PATCH with manage_roles; the page has only create and delete. The CEO system Role must stay locked. | Edit form for name, description and Permissions, with a warning of how many employees are affected; the CEO Role stays read-only and says why. | High | S | G-05 | ST-139 | Open
G-08 | 8 | RBAC | Bug | A Role created with many Permissions shows only 4 in the existing-Roles list. | Root cause found in the code: six of the page's hardcoded names (approve_leave, approve_request, manage_attendance, manage_payroll, view_finance, approve_expense) do not exist in the backend; the create handler keeps only real ids and silently drops the rest, so the Role is saved with fewer Permissions and the page never says so. | Use the backend catalog as the only source for the page; if a ticked Permission is not saved, show an error; add a test that every permission_required codename used in the views exists in the catalog so this class of bug cannot return. | High | S | — | ST-138 | Open
G-09 | 9 | Profile | Missing feature | Every employee should have their own profile section where they can see and edit their details. | /auth/me/ is read-only. There is no self-edit endpoint and no change-password endpoint. | GET and PATCH /auth/profile/ with a whitelist (full name, phone, address, emergency contact); email, department, designation, manager, Roles and salary can never be changed through it. Change password needs the current password and ends other sessions. A My Profile page. | High | M | G-04 | ST-140, ST-141, ST-142 | Open
G-10 | 10 | Attendance | Missing feature | A CEO or anyone with the Permission should see all employees' attendance (days present, times) by choosing an employee from a dropdown. | The attendance API is own-data only. The SRS marks FR-13 as Partly for exactly this: a manager cannot list a team member's attendance. | A new Permission view_team_attendance; a team endpoint built on the existing month calendar plus check-in, check-out and hours; scope is the whole company with the Permission, otherwise the user's subordinates; outside scope answers 404. | High | M | G-05 | ST-144 | Open
G-11 | 11 | Profile | Missing feature | The Platform Admin side needs a profile section too. | A Platform Admin is a User without an Employee, with no name and no profile page. | Reuse the same profile endpoint and My Profile page (full_name lives on User, so it works without an Employee). | Low | S | G-09 | ST-140, ST-141 | Open
G-12 | 12 | Platform Admin | Missing feature | The Companies page has no company detail page; the Platform Admin needs a company's details and its CEO's information. | The page is a list with Suspend and Activate only; there is no detail endpoint. | Company detail page and endpoint: plan, subscription timeline, owner (CEO) contact, employee count against the limit, payments and tickets summary, recent platform actions. Counts and contacts only, never employee names, tasks or salary, so Break-Glass stays the only way into company data. | Medium | M | G-17 | ST-152 | Open
G-13 | 13 | Platform Admin | Missing feature | The Platform Admin needs a dashboard: companies by state, revenue, dues and billing at a glance. | The Platform Admin home is the Companies list. Revenue and dues cannot exist yet because payments are not recorded. | A summary endpoint and a dashboard (cards, revenue per month, companies by state, a Needs attention list), built after the billing stories so the numbers are real. | Medium | M | G-17, G-18 | ST-153 | Open
G-14 | 14 | Platform Admin | Gap | Suspend and Activate on the Companies page have no place to write a note, while the Activity page shows a note column. | PlatformActionLog has a note field but the endpoints take no body, so the note is always empty. | Require a note (at least 10 characters) on suspend, activate and ticket resolve; show it in Activity and on the company detail page. | High | S | — | ST-154 | Open
G-15 | 15 | Platform Admin | Missing feature | There is nothing to request access to a company (Support Access Request). | The backend endpoint POST /platform-admin/requests/ exists and is tested; there is no form in the page. | A Request access form (reason) on each company row; later also from the company detail page and from a ticket. | Medium | S | — | ST-154 | Open
G-16 | 16 | Platform Admin | Missing feature | A company user has no way to ask the platform for support: no form, no button. | The backend endpoint POST /platform-admin/company/tickets/ exists; there is no page. A ticket has no resolution message for the person who sent it. | A Help & Support page: send a ticket, see my tickets with status and the resolution note the admin must write. | Medium | S | — | ST-154 | Open
G-17 | 17 | Billing | Missing feature | Billing needs a timeline page, for every company and for the Platform Admin: days left since purchase, counting down daily, a reminder 5 to 7 days before the end, and automatic deactivation if unpaid. | A subscription has only started_on: no end date, no reminders, no expiry; suspension is manual. | Period start and end; days left computed from today's date in the company time zone (never stored or decremented by a job, so a missed job cannot make it wrong); in-app reminders at 7, 3 and 1 days; a daily command plus a check on every request; after the end plus a 3-day grace the company becomes restricted (see X-03), not locked out. | High | L | — | ST-145, ST-149, ST-148 | Open
G-18 | 18 | Billing | Design gap | The billing sector is incomplete: a new client should register, choose a plan, pay manually (bKash, Nagad or other) by submitting a form, wait, and be approved by the Platform Admin. | Every new company starts on Basic and is active at once; no payment record exists. | Register creates the company as pending_payment; plan and months; a manual payment form; a waiting page; a PaymentSubmission model; a Platform Admin review page; the company starts only when the admin approves. The amount is computed on the server and a transaction id can be used once. | High | L | G-17 | ST-146, ST-147, ST-148 | Open
G-19 | 19 | Billing | Missing feature | A client should be able to choose monthly, yearly or a custom length (for example 3 months), with price and timeline following it. | Plans have only a monthly price. | Price = monthly price × months (1 to 36), with 12 months costing 10 months (the rule is one constant and easy to change); a quote endpoint so the screen and the server always agree. | Medium | M | G-18 | ST-146, ST-147 | Open
G-20 | 20 | Billing | Design gap | When the time ends, paying again should create an invoice automatically (or a better way). | Invoices come from a command, one per month, and are not tied to any payment. | Better way: create the renewal Invoice 7 days before the end so the client sees what to pay; the client pays and submits the transaction against it; the admin's approval marks it Paid and extends the subscription from the old end date, so no days are lost. An invoice is created on approval, not when a form is submitted. | Medium | M | G-17, G-18 | ST-146, ST-149 | Open
G-21 | 21 | Billing | Missing feature | Invoices need a detail page. | The Billing page only lists invoices. | An invoice detail page with number, period, months, amount, dates, payment method, transaction id and a Print button; another company's invoice is a 404. | Low | S | G-20 | ST-149 | Open
G-22 | 22 | Billing | Missing feature | There is no way to update a plan; the client should see the extra amount, pay, request, and the admin approves. | change_plan exists only as a service used by the set_company_plan command. | Upgrade request: extra = (new monthly price − old monthly price) × days left ÷ 30, from the server; paid outside, submitted as a payment of kind upgrade; the admin approves and the plan changes at once. A lower plan only at the next renewal, and only if the team fits. | Medium | M | G-18 | ST-151 | Open
G-23 | 23 | UI | Cleanup | Sidebar items marked Soon must be completed or removed. | Projects, Payroll and Expenses are muted Soon items. Payroll is already covered by Salary Structures and Payslips; Projects and Expense are listed as Not built in the SRS. | Remove all three so nothing in the menu looks unfinished. | Low | S | — | ST-154 | Open
X-01 | — | RBAC | Gap (found in analysis) | Deleting a Role that employees still hold is not handled. | The error-handling reference lists it as Not handled; only the CEO system Role and a Role used by an approval step are protected. | Refuse the delete with code ROLE_IN_USE and show who holds the Role. | Medium | S | G-07 | ST-139 | Open
X-02 | — | Organization | Bug (found in analysis) | Deleting a Department silently clears the Department on its employees. | Employee.department is SET_NULL. | Refuse the delete while the Department has employees and say who is in it (same rule as the Designation). | Medium | S | G-01 | ST-150 | Open
X-03 | — | Billing | Design gap (found in analysis) | A company that is deactivated for non-payment could not even log in to pay. | Suspend (is_active false) blocks login and every request, which is right for a misuse suspension but wrong for an unpaid plan. | A separate restricted mode: the user logs in, but only Billing, payment, profile and support endpoints work (code SUBSCRIPTION_RESTRICTED). The same gate also holds a new company in pending_payment, so one mechanism serves both. Suspend stays a full block. | High | M | G-17, G-18 | ST-145 | Open
X-04 | — | RBAC | Gap (found in analysis) | Nothing checks that the codenames used in the views exist in the Permission catalog, which is how G-08 happened. | Permission codenames are plain strings in views and in the frontend. | A test that reads every permission_required in the ViewSets and fails if the codename is not in the catalog. | High | S | G-08 | ST-138 | Open
X-05 | — | Profile | Gap (found in analysis) | Users cannot change their password and cannot end their other sessions. | There is no change-password endpoint. | Change password with the current password; blacklist the user's other refresh tokens; a temporary password forces a change at first login. | High | M | G-09 | ST-142 | Open
X-06 | — | Billing | Design rule (found in analysis) | Manual payments can be faked or repeated. | No payment model exists yet. | The amount is always computed on the server, a transaction id is unique per method, one pending submission per company, and the approval is idempotent (locked row) so approving twice never extends twice. A company can never approve its own payment. | High | M | G-18 | ST-146 | Open
X-07 | — | Quality | Gap (found in analysis) | The SRS traceability list and the documents do not yet know the new features. | Documents are generated from the code, but the requirement list is a hand-kept table with code evidence. | Add the new requirements with evidence, regenerate the documents, update the demo script. | Medium | S | all | ST-155 | Open
X-08 | — | Quality | Risk (found in analysis) | Existing tests and Selenium helpers assume a company is active right after register and that an employee is created with a typed password. | register_company in the backend test helpers and the Selenium login flow. | Keep an explicit-password path for employee creation; make the register_company test helper activate the subscription; update the Selenium helpers in ST-154. | Medium | S | G-18 | ST-145, ST-155 | Open