## Sprint Retro
Ordinis — Sprint 2 Retrospective
Sprint Details |  |  | Sprint Summary
Sprint Name / No. | Sprint 2 |  | Total Stories | 4
Sprint Start Date | 10-Sep-2026 |  | Completed Stories | 3
Sprint End Date | 23-Sep-2026 |  | Incomplete Stories | 1
|  |  | New Backlog Stories Created | 1
|  |  | Completion % | 75%
Story Status / Task Tracking
Story No. | Task | Task Status | Task Owner | Reason for Not Completing Task | New Backlog Story No. | Story Result
ST-107 | Design recursive traversal approach for subordinate/manager resolution over reports_to | Completed | Md. Nazmuz Saif |  |  | Completed
ST-107 | Implement get_all_subordinates(employee) and get_all_managers(employee) service functions | Completed | Md. Nazmuz Saif
ST-107 | Show subordinate list on the Employee detail view | Completed | Md. Nazmuz Saif
ST-107 | Self-test recursive resolution against a 4-level test hierarchy | Completed | Md. Nazmuz Saif
ST-108 | Design Permission/Role/RolePermission schema, formalizing the Designation-vs-Role separation | Completed | Montasim Kabir Mahin |  |  | Completed
ST-108 | Create Permission and Role models and migrations | Completed | Montasim Kabir Mahin
ST-108 | Build PermissionSerializer (read-only) and RoleSerializer/ViewSet | Completed | Montasim Kabir Mahin
ST-108 | Build Roles management page (create Role, select Permissions) | Completed | Montasim Kabir Mahin
ST-108 | Self-test Role creation/retrieval and company-level scoping | Completed | Montasim Kabir Mahin
ST-109 | Design EmployeeRole schema (Employee <-> Role assignment) | Completed | Sadia Jahan Disha |  |  | Completed
ST-109 | Create EmployeeRole model and migration | Completed | Sadia Jahan Disha
ST-109 | Build EmployeeRoleSerializer/ViewSet (assign/revoke) | Completed | Sadia Jahan Disha
ST-109 | Add assign/revoke Role controls to the Employee page | Completed | Sadia Jahan Disha
ST-109 | Self-test assigning multiple Roles and revoking a Role | Completed | Sadia Jahan Disha
ST-110 | Design the HasPermission / PermissionRequiredMixin enforcement approach | Deferred | Fawjiya Fahima Eifa | Task paused during Sprint 2 (reason not recorded — confirm with owner). | PB-26 | Incomplete
ST-110 | Implement Employee.has_permission(), HasPermission DRF permission class, and PermissionRequiredMixin; apply across organization and rbac ViewSets | Deferred | Fawjiya Fahima Eifa | Task paused during Sprint 2 (reason not recorded — confirm with owner). | PB-26
ST-110 | Hide/disable UI controls the current user lacks permission for | Deferred | Fawjiya Fahima Eifa | Task paused during Sprint 2 (reason not recorded — confirm with owner). | PB-26
ST-110 | Self-test that a permission-gated action is blocked without the permission and allowed with it | Deferred | Fawjiya Fahima Eifa | Task paused during Sprint 2 (reason not recorded — confirm with owner). | PB-26

## New Backlog
New Backlog Stories for Incomplete Tasks
At retrospective time, New Backlog Status is limited to To Do or Ready. In Progress begins only after a story is selected during Sprint Planning.
New Backlog Story No. | Source Sprint Story No. | Incomplete Task | Owner | Reason / Context | Priority | Backlog Status | Notes / Acceptance Criteria
PB-26 | ST-110 | Design: HasPermission / PermissionRequiredMixin enforcement approach (2h) Backend: Employee.has_permission(), HasPermission DRF class, PermissionRequiredMixin on organization + rbac ViewSets (5h) Frontend: hide/disable UI controls the user lacks permission for (3h) Self-Test: gated action blocked without permission, allowed with it (1h) | Fawjiya Fahima Eifa | All 4 ST-110 tasks (11 hrs) were marked Pause in Sprint 2; none delivered. Reason not recorded — confirm with owner before re-planning. | High | To Do | Carry-over of PB-10 (ST-110). Acceptance criteria: - Employee.has_permission(codename) correctly reflects the Employee's assigned Roles' Permissions - A protected endpoint rejects the request if the acting Employee lacks the required permission - Verified: an Employee without a Role cannot perform a Role-gated action

## Retrospective
Sprint Retrospective Discussion & Actions
A. What Went Well
No. | Observation / Feedback | Impact | Action / Follow-up | Owner | Target / Notes
1 | ST-107 (recursive subordinate / manager-chain resolution) was delivered end-to-end — all 4 tasks done and both QA test cases (TC-11, TC-12) passed on the 4-level hierarchy. | High | Reuse get_all_subordinates / get_all_managers as the standard hierarchy helpers in future features instead of re-implementing traversal. | Md. Nazmuz Saif | Apply from Sprint 3 onward.
2 | Story ownership was rotated as planned: ST-107, ST-108, ST-109 and ST-110 each had a different owner (Saif, Montasim, Sadia, Fawjiya) — the Sprint 1 retro action was applied. | High | Keep the one-owner-per-story rotation when stories are assigned at Sprint 3 planning. | Montasim Kabir Mahin | Confirmed for Sprint 3.
3 | ST-108 and ST-109 were built end-to-end (Design → Self-Test, 10 of 10 tasks done) by team members who did not code in Sprint 1. | High | Keep giving these members full-story ownership with lighter-scope stories; Md. Nazmuz Saif stays as fallback. | Montasim Kabir Mahin | Ongoing from Sprint 3.
4
5
6
7
8
B. What Didn't Go Well
No. | Observation / Feedback | Impact | Action / Follow-up | Owner | Target / Notes
1 | ST-110 (permission enforcement, 5 pts) was not delivered — all 4 tasks (Design, Backend, Frontend, Self-Test; 11 hrs) are marked Pause, so the enforcement part of the RBAC sprint goal is still open. | High | Carried to the backlog as PB-26. Confirm with the owner why it paused, then re-plan it at Sprint 3 planning. | Fawjiya Fahima Eifa | Re-plan at Sprint 3 planning.
2 | QA is behind development: 5 of 8 Sprint 2 test cases (TC-14 to TC-18) are still 'to do', including TC-14 for ST-108 and TC-15/TC-16 for ST-109, although both stories' build tasks are done. | High | Run TC-14, TC-15 and TC-16 first thing in Sprint 3 so ST-108 and ST-109 are QA-verified; TC-17/TC-18 follow once ST-110 is built. | Md. Tahsin Rahman Khan | Start of Sprint 3.
3
4
5
6
7
8
C. What Can Be Improved
No. | Observation / Feedback | Impact | Action / Follow-up | Owner | Target / Notes
1 | A story should count as done only after its QA test cases pass — ST-108 and ST-109 show every task Completed here but are not QA-verified yet. | High | Agree at Sprint 3 planning that a story is Completed only when its QA test cases have passed, and track QA test cases as tasks in the retro sheet. | Montasim Kabir Mahin | Decide at Sprint 3 planning.
2 | Status values in the planning sheet were inconsistent (Done / done, Pause, to do), and 'Pause' has no matching Task Status in the retro lists. | Medium | Use only the standard list values (Not Started, In Progress, Blocked, Completed, Deferred) and record a reason whenever a task is paused or blocked. | Montasim Kabir Mahin | Effective Sprint 3.
3 | ST-110 is a cross-cutting story (permission checks across organization and rbac ViewSets, plus UI gating) and was the only Sprint 2 story that stalled. | Medium | When re-planning, check what ST-110 needs from ST-108/ST-109 and consider splitting backend enforcement and UI gating into smaller stories. | Fawjiya Fahima Eifa | Apply at ST-110 re-planning.
4
5
6
7
8

## Lists
Task Status | New Backlog Status | Priority | Impact
Not Started | To Do | High | High
In Progress | Ready | Medium | Medium
Blocked |  | Low | Low
Completed
Deferred