## Sprint Retro
Ordinis — Sprint 3 Retrospective
Sprint Details |  |  | Sprint Summary
Sprint Name / No. | Sprint 3 |  | Total Stories | 9
Sprint Start Date | 30-Sep-2026 |  | Completed Stories | 8
Sprint End Date | 07-Oct-2026 |  | Incomplete Stories | 1
|  |  | New Backlog Stories Created | 1
|  |  | Completion % | 88.89%
Story Status / Task Tracking
Story No. | Task | Task Status | Task Owner | Reason for Not Completing Task | New Backlog Story No. | Story Result
ST-111 | Design permission-enforcement flow, CEO Role bootstrap at registration, and tenant-safe company resolution | Completed | Md. Nazmuz Saif |  |  | Completed
ST-111 | Seed the full Permission set and verify all migrations on a fresh database | Completed | Md. Nazmuz Saif
ST-111 | Fix HasPermission and IsCompanyActive; remove get_effective_company from mixins, views, serializers, and MeView | Completed | Md. Nazmuz Saif
ST-111 | Create the CEO Role inside the atomic company registration; add PermissionRequiredMixin to RoleViewSet; move RBAC into the rbac app | Completed | Md. Nazmuz Saif
ST-111 | Block self-manager and reports_to cycles on Employee create/update | Completed | Md. Nazmuz Saif
ST-111 | Build the Company Registration page (form, validation, API call, auto-login) | Completed | Md. Nazmuz Saif
ST-111 | Add subordinate list to Employee detail and Role assign/revoke to the Employee page; hide controls by permission | Completed | Md. Nazmuz Saif
ST-111 | Self-test 403 without permission, 200 with it, cross-company access, cycle block, and fresh-DB registration | Completed | Md. Nazmuz Saif
ST-111 | TC-19: [Selenium] Log in as an Employee without the manage_departments Permission and try to add a Department — expect an error message and no record created | Completed | Montasim Kabir Mahin
ST-111 | TC-20: [Selenium] Log in as a CEO right after registration and add a Department — expect success (CEO Role assigned automatically) | Completed | Montasim Kabir Mahin
ST-111 | TC-21: [Selenium] Register a new company from the registration page — expect a redirect to the dashboard as CEO of that company only | Completed | Montasim Kabir Mahin
ST-111 | TC-22: [Selenium] Try to set an Employee as their own manager or create a reports_to cycle — expect the request blocked with a message | Completed | Montasim Kabir Mahin
ST-111 | TC-23: [Selenium] Open an Employee detail page — expect the subordinate list; assign then revoke a Role — expect the page to update | Completed | Montasim Kabir Mahin
ST-112 | Design ApprovalChain and ApprovalStep schema (ordered steps, approver Role) | Completed | Md. Nazmuz Saif |  |  | Completed
ST-112 | Create the approvals app models and migrations; seed the chain-management Permission | Completed | Md. Nazmuz Saif
ST-112 | Build ApprovalChain/ApprovalStep serializers and ViewSets (company-scoped, step order unique) | Completed | Md. Nazmuz Saif
ST-112 | Build the Approval Chains page (create chain, add ordered steps with Role, edit, delete) | Completed | Md. Nazmuz Saif
ST-112 | Self-test chain creation, duplicate step order, and cross-company access | Completed | Md. Nazmuz Saif
ST-112 | TC-24: [Selenium] Create an Approval Chain with three ordered steps — expect the steps saved in order | Completed | Sadia Jahan Disha
ST-112 | TC-25: [Selenium] Add a step with a duplicate order or no Role — expect a validation error | Completed | Sadia Jahan Disha
ST-112 | TC-26: [Selenium] Log in as Company B and open Company A's chain by ID — expect HTTP 404 | Completed | Sadia Jahan Disha
ST-113 | Design ApprovalInstance and ApprovalAction flow (step pointer, approve/reject rules) | Completed | Md. Nazmuz Saif |  |  | Completed
ST-113 | Create ApprovalInstance (generic relation) and ApprovalAction models and migrations | Completed | Md. Nazmuz Saif
ST-113 | Build approve/reject actions: step-Role check, step advance, reject ends request, comment stored, double action blocked | Completed | Md. Nazmuz Saif
ST-113 | Build the pending-approvals list with an approve/reject dialog and comment box | Completed | Md. Nazmuz Saif
ST-113 | Self-test full multi-step approval, a reject, and an unauthorized approver | Completed | Md. Nazmuz Saif
ST-113 | TC-27: [Selenium] Approve as the holder of the current step's Role — expect the request to move to the next step | Completed | Fawjiya Fahima Eifa
ST-113 | TC-28: [Selenium] Reject with a comment — expect the request to end and the comment to be shown in the history | Completed | Fawjiya Fahima Eifa
ST-113 | TC-29: [Selenium] Try to approve without the step's Role, or act on the same step twice — expect the action blocked | Completed | Fawjiya Fahima Eifa
ST-114 | Design the UI component kit (props, colors, empty and loading states) from the design system | Completed | Md. Nazmuz Saif |  |  | Completed
ST-114 | Build StatusPill, MetricCard, EmptyState, and ChartCard components and the /dev/ui-kit showcase page | Completed | Md. Nazmuz Saif
ST-114 | Self-test every component in the showcase page at desktop and mobile widths | Completed | Md. Nazmuz Saif
ST-114 | TC-30: [Selenium] Open /dev/ui-kit — expect Success, Warning, and Failed status pills, each with color and text | Completed | Md. Tahsin Rahman Khan
ST-114 | TC-31: [Selenium] Open /dev/ui-kit — expect a MetricCard with value and delta, and an EmptyState whose action button is clickable | Completed | Md. Tahsin Rahman Khan
ST-115 | Design the grouped sidebar structure, top bar layout, and permission-based menu rules from the design system | Completed | Md. Nazmuz Saif |  |  | Completed
ST-115 | Build the collapsible grouped Sidebar with active-item highlight and permission-based items | Completed | Md. Nazmuz Saif
ST-115 | Build the top bar: page title, search box, company name, notification bell dropdown with empty state, and user menu | Completed | Md. Nazmuz Saif
ST-115 | Add the PlanBadge component (shows the plan name only when the server provides one; nothing hard-coded) | Completed | Md. Nazmuz Saif
ST-115 | Self-test sidebar groups, hidden items for a low-permission user, and the bell dropdown | Completed | Md. Nazmuz Saif
ST-115 | TC-32: Click a sidebar group header — expect its links to expand and collapse | Completed | Sadia Jahan Disha
ST-115 | TC-33: Click a sidebar group header — expect its links to expand and collapse | Completed | Sadia Jahan Disha
ST-115 | TC-34: Click a sidebar group header — expect its links to expand and collapse | Completed | Sadia Jahan Disha
ST-115 | TC-35: Click the notification bell — expect a dropdown with an empty state; click outside — expect it to close | Completed | Sadia Jahan Disha
ST-116 | Design the Task schema (assignee, assigned-by, priority, deadline, status) and the allowed status-transition map | Completed | Montasim Kabir Mahin |  |  | Completed
ST-116 | Create the tasks app Task model and migration; seed the create_task Permission | Completed | Montasim Kabir Mahin
ST-116 | Build TaskSerializer and TaskViewSet (company-scoped, assigned-by set by server, same-company assignee check) | Completed | Montasim Kabir Mahin
ST-116 | Build the submit action with transition validation and an assignee-only check | Completed | Montasim Kabir Mahin
ST-116 | Build the Tasks page (list, create, edit, delete; priority badge, deadline) with a Submit button for the assignee | Completed | Montasim Kabir Mahin
ST-116 | Self-test task CRUD, cross-company assignee, a valid submit, an invalid transition, and a non-assignee submit | Completed | Montasim Kabir Mahin
ST-116 | TC-36: [Selenium] Create a Task with priority and deadline for an Employee — expect it in the Tasks list | Completed | Md. Nazmuz Saif
ST-116 | TC-37: [Selenium] Assign a Task to an Employee of another company — expect the request rejected | Completed | Md. Nazmuz Saif
ST-116 | TC-38: [Selenium] Edit and delete a Task; log in without create_task — expect no create/edit/delete buttons | Completed | Md. Nazmuz Saif
ST-116 | TC-39: [Selenium] As the assignee, submit an In Progress Task — expect the status to become Submitted | Completed | Md. Nazmuz Saif
ST-116 | TC-40: [Selenium] Try a move that is not allowed (Completed to Not Started) — expect a clear error | Completed | Md. Nazmuz Saif
ST-116 | TC-41: [Selenium] As a different Employee, try to submit someone else's Task — expect the request blocked | Completed | Md. Nazmuz Saif
ST-117 | Design DelegationRule schema (delegator, delegate, date range) | Completed | Md. Tahsin Rahman Khan |  |  | Completed
ST-117 | Create DelegationRule model and migration | Completed | Md. Tahsin Rahman Khan
ST-117 | Build DelegationRule serializer and ViewSet with date-range, self-delegation, and same-company validation | Completed | Md. Tahsin Rahman Khan
ST-117 | Build the Delegation page (create, list, delete) | Completed | Md. Tahsin Rahman Khan
ST-117 | Self-test valid delegation, reversed dates, and self-delegation | Completed | Md. Tahsin Rahman Khan
ST-117 | TC-42: [Selenium] Create a delegation with a valid date range — expect it in the list | Completed | Montasim Kabir Mahin
ST-117 | TC-43: [Selenium] Enter an end date before the start date — expect a validation error | Completed | Montasim Kabir Mahin
ST-117 | TC-44: [Selenium] Delegate to yourself — expect the request rejected | Completed | Montasim Kabir Mahin
ST-118 | Design SalaryStructure schema and finance-Permission gating (hierarchy-independent) | Completed | Fawjiya Fahima Eifa |  |  | Incomplete
ST-118 | Create the payroll app SalaryStructure model and migration; seed the finance Permission | Deferred | Fawjiya Fahima Eifa | Marked Incomplete in the Sprint 3 planning sheet (reason not recorded — confirm with owner). | PB-40
ST-118 | Build SalaryStructure serializer and ViewSet gated by the finance Permission (company-scoped) | Deferred | Fawjiya Fahima Eifa | Marked Incomplete in the Sprint 3 planning sheet (reason not recorded — confirm with owner). TC-46 (create and edit a Salary Structure with the finance Permission) failed. | PB-40
ST-118 | Build the Salary Structures page, hidden for users without the Permission | Completed | Fawjiya Fahima Eifa
ST-118 | Self-test access with and without the finance Permission | Deferred | Fawjiya Fahima Eifa | Marked Incomplete in the Sprint 3 planning sheet (reason not recorded — confirm with owner). | PB-40
ST-118 | TC-45: [Selenium] Log in without the finance Permission and open Salary Structures — expect no menu item and HTTP 403 from the API | Completed | Md. Tahsin Rahman Khan
ST-118 | TC-46: [Selenium] Log in with the finance Permission and create and edit a Salary Structure — expect success | Deferred | Md. Tahsin Rahman Khan | TC-46 Failed in the Selenium cross-review (reason not recorded — confirm with owner); re-test needed. | PB-40
ST-118 | TC-47: [Selenium] Log in as a manager above the Accountant in the hierarchy but without the finance Permission — expect salary data still blocked | Completed | Md. Tahsin Rahman Khan
ST-119 | Design the Attendance schema and the one-check-in-per-day rule (company local time) | Completed | Sadia Jahan Disha |  |  | Completed
ST-119 | Create the attendance app Attendance model and migration (unique per employee per day) | Completed | Sadia Jahan Disha
ST-119 | Build check-in and check-out actions with duplicate and out-of-order validation | Completed | Sadia Jahan Disha
ST-119 | Build the Attendance page with Check In / Check Out buttons and today's status | Completed | Sadia Jahan Disha
ST-119 | Self-test check-in, duplicate check-in, and check-out before check-in | Completed | Sadia Jahan Disha
ST-119 | TC-48: [Selenium] Click Check In — expect today's status to show the check-in time | Completed | Fawjiya Fahima Eifa
ST-119 | TC-49: [Selenium] Click Check In a second time on the same day — expect a clear error message | Completed | Fawjiya Fahima Eifa
ST-119 | TC-50: [Selenium] Log in as a new Employee and click Check Out before Check In — expect the request blocked | Completed | Fawjiya Fahima Eifa

## New Backlog
New Backlog Stories for Incomplete Tasks
At retrospective time, New Backlog Status is limited to To Do or Ready. In Progress begins only after a story is selected during Sprint Planning.
New Backlog Story No. | Source Sprint Story No. | Incomplete Task | Owner | Reason / Context | Priority | Backlog Status | Notes / Acceptance Criteria
PB-40 | ST-118 | Database: Create the payroll app SalaryStructure model and migration; seed the finance Permission (1h) Backend: Build SalaryStructure serializer and ViewSet gated by the finance Permission, company-scoped (2h) Self-Test: access with and without the finance Permission (1h) QA: TC-46 [Selenium] log in with the finance Permission and create and edit a Salary Structure — re-test after the fix (1.5h) | Fawjiya Fahima Eifa | 3 of 5 ST-118 tasks (4 hrs) were marked Incomplete in Sprint 3, and TC-46 (1.5 hrs) failed; Design and Frontend were completed, and TC-45 and TC-47 passed. Reason not recorded — confirm with owner before re-planning. | High | To Do | Carry-over of PB-18 (ST-118). Acceptance criteria: - A Salary Structure (base salary and allowances) can be defined per Employee - Salary Structure endpoints require the finance Permission - Access does not depend on the reporting hierarchy - Salary UI is hidden for users without the Permission - TC-46 passes on re-test

## Retrospective
Sprint Retrospective Discussion & Actions
A. What Went Well
No. | Observation / Feedback | Impact | Action / Follow-up | Owner | Target / Notes
1 | 8 of 9 stories (38 of 41 pts) were delivered, and every one of their test cases Passed. The 4 Sprint 2 ST-110 carry-over tasks (11 hrs) were closed inside ST-111, so permission enforcement and tenant-safe company resolution — the open part of the Sprint 2 RBAC goal — are now delivered. | High | Use ST-111 as the pattern for carry-overs: re-plan the unfinished work inside a new story that has its own test cases. | Md. Nazmuz Saif | Apply to the ST-118 carry-over in Sprint 4.
2 | Every story was tested by a member who did not write it (cross-test assignment), and all 32 Selenium test cases (TC-19 to TC-50) have a result: 31 Passed, 1 Failed. In Sprint 2, 5 of 8 test cases were still 'to do' at sprint end. | High | Keep the cross-test rotation and finish all test cases inside the sprint in Sprint 4. | Montasim Kabir Mahin | Sprint 4.
3 | The Approval Chain (ST-112) and approve/reject engine (ST-113) were delivered with all 6 test cases (TC-24 to TC-29) Passed, including ordered steps, cross-company 404, comment on every action, and a blocked double action. | High | Reuse the approval engine for leave requests (PB-29, PB-30) instead of building a separate flow. | Md. Nazmuz Saif | Sprint 5 (PB-30).
4 | Guard rules were enforced and tested across the stories: self-manager and reports_to cycle block (TC-22), cross-company access (TC-26, TC-37), invalid task status change (TC-40), non-assignee submit (TC-41), reversed dates and self-delegation (TC-43, TC-44), duplicate check-in and early check-out (TC-49, TC-50). | High | Keep a negative-path test case for every story's validation rule, as done in Sprint 3. | Md. Tahsin Rahman Khan | Ongoing.
5 | Story ownership kept rotating: Md. Tahsin Rahman Khan owned his first full story (ST-117, all 5 tasks Completed), and Montasim Kabir Mahin, Sadia Jahan Disha and Fawjiya Fahima Eifa each owned a story from Design to Self-Test. | High | Keep the one-owner-per-story rotation and give lighter-scope stories to members still building experience; Md. Nazmuz Saif stays as fallback. | Montasim Kabir Mahin | Ongoing from Sprint 4.
6 | The shared UI kit (StatusPill, MetricCard, EmptyState, ChartCard, with the /dev/ui-kit showcase) and the app shell (grouped sidebar, top bar, notification bell, PlanBadge) were delivered, and menu items already hide by Permission. | Medium | Build the Sprint 4 screens (role dashboards PB-22, Kanban board PB-25) on these components instead of creating new ones. | Md. Nazmuz Saif | Apply from Sprint 4.
7 | The Sprint 2 rule 'a story is Completed only after its test cases pass' held: all 8 Completed stories have every test case Passed, and ST-118 stays open. | Medium | Keep the rule: a story is Completed only when its tasks are done and its test cases have passed. | Montasim Kabir Mahin | Ongoing.
B. What Didn't Go Well
No. | Observation / Feedback | Impact | Action / Follow-up | Owner | Target / Notes
1 | ST-118 (salary structure restricted by the finance Permission, 3 pts) was not delivered: Database, Backend and Self-Test (4 hrs) are marked Incomplete and TC-46 (create and edit a Salary Structure with the finance Permission) failed. Only the blocking tests (TC-45, TC-47) passed. The Sprint 3 goal item 'salary-data restriction' is therefore open. | High | Carried to the backlog as PB-40. Confirm with the owner why the three tasks stopped, then re-plan it at Sprint 4 planning and re-run TC-46. | Fawjiya Fahima Eifa | Re-plan at Sprint 4 planning.
2 | Work was concentrated on one person: Md. Nazmuz Saif owned 5 of 9 stories (24 of 41 pts, 66 of 104 task hours) and also took the 11 hrs of ST-110 carry-over. | Medium | Spread Sprint 4 story ownership more evenly (PB-21 to PB-24 are all listed under Md. Nazmuz Saif) and keep him as fallback. | Montasim Kabir Mahin | Sprint 4 planning.
3 | ST-115 test cases are weak: TC-32, TC-33 and TC-34 have identical text (expand/collapse a sidebar group) and TC-32 to TC-35 lack the [Selenium] tag. No test case covers the permission-hidden menu item, active-item highlight, top bar or PlanBadge criteria. | Medium | Rewrite TC-32 to TC-34 so each covers a different ST-115 criterion, add the [Selenium] tag, and re-run them. | Sadia Jahan Disha | Start of Sprint 4.
4 | The Sprint 3 sheet shows no result for Sprint 2's pending test cases TC-14 to TC-18, which the Sprint 2 retro asked to run at the start of Sprint 3. | Medium | Confirm whether TC-14 to TC-18 were run and record their results. | Md. Tahsin Rahman Khan | Start of Sprint 4.
5 | The reason ST-110 paused in Sprint 2 is still not recorded; its 4 tasks moved from Fawjiya Fahima Eifa to Md. Nazmuz Saif in Sprint 3 without a note on why. | Medium | Ask the owner why ST-110 stopped and record it, so the same stall is not repeated on ST-118. | Montasim Kabir Mahin | Before Sprint 4 planning.
C. What Can Be Improved
No. | Observation / Feedback | Impact | Action / Follow-up | Owner | Target / Notes
1 | Sprint 3 was planned at 41 pts in 8 days (Sep 30 – Oct 7); Sprint 1 was 21 pts in 9 days and Sprint 2 was 18 pts in 14 days. 38 pts were delivered, and the Sprint 4 backlog already holds 44 pts plus the ST-118 carry-over. | High | At Sprint 4 planning, size the sprint against delivered points (38) and the real sprint length, not the whole Sprint 4 backlog; move lower-priority stories to Sprint 5. | Montasim Kabir Mahin | Sprint 4 planning.
2 | The planning sheet still uses Done, Incomplete, 'Done (in ST-111)' and Passed/Failed instead of the standard list values, and the three Incomplete ST-118 tasks have no reason recorded. 'Pause' is no longer used. | Medium | Use only the standard list values (Not Started, In Progress, Blocked, Completed, Deferred) and record a reason whenever a task is not completed. | Montasim Kabir Mahin | Effective Sprint 4.
3 | ST-118's Frontend task was marked Completed while its Database and Backend tasks were not, so a Salary Structures page exists without its backend finished. | Medium | Do story tasks in order (Design → Database → Backend → Frontend → Self-Test) and mark a Frontend task Completed only after the API it calls works. | Fawjiya Fahima Eifa | Apply at ST-118 re-planning.
4 | The planning sheet's Task Breakdown does not list the QA test cases as tasks, so they had to be added to this retro sheet from the Overall Testing table. | Medium | List each story's test cases as tasks in the sprint planning breakdown, so story progress and QA progress are tracked together. | Montasim Kabir Mahin | Sprint 4 planning.
5 | PB-26 was given to the ST-110 carry-over in the Sprint 2 retro, but the Product Backlog now uses PB-26 for a different story (daily progress log); the carry-over was delivered as PB-11 (ST-111). | Low | Check the next free PB number in the Product Backlog before creating a carry-over story (PB-40 is used for the ST-118 carry-over). | Montasim Kabir Mahin | Sprint 4 planning.

## Lists
Task Status | New Backlog Status | Priority | Impact
Not Started | To Do | High | High
In Progress | Ready | Medium | Medium
Blocked |  | Low | Low
Completed
Deferred