## Sprint Retro
Ordinis — Sprint 4 Retrospective
Sprint Details |  |  | Sprint Summary
Sprint Name / No. | Sprint 4 |  | Total Stories | 9
Sprint Start Date | 07-Oct-2026 |  | Completed Stories | 9
Sprint End Date | 14-Oct-2026 |  | Incomplete Stories | 0
|  |  | New Backlog Stories Created | 0
|  |  | Completion % | 100%
Story Status / Task Tracking
Story No. | Task | Task Status | Task Owner | Reason for Not Completing Task | New Backlog Story No. | Story Result
ST-120 | Create the payroll app SalaryStructure model and migration; seed the finance Permission | Completed | Md. Nazmuz Saif |  |  | Completed
ST-120 | Build SalaryStructure serializer and ViewSet gated by the finance Permission (no hierarchy rule, one structure per Employee) | Completed | Md. Nazmuz Saif
ST-120 | Fix the Salary Structures page: Edit and Delete work, statuses show correctly, UI kit components are used, page is hidden without the Permission | Completed | Md. Nazmuz Saif
ST-120 | Self-test create, edit, delete, access with and without the finance Permission, and the manager-above-Accountant case | Completed | Md. Nazmuz Saif
ST-120 | Selenium cross-review QA: TC-51 to TC-52 (2 test cases, all Passed) | Completed | Md. Tahsin Rahman Khan
ST-121 | Design the pagination format and what changes in the frontend lists | Completed | Md. Nazmuz Saif |  |  | Completed
ST-121 | Wire pagination into every list endpoint and keep the standard response format | Completed | Md. Nazmuz Saif
ST-121 | Write requirements.txt, .env.example, and the README (install, migrate, run, test) | Completed | Md. Nazmuz Saif
ST-121 | Update every frontend list service and page to read paged results and add page controls | Completed | Md. Nazmuz Saif
ST-121 | Self-test a long list on two pages and a clean install from the README | Completed | Md. Nazmuz Saif
ST-121 | Selenium cross-review QA: TC-53 (1 test case, all Passed) | Completed | Md. Tahsin Rahman Khan
ST-122 | Design the five Role dashboards (which MetricCards and charts, which Permission each needs) | Completed | Md. Nazmuz Saif |  |  | Completed
ST-122 | Build the dashboard summary endpoint(s) that return only what the user's Permissions allow | Completed | Md. Nazmuz Saif
ST-122 | Build the CEO, Manager, HR, Accountant, and Employee dashboards with MetricCards and charts (violet palette) | Completed | Md. Nazmuz Saif
ST-122 | Land on the dashboard after login and turn the Dashboard menu item into a link | Completed | Md. Nazmuz Saif
ST-122 | Self-test each dashboard, a user without the Permission, loading and empty states, desktop and mobile | Completed | Md. Nazmuz Saif
ST-122 | Selenium cross-review QA: TC-54 to TC-56 (3 test cases, all Passed) | Completed | Md. Tahsin Rahman Khan
ST-123 | Design the Break-Glass flow (request, approve or deny, expiry, log) and the Platform Admin account | Completed | Md. Nazmuz Saif |  |  | Completed
ST-123 | Create SupportAccessRequest and ImpersonationLog models and migrations; mark Platform Admin accounts | Completed | Md. Nazmuz Saif
ST-123 | Build request, approve, deny, automatic expiry, gated company-data access, and the access log | Completed | Md. Nazmuz Saif
ST-123 | Build the CEO screen to review requests and read the Impersonation Log | Completed | Md. Nazmuz Saif
ST-123 | Self-test approve, deny, expiry, access without an approved request, and the log entries | Completed | Md. Nazmuz Saif
ST-123 | Selenium cross-review QA: TC-57 to TC-58 (2 test cases, all Passed) | Completed | Md. Tahsin Rahman Khan
ST-124 | Design the admin panel pages and the rule that no client data is shown | Completed | Md. Nazmuz Saif |  |  | Completed
ST-124 | Build the Platform Admin endpoints (companies, suspend and activate, support tickets, requests), allowed only for Platform Admins | Completed | Md. Nazmuz Saif
ST-124 | Build the admin panel pages with menu item shown only to Platform Admins | Completed | Md. Nazmuz Saif
ST-124 | Self-test suspend and activate, a CEO opening the panel, and that no client data shows | Completed | Md. Nazmuz Saif
ST-124 | Selenium cross-review QA: TC-59 to TC-60 (2 test cases, all Passed) | Completed | Md. Tahsin Rahman Khan
ST-125 | Design the Kanban columns and status mapping and the TaskProgressLog schema | Completed | Montasim Kabir Mahin |  |  | Completed
ST-125 | Create the TaskProgressLog model and migration | Completed | Montasim Kabir Mahin
ST-125 | Build the progress log endpoints (assignee only) and the Kanban data with allowed moves | Completed | Montasim Kabir Mahin
ST-125 | Build the Kanban board and the progress timeline on the Task | Completed | Montasim Kabir Mahin
ST-125 | Self-test card moves, an invalid move, adding progress as the assignee and as someone else | Completed | Montasim Kabir Mahin
ST-125 | Selenium cross-review QA: TC-61 to TC-63 (3 test cases, all Passed) | Completed | Md. Nazmuz Saif
ST-126 | Design the Notification schema and the Action Inbox sources | Completed | Md. Tahsin Rahman Khan |  |  | Completed
ST-126 | Create the Notification model and migration | Completed | Md. Tahsin Rahman Khan
ST-126 | Build notification creation (Task assigned, approval reached), mark-read, and the inbox aggregation | Completed | Md. Tahsin Rahman Khan
ST-126 | Build the Action Inbox page and connect the notification bell | Completed | Md. Tahsin Rahman Khan
ST-126 | Self-test each inbox source, mark read, and that nobody else's items appear | Completed | Md. Tahsin Rahman Khan
ST-126 | Selenium cross-review QA: TC-64 to TC-65 (2 test cases, all Passed) | Completed | Montasim Kabir Mahin
ST-127 | Design the Payslip schema, the calculation, and the one-per-month rule | Completed | Sadia Jahan Disha |  |  | Completed
ST-127 | Create the Payslip model and migration with a unique Employee and month | Completed | Sadia Jahan Disha
ST-127 | Build generate_payslip with duplicate prevention and the finance Permission check | Completed | Sadia Jahan Disha
ST-127 | Build the Payslip generate and view pages | Completed | Sadia Jahan Disha
ST-127 | Self-test generate, duplicate, no Salary Structure, and own-Payslip-only access | Completed | Sadia Jahan Disha
ST-127 | Selenium cross-review QA: TC-66 to TC-67 (2 test cases, all Passed) | Completed | Fawjiya Fahima Eifa
ST-128 | Design the LeaveType and LeaveRequest schema and the balance calculation | Completed | Fawjiya Fahima Eifa |  |  | Completed
ST-128 | Create the LeaveType and LeaveRequest models and migrations | Completed | Fawjiya Fahima Eifa
ST-128 | Build apply_leave with balance validation and date checks | Completed | Fawjiya Fahima Eifa
ST-128 | Build the leave application page and the My Leave list | Completed | Fawjiya Fahima Eifa
ST-128 | Self-test an in-balance request, an over-balance request, and reversed dates | Completed | Fawjiya Fahima Eifa
ST-128 | Selenium cross-review QA: TC-68 to TC-70 (3 test cases, all Passed) | Completed | Sadia Jahan Disha

## New Backlog
New Backlog Stories for Incomplete Tasks
At retrospective time, New Backlog Status is limited to To Do or Ready. In Progress begins only after a story is selected during Sprint Planning.
New Backlog Story No. | Source Sprint Story No. | Incomplete Task | Owner | Reason / Context | Priority | Backlog Status | Notes / Acceptance Criteria
No new backlog stories — all Sprint 4 tasks were completed.

## Retrospective
Sprint Retrospective Discussion & Actions
A. What Went Well
No. | Observation / Feedback | Impact | Action / Follow-up | Owner | Target / Notes
1 | All 9 stories (47 pts) and all 43 tasks were Completed — the largest sprint so far (Sprint 3 had 41 pts and 1 story left incomplete). Completion is 100% with no new backlog stories created. | High | Use Sprint 4 (47 pts) as the capacity reference when sizing Sprint 5 (40 pts currently planned). | Montasim Kabir Mahin | Check at Sprint 5 planning.
2 | The Sprint 3 carry-over was closed: ST-120 finished the Salary Structure work (PB-18 / PB-40). TC-46, which Failed in Sprint 3, was re-run as TC-51 and Passed; TC-52 added for Delete. | High | Keep the practice: a failed test case is re-run under a new TC number that names the original, so nothing is lost between sprints. | Md. Tahsin Rahman Khan | Continue in Sprint 5.
3 | Selenium cross-review QA worked: all 20 test cases (TC-51 to TC-70) Passed with no failures, and every story was tested by a member who did not write its code. | High | Keep the cross-test assignment table for every Sprint 5 story. | Montasim Kabir Mahin | Set at Sprint 5 planning.
4 | The four members besides the lead delivered a full story each (Design to Self-Test): ST-125 (Mahin), ST-126 (Tahsin), ST-127 (Disha), ST-128 (Fawjiya) — 20 of 20 tasks Completed, including Fawjiya, whose ST-110 and ST-118 had stalled earlier. | High | Keep full-story ownership for these members in Sprint 5, with Md. Nazmuz Saif as fallback. | Montasim Kabir Mahin | Ongoing.
5
6
7
8
B. What Didn't Go Well
No. | Observation / Feedback | Impact | Action / Follow-up | Owner | Target / Notes
1 | Development work is concentrated on Md. Nazmuz Saif: 5 of 9 stories (ST-120 to ST-124), 24 of 47 pts, 23 of 43 tasks and 57 of 104 estimated hours (about 55%). He also acted as Selenium tester for ST-125. | High | Sprint 5 currently gives him PB-30 to PB-34 (21 of 40 pts). At planning, move at least one story (for example PB-32 test suite or PB-33 documents) to another member. | Montasim Kabir Mahin | Decide at Sprint 5 planning.
2 | QA is concentrated on one person: Md. Tahsin Rahman Khan ran 10 of 20 test cases (15 of 30 QA hours), covering all five of Saif's stories, while also building ST-126 (11 hours). | Medium | Split testing of the lead developer's Sprint 5 stories across at least two testers. | Montasim Kabir Mahin | Set in the Sprint 5 cross-test table.
3 | Selenium coverage has gaps: no case for the Manager and HR dashboards (ST-122 tested CEO, Employee, Accountant only), automatic Break-Glass expiry (ST-123), an invalid Kanban move (ST-125), or Payslip own-only access and the no-Salary-Structure message (ST-127). ST-121 has one case. | Medium | Add these cases to the Selenium regression suite (PB-32) so they are covered before the final demo. | Md. Tahsin Rahman Khan | Within PB-32, Sprint 5.
4
5
6
7
8
C. What Can Be Improved
No. | Observation / Feedback | Impact | Action / Follow-up | Owner | Target / Notes
1 | Sprint 5 is the last sprint: 10 stories (40 pts) are all To Do, there is no later sprint to carry work into, and a demo rehearsal with a bug-fix buffer (PB-34) is included. | High | Split the stories into demo-critical (High: PB-30, 31, 32, 34, 36, 37) and nice-to-have (Medium: PB-33, 35, 38, 39); build the High ones first. | Montasim Kabir Mahin | Agree at Sprint 5 planning.
2 | Backlog and sheet hygiene: PB-18 still shows Incomplete although its work was finished under PB-40; the Sprint 3 sheet has TC-32, TC-33 and TC-34 as the same test case three times; Sprint 4 began on Oct 7, the day Sprint 3 ended. | Medium | Set PB-18 to Done (completed via PB-40), remove the duplicate test cases, and start Sprint 5 on a day that does not overlap Sprint 4. | Montasim Kabir Mahin | Before Sprint 5 planning.
3 | The planning sheets record only estimated hours, so there is no way to tell whether the 104 estimated implementation hours in Sprint 4 were realistic. | Medium | Add an Actual (hrs) column to the Sprint 5 task breakdown and compare it with the estimate at the retrospective. | Montasim Kabir Mahin | Effective Sprint 5.
4
5
6
7
8

## Lists
Task Status | New Backlog Status | Priority | Impact
Not Started | To Do | High | High
In Progress | Ready | Medium | Medium
Blocked |  | Low | Low
Completed
Deferred