## Sprint Retro
Ordinis — Sprint 1 Retrospective
Sprint Details |  |  | Sprint Summary
Sprint Name / No. | Sprint 1 |  | Total Stories | 6
Sprint Start Date | 01-Sep-2026 |  | Completed Stories | 6
Sprint End Date | 09-Sep-2026 |  | Incomplete Stories | 0
|  |  | New Backlog Stories Created | 0
|  |  | Completion % | 100%
Story Status / Task Tracking
Story No. | Task | Task Status | Task Owner | Reason for Not Completing Task | New Backlog Story No. | Story Result
ST-101 | Design Company + CompanySettings + CEO Designation data model and registration sequence | Completed | Md. Nazmuz Saif |  |  | Completed
ST-101 | Create and verify migrations for Company, CompanySettings, Designation, User, Employee | Completed | Md. Nazmuz Saif
ST-101 | Build atomic CompanyRegisterSerializer (transaction-wrapped) + CompanyRegisterView | Completed | Md. Nazmuz Saif
ST-101 | Build Company Registration page (form, validation, API call) | Completed | Md. Nazmuz Saif
ST-101 | Self-test registration with valid data and with a missing required field | Completed | Md. Nazmuz Saif
ST-102 | Design JWT token structure (claims: email, company_id) and refresh flow | Completed | Md. Nazmuz Saif |  |  | Completed
ST-102 | Configure djangorestframework-simplejwt; build CustomTokenObtainPairSerializer; wire login/refresh endpoints | Completed | Md. Nazmuz Saif
ST-102 | Build Login page (form, error display, token storage) | Completed | Md. Nazmuz Saif
ST-102 | Self-test login with valid and invalid credentials | Completed | Md. Nazmuz Saif
ST-103 | Add is_active check to Company model and login serializer; build IsCompanyActive permission class | Completed | Md. Nazmuz Saif |  |  | Completed
ST-103 | Self-test login attempt from a suspended-company account | Completed | Md. Nazmuz Saif
ST-104 | Design Department schema (company-scoped) | Completed | Md. Nazmuz Saif |  |  | Completed
ST-104 | Create Department model and migration | Completed | Md. Nazmuz Saif
ST-104 | Build DepartmentSerializer + DepartmentViewSet (company-filtered queryset) | Completed | Md. Nazmuz Saif
ST-104 | Build Departments page (list, create, edit, delete) | Completed | Md. Nazmuz Saif
ST-104 | Self-test Department CRUD and cross-tenant isolation | Completed | Md. Nazmuz Saif
ST-105 | Design Designation schema (company-scoped, label-only) | Completed | Md. Nazmuz Saif |  |  | Completed
ST-105 | Create Designation model and migration | Completed | Md. Nazmuz Saif
ST-105 | Build DesignationSerializer + DesignationViewSet | Completed | Md. Nazmuz Saif
ST-105 | Build Designations page (list, create, edit, delete) | Completed | Md. Nazmuz Saif
ST-105 | Self-test Designation CRUD, scoped to own company | Completed | Md. Nazmuz Saif
ST-106 | Design self-referencing Employee hierarchy (reports_to) and circular-reference rule | Completed | Md. Nazmuz Saif |  |  | Completed
ST-106 | Create Employee model and migration with self-referencing reports_to FK | Completed | Md. Nazmuz Saif
ST-106 | Build EmployeeSerializer + EmployeeViewSet; add circular-reference guard on reports_to | Completed | Md. Nazmuz Saif
ST-106 | Build Employees page (list, create, edit — manager/reports-to dropdown) | Completed | Md. Nazmuz Saif
ST-106 | Self-test hierarchy assignment across levels and the circular-reference block | Completed | Md. Nazmuz Saif

## New Backlog
New Backlog Stories for Incomplete Tasks
At retrospective time, New Backlog Status is limited to To Do or Ready. In Progress begins only after a story is selected during Sprint Planning.
New Backlog Story No. | Source Sprint Story No. | Incomplete Task | Owner | Reason / Context | Priority | Backlog Status | Notes / Acceptance Criteria

## Retrospective
Sprint Retrospective Discussion & Actions
A. What Went Well
No. | Observation / Feedback | Impact | Action / Follow-up | Owner | Target / Notes
1 | All 6 Sprint 1 stories (company onboarding, auth, Department/Designation/Employee with hierarchy) were completed end-to-end by one owner, keeping the work consistent and easy to track. | High | Keep the one-owner-per-story pattern going forward — it kept Sprint 1 simple to build and verify. | Md. Nazmuz Saif | Confirmed for Sprint 2 onward.
2 | Atomic company self-registration (Company + Settings + Designation + User + Employee) worked correctly on the first verified end-to-end test. | High | Keep using @transaction.atomic for every multi-model creation flow in future sprints. | Md. Nazmuz Saif | Apply from Sprint 2 onward.
3 | Multi-tenant isolation (company-filtered queryset) was correct from the very first app built (Department/Employee). | High | Keep applying the same get_queryset() company-filter pattern to every new app without exception. | Md. Nazmuz Saif | Ongoing standard for all future apps.
4
5
6
7
8
B. What Didn't Go Well
No. | Observation / Feedback | Impact | Action / Follow-up | Owner | Target / Notes
1 | All 6 stories were coded by one person this sprint — the rest of the team did not get hands-on coding practice yet. | Medium | Starting Sprint 2, rotate story ownership so each team member codes their own story end-to-end. | Montasim Kabir Mahin | Effective Sprint 2.
2 | Self-referencing hierarchy (reports_to) needed a second pass to correctly block circular references. | Medium | Think through edge cases (self-reference, cycles) at design time, before first implementation. | Md. Nazmuz Saif | Apply during design step of future sprints.
3
4
5
6
7
8
C. What Can Be Improved
No. | Observation / Feedback | Impact | Action / Follow-up | Owner | Target / Notes
1 | From Sprint 2, each story needs to be assigned to one clear owner (Design through Frontend) so coding responsibility never overlaps between two people on the same story. | High | Assign one full-story owner per story at sprint planning, in a fixed rotation order across the team. | Montasim Kabir Mahin | Applied starting Sprint 2 planning.
2 | Members newer to coding (System Designer, System Analyst, QA) will need lighter-scope stories at first. | Medium | Scope their stories smaller (fewer sub-tasks / lower hours); Md. Nazmuz Saif backs up as a fallback if a task can't be finished. | Montasim Kabir Mahin | Applied starting Sprint 2.
3
4
5
6
7
8

## Lists
Task Status | New Backlog Status | Priority | Impact
Not Started | To Do | High | High
In Progress | Ready | Medium | Medium
Blocked |  | Low | Low
Completed
Deferred