## Team
Ordinis — Project Team
SL | Student ID | Student Name | Role
1 | 23201023 | Md. Nazmuz Saif | Software Developer (Programmer)
2 | 23201008 | Fawjiya Fahima Eifa | System Designer / Software Architect
3 | 23201055 | Montasim Kabir Mahin | Project Manager
4 | 23201029 | Sadia Jahan Disha | System Analyst / Business Analyst
5 | 23201050 | Md. Tahsin Rahman Khan | Tester / Quality Assurance (QA) Engineer
Each sprint's stories are assigned one full story (Design → Database → Backend → Frontend → Self-Test) per person, in order: Md. Nazmuz Saif → Montasim Kabir Mahin → Sadia Jahan Disha → Fawjiya Fahima Eifa → Md. Tahsin Rahman Khan. Overall QA testing at the end of each sprint is always run by Md. Tahsin Rahman Khan.

## Product Backlog
Ordinis — Product Backlog
Organization Operating System (OrgOS) — Multi-Tenant SaaS Platform
Backlog ID | Epic / Module | User Story | Priority | Story Points | Status | Sprint Assigned | Owner
PB-01 | Authentication & Onboarding | As a Company Owner, I want to self-register my company and create my CEO account in one step, so that I can start using Ordinis without manual setup by an admin. | High | 5 | Done | Sprint 1 | Md. Nazmuz Saif
PB-02 | Authentication & Onboarding | As a User, I want to log in with my email and password, so that I can securely access my company's Ordinis dashboard. | High | 3 | Done | Sprint 1 | Md. Nazmuz Saif
PB-03 | Authentication & Onboarding | As a User, I want my login blocked if my company's subscription is suspended, so that access matches billing status. | Medium | 2 | Done | Sprint 1 | Md. Nazmuz Saif
PB-04 | Organization Management | As a CEO, I want to create and manage Departments for my company, so that I can structure my organization the way I need. | High | 3 | Done | Sprint 1 | Md. Nazmuz Saif
PB-05 | Organization Management | As a CEO, I want to create and manage Designations (job titles), so that employees can be labeled correctly without affecting their access rights. | High | 3 | Done | Sprint 1 | Md. Nazmuz Saif
PB-06 | Organization Management | As a CEO, I want to add Employees and assign each one a manager (reports-to), so that my real reporting hierarchy is reflected in the system. | High | 5 | Done | Sprint 1 | Md. Nazmuz Saif
PB-07 | Organization Management | As a Department Head, I want the system to resolve my full list of subordinates automatically, so that I can see my whole team regardless of hierarchy depth. | Medium | 5 | Done | Sprint 2 | Md. Nazmuz Saif
PB-08 | RBAC (Roles & Permissions) | As a CEO, I want to create custom Roles as bundles of Permissions, so that access rights are independent of job titles. | High | 5 | To Do | Sprint 2 | Montasim Kabir Mahin
PB-09 | RBAC (Roles & Permissions) | As a CEO, I want to assign one or more Roles to any Employee, so that I can grant exactly the access that person needs. | High | 3 | To Do | Sprint 2 | Sadia Jahan Disha
PB-10 | RBAC (Roles & Permissions) | As the System, I want every protected action to check a specific Permission codename, so that access control never depends on a hardcoded job-title check. | High | 5 | To Do | Sprint 2 | Fawjiya Fahima Eifa
PB-11 | RBAC (Roles & Permissions) | As an Accountant, I want salary and financial data restricted to users with finance permission only, so that confidential pay data stays private regardless of hierarchy. | High | 3 | To Do | Sprint 3
PB-12 | Approval Workflow | As a CEO, I want to define a multi-step Approval Chain for leave requests, so that my company's actual approval process is enforced by the system. | Medium | 5 | To Do | Sprint 3
PB-13 | Approval Workflow | As an Approver, I want to approve or reject a pending request with a comment, so that decisions and reasons are recorded. | Medium | 3 | To Do | Sprint 3
PB-14 | Approval Workflow | As a Department Head, I want to delegate my approval authority to someone else for a date range, so that requests are not stuck when I'm on leave. | Medium | 3 | To Do | Sprint 3
PB-15 | Task Management | As a Department Head, I want to create Tasks and assign them to Employees with a priority and deadline, so that work is tracked centrally. | High | 5 | To Do | Sprint 3
PB-16 | Task Management | As an Employee, I want to submit a Task only through valid status changes, so that progress reporting stays accurate and consistent. | High | 3 | To Do | Sprint 3
PB-17 | Task Management | As an Employee, I want to log daily progress on a multi-day task, so that my manager can see progress without me uploading code or files. | Medium | 3 | To Do | Sprint 4
PB-18 | Attendance & Leave | As an Employee, I want to check in and check out once per day, so that my attendance is recorded accurately. | High | 3 | To Do | Sprint 4
PB-19 | Attendance & Leave | As an Employee, I want to apply for leave and have my balance validated automatically, so that I can't accidentally over-request leave. | High | 5 | To Do | Sprint 4
PB-20 | Attendance & Leave | As an Approver, I want to approve or reject a pending leave request, so that leave decisions are recorded in the system. | High | 3 | To Do | Sprint 4
PB-21 | Payroll | As an Accountant, I want to define a Salary Structure per employee, so that payslips can be generated automatically. | High | 3 | To Do | Sprint 5
PB-22 | Payroll | As an Accountant, I want to generate a Payslip for a given month without creating duplicates, so that payroll runs stay accurate. | High | 5 | To Do | Sprint 5
PB-23 | Notifications | As a User, I want a personalized Action Inbox combining my pending tasks, approvals, and notifications, so that I know what needs my attention in one place. | Medium | 5 | To Do | Sprint 5
PB-24 | Audit & Analytics | As a CEO, I want every sensitive action logged in an append-only Audit Log, so that I have a tamper-proof history of what happened. | High | 5 | To Do | Sprint 6
PB-25 | Billing & Platform Admin | As the Platform Owner, I want a Break-Glass access process for support, so that I can help a client without having default access to their data. | Medium | 5 | To Do | Sprint 6

## Sprint 1
Ordinis — Sprint 1 Planning
Sprint Duration: Sep 1 – Sep 9
Sprint Goal: Stand up Company onboarding, authentication, and the core Organization structure (Department, Designation, Employee with hierarchy) so a company can self-register and build its org chart.
Selected Stories for this Sprint
Story ID | User Story | Owner | Story Points | Acceptance Criteria
ST-101 | As a Company Owner, I want to self-register my company and create my CEO account in one step, so that I can start using Ordinis without manual setup by an admin. | Md. Nazmuz Saif | 5 | - Registration form creates Company, CompanySettings, CEO Designation, User, and Employee in one atomic transaction - A valid JWT is returned immediately - Registration fails cleanly (no partial records) if any step fails
ST-102 | As a User, I want to log in with my email and password, so that I can securely access my company's Ordinis dashboard. | Md. Nazmuz Saif | 3 | - Valid credentials return an access token and a refresh token - Invalid credentials return a generic error (no enumeration) - Access token works on a protected endpoint; refresh token issues a new access token
ST-103 | As a User, I want my login blocked if my company's subscription is suspended, so that access matches billing status. | Md. Nazmuz Saif | 2 | - Login from a suspended company returns a specific error and no token - An already-issued token from a since-suspended company is rejected on the next call
ST-104 | As a CEO, I want to create and manage Departments for my company, so that I can structure my organization the way I need. | Md. Nazmuz Saif | 3 | - CRUD works for Departments, scoped strictly to the CEO's own company - Accessing another company's Department by ID returns 404
ST-105 | As a CEO, I want to create and manage Designations (job titles), so that employees can be labeled correctly without affecting their access rights. | Md. Nazmuz Saif | 3 | - CRUD works for Designations, scoped to the CEO's own company - Creating/removing a Designation has no effect on any Employee's permissions
ST-106 | As a CEO, I want to add Employees and assign each one a manager (reports-to), so that my real reporting hierarchy is reflected in the system. | Md. Nazmuz Saif | 5 | - Employee can be created with Department, Designation, and reports_to - Hierarchy supports any depth without code changes - An Employee cannot be set as their own manager
Task Breakdown — one owner does the full story (Design → Database → Backend → Frontend → Self-Test)
Story ID | Category | Task | Owner | Estimate (hrs) | Status
ST-101 | Design | Design Company + CompanySettings + CEO Designation data model and registration sequence | Md. Nazmuz Saif | 3 | Done
ST-101 | Database | Create and verify migrations for Company, CompanySettings, Designation, User, Employee | Md. Nazmuz Saif | 2 | Done
ST-101 | Backend | Build atomic CompanyRegisterSerializer (transaction-wrapped) + CompanyRegisterView | Md. Nazmuz Saif | 4 | Done
ST-101 | Frontend | Build Company Registration page (form, validation, API call) | Md. Nazmuz Saif | 3 | Done
ST-101 | Self-Test | Self-test registration with valid data and with a missing required field | Md. Nazmuz Saif | 1 | Done
ST-102 | Design | Design JWT token structure (claims: email, company_id) and refresh flow | Md. Nazmuz Saif | 2 | Done
ST-102 | Backend | Configure djangorestframework-simplejwt; build CustomTokenObtainPairSerializer; wire login/refresh endpoints | Md. Nazmuz Saif | 3 | Done
ST-102 | Frontend | Build Login page (form, error display, token storage) | Md. Nazmuz Saif | 3 | Done
ST-102 | Self-Test | Self-test login with valid and invalid credentials | Md. Nazmuz Saif | 1 | Done
ST-103 | Backend | Add is_active check to Company model and login serializer; build IsCompanyActive permission class | Md. Nazmuz Saif | 3 | Done
ST-103 | Self-Test | Self-test login attempt from a suspended-company account | Md. Nazmuz Saif | 1 | Done
ST-104 | Design | Design Department schema (company-scoped) | Md. Nazmuz Saif | 1 | Done
ST-104 | Database | Create Department model and migration | Md. Nazmuz Saif | 1 | Done
ST-104 | Backend | Build DepartmentSerializer + DepartmentViewSet (company-filtered queryset) | Md. Nazmuz Saif | 2 | Done
ST-104 | Frontend | Build Departments page (list, create, edit, delete) | Md. Nazmuz Saif | 3 | Done
ST-104 | Self-Test | Self-test Department CRUD and cross-tenant isolation | Md. Nazmuz Saif | 1 | Done
ST-105 | Design | Design Designation schema (company-scoped, label-only) | Md. Nazmuz Saif | 1 | Done
ST-105 | Database | Create Designation model and migration | Md. Nazmuz Saif | 1 | Done
ST-105 | Backend | Build DesignationSerializer + DesignationViewSet | Md. Nazmuz Saif | 2 | Done
ST-105 | Frontend | Build Designations page (list, create, edit, delete) | Md. Nazmuz Saif | 2 | Done
ST-105 | Self-Test | Self-test Designation CRUD, scoped to own company | Md. Nazmuz Saif | 1 | Done
ST-106 | Design | Design self-referencing Employee hierarchy (reports_to) and circular-reference rule | Md. Nazmuz Saif | 2 | Done
ST-106 | Database | Create Employee model and migration with self-referencing reports_to FK | Md. Nazmuz Saif | 2 | Done
ST-106 | Backend | Build EmployeeSerializer + EmployeeViewSet; add circular-reference guard on reports_to | Md. Nazmuz Saif | 4 | Done
ST-106 | Frontend | Build Employees page (list, create, edit — manager/reports-to dropdown) | Md. Nazmuz Saif | 4 | Done
ST-106 | Self-Test | Self-test hierarchy assignment across levels and the circular-reference block | Md. Nazmuz Saif | 1 | Done
Overall Testing — QA Pass (Md. Tahsin Rahman Khan)
Story ID | Test Case No. | Test Case | Owner | Estimate (hrs) | Result
ST-101 | TC-01 | Register new company with valid data — expect Company, Settings, CEO Designation, User, Employee all created and a valid JWT returned | Md. Tahsin Rahman Khan | 1 | Passed
ST-101 | TC-02 | Submit registration with a missing required field — expect a validation error and no partial records created | Md. Tahsin Rahman Khan | 1 | Passed
ST-102 | TC-03 | Log in with valid credentials — expect access + refresh token returned | Md. Tahsin Rahman Khan | 1 | Passed
ST-102 | TC-04 | Log in with invalid credentials — expect a generic error message, no token issued | Md. Tahsin Rahman Khan | 1 | Passed
ST-103 | TC-05 | Attempt login as a user of a suspended company — expect a specific error and no token issued | Md. Tahsin Rahman Khan | 1 | Passed
ST-104 | TC-06 | Create a Department — expect it visible only within the creating company's list | Md. Tahsin Rahman Khan | 1 | Passed
ST-104 | TC-07 | Attempt to access another company's Department by ID — expect HTTP 404 | Md. Tahsin Rahman Khan | 1 | Passed
ST-105 | TC-08 | Create, edit, and delete a Designation — expect changes scoped to own company only | Md. Tahsin Rahman Khan | 1 | Passed
ST-106 | TC-09 | Assign an Employee's manager across a 3+ level hierarchy — expect the correct chain stored | Md. Tahsin Rahman Khan | 1 | Passed
ST-106 | TC-10 | Attempt to set an Employee as their own manager — expect the request rejected | Md. Tahsin Rahman Khan | 1 | Passed
Coordination Tasks (Montasim Kabir Mahin)
Task | Owner | Estimate (hrs) | Status
Sprint 1 planning session — select stories from backlog, confirm scope | Montasim Kabir Mahin | 2 | Done
Daily coordination and progress tracking | Montasim Kabir Mahin | 3 | Done
Sprint 1 review and retrospective facilitation | Montasim Kabir Mahin | 2 | Done
| Total Implementation Hours |  |  | 54
| Total QA Hours |  |  | 10
Total Coordination Hours |  | 7

## Sprint 2
Ordinis — Sprint 2 Planning
Sprint Duration: Sep 10 – Sep 23
Sprint Goal: Deliver the RBAC engine (Roles as Permission bundles, independent of Designation) and recursive hierarchy resolution, completing the Core Engine's access-control foundation.
Selected Stories for this Sprint
Story ID | User Story | Owner | Story Points | Acceptance Criteria
ST-107 | As a Department Head, I want the system to resolve my full list of subordinates automatically, so that I can see my whole team regardless of hierarchy depth. | Md. Nazmuz Saif | 5 | - Given an Employee, returns all direct and indirect subordinates - Given an Employee, returns the full chain of managers up to the top - Works for flat, 3-level, and 4+ level structures - Verified with real multi-level test data
ST-108 | As a CEO, I want to create custom Roles as bundles of Permissions, so that access rights are independent of job titles. | Montasim Kabir Mahin | 5 | - CEO can create a Role with a name and a list of Permission codenames - A Role is scoped to the CEO's own company - Roles are retrievable independent of any Designation
ST-109 | As a CEO, I want to assign one or more Roles to any Employee, so that I can grant exactly the access that person needs. | Sadia Jahan Disha | 3 | - CEO can assign a Role to any Employee in their company - An Employee can hold more than one Role at once - CEO can revoke a Role from an Employee
ST-110 | As the System, I want every protected action to check a specific Permission codename, so that access control never depends on a hardcoded job-title check. | Fawjiya Fahima Eifa | 5 | - Employee.has_permission(codename) correctly reflects the Employee's assigned Roles' Permissions - A protected endpoint rejects the request if the acting Employee lacks the required permission - Verified: an Employee without a Role cannot perform a Role-gated action
Carried Over from Sprint 1
Story ID | Category | Task | Owner | Estimate (hrs) | Status
(none — Sprint 1 fully completed)
Task Breakdown — one owner does the full story (Design → Database → Backend → Frontend → Self-Test)
Story ID | Category | Task | Owner | Estimate (hrs) | Status
ST-107 | Design | Design recursive traversal approach for subordinate/manager resolution over reports_to | Md. Nazmuz Saif | 2 | Done
ST-107 | Backend | Implement get_all_subordinates(employee) and get_all_managers(employee) service functions | Md. Nazmuz Saif | 4 | Done
ST-107 | Frontend | Show subordinate list on the Employee detail view | Md. Nazmuz Saif | 2 | Done
ST-107 | Self-Test | Self-test recursive resolution against a 4-level test hierarchy | Md. Nazmuz Saif | 1 | Done
ST-108 | Design | Design Permission/Role/RolePermission schema, formalizing the Designation-vs-Role separation | Montasim Kabir Mahin | 2 | To Do
ST-108 | Database | Create Permission and Role models and migrations | Montasim Kabir Mahin | 1 | To Do
ST-108 | Backend | Build PermissionSerializer (read-only) and RoleSerializer/ViewSet | Montasim Kabir Mahin | 3 | To Do
ST-108 | Frontend | Build Roles management page (create Role, select Permissions) | Montasim Kabir Mahin | 3 | To Do
ST-108 | Self-Test | Self-test Role creation/retrieval and company-level scoping | Montasim Kabir Mahin | 1 | To Do
ST-109 | Design | Design EmployeeRole schema (Employee <-> Role assignment) | Sadia Jahan Disha | 1 | To Do
ST-109 | Database | Create EmployeeRole model and migration | Sadia Jahan Disha | 1 | To Do
ST-109 | Backend | Build EmployeeRoleSerializer/ViewSet (assign/revoke) | Sadia Jahan Disha | 2 | To Do
ST-109 | Frontend | Add assign/revoke Role controls to the Employee page | Sadia Jahan Disha | 2 | To Do
ST-109 | Self-Test | Self-test assigning multiple Roles and revoking a Role | Sadia Jahan Disha | 1 | To Do
ST-110 | Design | Design the HasPermission / PermissionRequiredMixin enforcement approach | Fawjiya Fahima Eifa | 2 | To Do
ST-110 | Backend | Implement Employee.has_permission(), HasPermission DRF permission class, and PermissionRequiredMixin; apply across organization and rbac ViewSets | Fawjiya Fahima Eifa | 5 | To Do
ST-110 | Frontend | Hide/disable UI controls the current user lacks permission for | Fawjiya Fahima Eifa | 3 | To Do
ST-110 | Self-Test | Self-test that a permission-gated action is blocked without the permission and allowed with it | Fawjiya Fahima Eifa | 1 | To Do
Overall Testing — QA Pass (Md. Tahsin Rahman Khan)
Story ID | Test Case No. | Test Case | Owner | Estimate (hrs) | Result
ST-107 | TC-11 | Get subordinates for a mid-level manager in a 4-level tree — expect the correct full descendant list | Md. Tahsin Rahman Khan | 1 | Passed
ST-107 | TC-12 | Get the manager chain for a leaf-level Employee — expect the correct full ancestor chain | Md. Tahsin Rahman Khan | 1 | Passed
ST-108 | TC-13 | Create a Role with a chosen Permission set — expect it retrievable with the correct Permissions | Md. Tahsin Rahman Khan | 1 | Not Run
ST-108 | TC-14 | Create a Role in Company A — expect it invisible to Company B | Md. Tahsin Rahman Khan | 1 | Not Run
ST-109 | TC-15 | Assign two Roles to one Employee — expect both retained simultaneously | Md. Tahsin Rahman Khan | 1 | Not Run
ST-109 | TC-16 | Revoke one Role from an Employee — expect the associated permission no longer granted | Md. Tahsin Rahman Khan | 1 | Not Run
ST-110 | TC-17 | Employee without the required permission attempts a protected action — expect the request blocked | Md. Tahsin Rahman Khan | 1 | Not Run
ST-110 | TC-18 | Employee with the correct permission performs the same action — expect it allowed | Md. Tahsin Rahman Khan | 1 | Not Run
Coordination Tasks (Montasim Kabir Mahin)
Task | Owner | Estimate (hrs) | Status
Sprint 2 planning session — select stories from backlog, confirm scope | Montasim Kabir Mahin | 2 | Done
Daily coordination and progress tracking | Montasim Kabir Mahin | 3 | To Do
Sprint 2 review and retrospective facilitation | Montasim Kabir Mahin | 2 | To Do
| Total Implementation Hours |  |  | 37
| Total QA Hours |  |  | 8
Total Coordination Hours |  | 7